## INDEX
JAL REKHA – CYCLE 4 USER STORIES REGISTER (Jan 2026 – May 2026)
Prepared for: CMMI Level 5 Audit ¦ Project: Jal Rekha ¦ Department: PHED, Madhya Pradesh
Sr. No. | Sheet Name | Module / Area | No. of User Stories
1 | Anusharavan US | Anusharavan (RFI, Stages, Reports) | 6
2 | Asset Mapping US | Asset Mapping (GIS, Survey) | 2
3 | Bharosa US | Bharosa Factory Testing (Web + Mobile) | 4
4 | Cube Testing US | Cube Testing (Contractor / FE / GM / SQC) | 7
5 | Daily Inspection US | Daily Inspection | 1
6 | Dashboard US | Dashboard & Public Reports | 2
7 | Dhara US | Dhara (Reports, Meter, Mobile) | 8
8 | FHTC US | FHTC + AI Tap Connection | 3
9 | Master US | Master Module (GM / CR / Schema) | 2
10 | Material Testing US | Material Testing (GM / Contractor / FE) | 3
11 | Nirmal US | Nirmal (FE Mobile, GM, CR) | 3
12 | O&M Billing US | O&M Billing (GM / Contractor / Workflow) | 4
13 | Sahbhagita US | Sahbhagita (GM / CR / Reports) | 3
14 | SVS US | SVS Water Supply Monitoring – Har Ghar Jal | 12
15 | CMMI Doc US | CMMI Documentation + Dept Meetings | 4
16 | Site Security US | Site Security Audit | 1
17 | Sopan US | Sopan Contractor | 1
18 | User Role US | User & Role Management | 1
TOTAL USER STORIES – CYCLE 4 |  |  | 67

## Anusharavan US
Jal Rekha – Cycle 4 User Stories ¦ ANUSHARAVAN MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Anusharavan - NEW Stage Changes | US-ANS-C4-001 | As a system user, I want new RFI stages added to Anusharavan module so that the inspection workflow captures all required stages accurately. | AC1: New stages defined and added in RFI workflow configuration; AC2: Stage transitions validated with correct role permissions; AC3: Contractor and FE mobile app reflects new stages; AC4: GM dashboard displays stage-wise status counts; AC5: Notifications triggered on each stage change
Anusharavan - NEW Stage Changes | US-ANS-C4-002 | As a Field Engineer (FE), I want PIU inspection details added to the RFI form so that I can capture field-level data accurately during inspection. | AC1: FE inspection detail fields (PIU, Inspection Date, GPS, Remarks) added to RFI form; AC2: Mandatory field validation enforced before submission; AC3: Inspection date auto-populated but editable; AC4: PIU-wise inspection data visible in GM reports; AC5: Data persists across sessions
Anusharavan - Stage Updation | US-ANS-C4-003 | As a developer, I want existing RFI stages updated and history screen search enhanced so that users can quickly locate past inspection records. | AC1: History screen search functional for Contractor and FE login by scheme, date, and status; AC2: Search results load within 3 seconds; AC3: Post-fix verification of pipeline details on History Detail screen completed; AC4: Play Store live build tested and verified; AC5: No regression in existing stage functionality
Anusharavan - Report Creation/Modification | US-ANS-C4-004 | As a GM user, I want customized RFI reports with FE inspection details included so that I can generate PIU-wise performance reports. | AC1: Customized report includes FE inspection columns (PIU, Inspector Name, Inspection Date); AC2: Report filters by PIU, Scheme, Date Range operational; AC3: Export to Excel and PDF functional with all columns; AC4: Summary report shows aggregate counts per PIU; AC5: Report loads within 5 seconds for 500+ records
Anusharavan - Testing & Video | US-ANS-C4-005 | As a QA engineer, I want complete testing of Anusharavan module changes including a demo video so that all functionalities are validated before production release. | AC1: Test cases created for all new stage changes and report modifications; AC2: Internal testing pass rate 100% before UAT; AC3: UAT conducted with PHED stakeholders; AC4: All production defects logged and resolved; AC5: Demo video created covering new stages, inspection entry, and report generation
Anusharavan CR - FE Inspection PIU & Report | US-ANS-C4-006 | As a contractor, I want updated RFI workflow with FE Inspection date visible in PIU pending-for-action web page so that I can track pending inspections efficiently. | AC1: FE Inspection Date column added to PIU Pending for Action web page; AC2: Data sourced correctly from inspection records; AC3: Column sortable and filterable; AC4: Customized report updated to include FE Inspection date; AC5: CR changes tested in staging before production deployment

## Asset Mapping US
Jal Rekha – Cycle 4 User Stories ¦ ASSET MAPPING MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Asset Mapping - Bug Fixing & Redesign | US-AST-C4-001 | As a user, I want the Asset Mapping module redesigned and deployed to live server so that the interface is modern and all known bugs are resolved. | AC1: Redesigned pages deployed on live server; AC2: OHT search box functional with real-time filtering on map; AC3: All frontend bugs identified in previous cycle fixed; AC4: Accuracy field changes for Asset Mapping implemented; AC5: Data GET method updated per new specifications
Asset Mapping - Data Correction & Reports | US-AST-C4-002 | As an SQC/TPIA/Contractor user, I want dedicated report pages in Asset Mapping so that I can view and download survey and GIS data efficiently. | AC1: Report creation for SQC, TPIA, and Contractor login completed; AC2: Survey data download functionality (D&D format) operational; AC3: Field survey data correction tools available with audit trail; AC4: OHT village testing bug resolved; AC5: Move OHTs feature functional with validation; AC6: Video creation for module demonstration completed

## Bharosa US
Jal Rekha – Cycle 4 User Stories ¦ BHAROSA MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Bharosa - Factory Testing Web CR | US-BHR-C4-001 | As a developer, I want multiple document upload functionality added to the Bharosa Factory Testing web module so that inspectors can attach all evidence in one submission. | AC1: Multiple file upload (PDF, DOC, JPG, PNG) supported with progress indicator; AC2: Maximum 10 files per upload, each file ≤10MB; AC3: Uploaded documents viewable and downloadable from record; AC4: QAP document upload functionality included; AC5: UI updated in existing Bharosa web pages; AC6: Bug fixes applied to new functionality post-deployment
Bharosa - Factory Testing Web | US-BHR-C4-002 | As a system architect, I want database architecture designed and service APIs created for Bharosa Factory Testing so that all web and mobile components are supported by a robust backend. | AC1: DB schema designed with master check functionality; AC2: Service/API created for all Bharosa web pages (web and mobile); AC3: Factory Testing Contractor Login mobile page created; AC4: Unit, SIT, and UAT testing completed; AC5: Mobile app development and testing completed; AC6: Test cases and scenarios documented
Bharosa - Factory Testing Web | US-BHR-C4-003 | As a UI/UX designer, I want wireframes for Bharosa Factory Testing module created and UI enhanced so that development has clear specifications and the deployed UI is consistent. | AC1: Wireframes created for all screens including Inspector, GM, TPIA login; AC2: UI updated in existing pages per wireframe approval; AC3: Input field for unit added and unit details displayed correctly; AC4: Save as Draft, Image, and Video upload options implemented; AC5: Production deployment completed after successful testing
Bharosa CR - Factory Testing Mobile | US-BHR-C4-004 | As a mobile user, I want QAP document download functionality on the Bharosa mobile app so that field users can access quality assurance documents offline. | AC1: QAP document download feature added to mobile app; AC2: Download works for all supported formats (PDF, DOC); AC3: Offline access supported after download; AC4: Internal testing completed with zero critical defects; AC5: CR for mobile Bharosa factory testing applied and tested in production

## Cube Testing US
Jal Rekha – Cycle 4 User Stories ¦ CUBE TESTING MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Cube Testing Requirement - Gathering & Design | US-CUBE-C4-001 | As a business analyst, I want Cube Testing requirements gathered and wireframes created so that the development team has complete specifications for implementation. | AC1: Requirement gathering sessions conducted with Civil Engineers, Lab Technicians, and GM users; AC2: Wireframes created for web and mobile screens; AC3: Workflow documented (Sample Collection → Curing → 7-Day Test → 28-Day Test → Result → TPIA → GM Approval); AC4: DB schema, master and design tables defined; AC5: Business logic APIs and function/SP development completed
Cube Testing Requirement - Development | US-CUBE-C4-002 | As a developer, I want Cube Testing database functions, stored procedures, and web pages created so that the full testing lifecycle is supported on web and mobile. | AC1: DB schema with query optimization deployed; AC2: New web pages and UI updates completed per wireframes; AC3: Data validation and integrity checks implemented; AC4: Report creation/modification for Cube Testing functional; AC5: Internal testing and production deployment completed; AC6: Test cases, test scenarios, and test plan documents created
Cube Testing - Contractor Login | US-CUBE-C4-003 | As a contractor, I want to create cube inspection entries through the mobile/web application so that sample data is captured at the point of collection. | AC1: Contractor can create new cube inspection records (Component, Casting Date, Mix Design, Quantity); AC2: RFI Survey form API integrated with Cube Testing contractor login; AC3: Survey form with pagination and contractor history list functional; AC4: Requirement gathering and user stories created for contractor login; AC5: Internal and UAT/Prod testing completed with defects resolved
Cube Testing - FE Login | US-CUBE-C4-004 | As a Field Engineer, I want to record and submit cube test results after 7-day and 28-day curing periods so that compressive strength data is captured accurately. | AC1: FE Sync API integrated with FE Survey module; AC2: 7-day and 28-day check enforced before result submission; AC3: Cube inspection carried out by FE with GPS capture; AC4: FE Insert document functionality fixed for production issues; AC5: FE workflow tested end-to-end; AC6: Test scenarios and security test cases created
Cube Testing - GM / SQC / TPIA | US-CUBE-C4-005 | As a GM user, I want summary reports and Pending for Action page in Cube Testing so that I can monitor and approve cube test results across all schemes. | AC1: Summary reports created on GM login for 7-day and 28-day scenarios; AC2: GM Action Page with Pending for Action web page functional; AC3: RFI request status update and list view functional; AC4: Customized reports available from GM login; AC5: Bug fixes applied and production issues resolved
Cube Testing - SQC/TPIA | US-CUBE-C4-006 | As an SQC/TPIA user, I want web pages and APIs for SQC and TPIA login in Cube Testing so that I can verify and approve cube test results. | AC1: SQC login web pages and APIs created; AC2: TPIA login web pages and APIs created; AC3: Bug fixing in Cube Testing module completed; AC4: End-to-end testing of SQC/TPIA workflow completed; AC5: Test scenarios and test cases documented for SQC/TPIA login
Cube Testing CR | US-CUBE-C4-007 | As a department stakeholder, I want change requests for Cube Testing implemented including mandatory multiple image upload and manual component entry so that data quality is enhanced. | AC1: Mandatory multiple image upload functionality added to cube testing forms; AC2: Manual entry option for components added where dropdown is unavailable; AC3: New web page modifications per CR completed; AC4: CR testing conducted in staging and production; AC5: All CR items logged and tracked to closure

## Daily Inspection US
Jal Rekha – Cycle 4 User Stories ¦ DAILY INSPECTION MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Daily Inspection - Development & Fixes | US-DI-C4-001 | As a developer, I want Daily Inspection module bug fixes and new functionality implemented so that FE and GM users can perform inspections without technical issues. | AC1: Frontend, API, database, and mobile app bugs fixed with root cause documented; AC2: New web pages created/modified per requirements; AC3: GET/SET data access methods created and updated; AC4: Database architecture designed with master check functionality; AC5: Service/API created for all new inspection features; AC6: Production deployment and unit testing completed; AC7: Requirement gathering completed with stakeholder sign-off

## Dashboard US
Jal Rekha – Cycle 4 User Stories ¦ DASHBOARD MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Dashboard - Data & Wireframe | US-DASH-C4-001 | As a PM user, I want Dashboard data verified and Excel reports modified for all Jal Rekha modules so that the management dashboard reflects accurate real-time data. | AC1: Data verification completed for all modules on dashboard; AC2: Modified Excel reports generated for all Jal Rekha modules; AC3: Wireframes created for new dashboard widgets; AC4: Requirement gathering for dashboard enhancements documented; AC5: All dashboard KPIs tested for accuracy
All Public Reports on Dashboard | US-DASH-C4-002 | As a public user, I want all Jal Rekha module reports accessible on the public dashboard so that scheme performance data is transparently available. | AC1: Public reports enabled for all applicable modules on dashboard; AC2: CR/Prod/UAT bug testing completed for public reports; AC3: Internal testing pass rate 100% before enabling public access; AC4: Report load time <5 seconds for public dashboard; AC5: No authentication required for public report access

## Dhara US
Jal Rekha – Cycle 4 User Stories ¦ DHARA MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Dhara - Reports & UI Enhancement | US-DHR-C4-001 | As a GM user, I want updated DWSR, MWSR, UFW reports and new Approved Village Wise MWSR report so that I can monitor water supply performance at all levels. | AC1: DWSR Detailed and Datewise Report created with new pages; AC2: Approved Village Wise MWSR page created with service; AC3: Bulk Consumer MWSR Report created and integrated; AC4: HSC Summary Report page developed; AC5: Date filter enhancement in DWSR Report functional; AC6: UFW Report data corrections applied
Dhara - UI Update & Bug Fixes | US-DHR-C4-002 | As a developer, I want Dhara module inner pages redesigned and existing bugs fixed so that users experience a consistent and error-free interface. | AC1: New UI update applied to all Dhara inner pages; AC2: Bug fixes for report data issues (District data mismatch in DWSR DateWise Detailed Report) resolved; AC3: WTP Meter Mapping page issue and delete restriction changes fixed; AC4: Public Page Data Visibility Issue for PIU and Scheme 'ALL' selection resolved; AC5: SIT testing and UAT testing completed
Dhara - Meter Reading & Contractor Objection | US-DHR-C4-003 | As a GM and Contractor user, I want meter reading survey changes and contractor objection module implemented so that meter disputes are formally managed. | AC1: Contractor Objection Module UI and Modal created for Intake, WTP, ESR/OHT meters; AC2: Contractor Objection API and Database integrated; AC3: Meter reading survey updated for intake, WTP, OHT, and bulk for web and mobile; AC4: Approved status flow: FE → GM → Contractor enforced; AC5: Bulk Consumer and mapping added with update/recreate of Dhara reports
Dhara CR - Reports (MWSR, DWSR, UFW) | US-DHR-C4-004 | As a QA analyst, I want requirement gathering and internal testing for Dhara report changes so that MWSR, DWSR, and UFW reports are accurate and meet department expectations. | AC1: Requirement gathering of report changes completed and documented; AC2: Updated and recreated fetch for DWSR, MWSR, Bulk Consumer, Approved Reports, and UFW; AC3: Internal testing completed for all report changes; AC4: DWSR public report enhancements with new pages and services deployed; AC5: JavaScript modification for data loading issue resolved
Dhara - GM PIU User Change Request | US-DHR-C4-005 | As a GM PIU user, I want Dhara WTP meter reading issues resolved and intake meter reading survey changes implemented so that meter data is captured correctly. | AC1: WTP Meter Reading Issue identified and resolved for affected schemes; AC2: Intake meter reading survey changes implemented per department requirement; AC3: Bulk meter consumer reading survey form updated; AC4: Test case and scenario creation completed for all changes; AC5: Staging and production deployment completed
Dhara - Mobile Application | US-DHR-C4-006 | As a field user, I want a mobile application developed for Dhara module so that meter readings and survey data can be captured in the field. | AC1: Dhara mobile application development completed; AC2: All meter survey types (Intake, WTP, OHT, Bulk) supported on mobile; AC3: GPS capture and offline mode functional; AC4: Data sync with web portal on connectivity; AC5: Mobile app UAT/Prod testing completed; AC6: Knowledge transfer sessions conducted for field users
Dhara CR - OHT-WTP Village Meter Survey Rename & New Fields | US-DHR-C4-007 | As a GM and Contractor user, I want the OHT Meter Survey renamed to 'OHT-WTP Village Meter Survey' and new report fields added (Survey Date, Scheme, Component Name, Village Meter details, Reading Start/End, Total Clear Water Supplied, PE Remark) so that the survey captures complete village-level meter data accurately. | AC1: OHT Meter Survey module/page renamed to 'OHT-WTP Village Meter Survey' across web and mobile; AC2: New fields added to report (1. Survey Date, 2. Scheme, 3. Component Name, 4. Name of Village Meter, 5. Name of Village, 6. Habitation Name, 7. Local Name [new column], 8. Village Meter Status, 9. Village Meter Reading Start, 10. Village Meter Reading End, 11. Total Clear Water Supplied in Village [KL], 12. PE Survey Remark, 13. GM Remark); AC3: Conditional GM review flow: Is Objection? → Contractor Remark + Upload Doc; Is Approved? → Approved; Any Concern? → Contractor Remark + Upload Doc View; AC4: Database schema updated to support new columns; AC5: Existing OHT meter records migrated without data loss; AC6: Report tested for all 13 fields in staging and production
Dhara CR - GM ID Login Work Process Flow (Intake / WTP / OHT Meter Surveys) | US-DHR-C4-008 | As a GM user, I want a structured work process flow for reviewing Intake Meter Survey, WTP Meter Survey, and OHT Meter Survey pages in the Dhara module after login so that GM can systematically review all field data and take an approval decision (Objection / Approved / Any Concern). | AC1: GM login navigates to Dhara Module and can select Intake Meter Survey, WTP Meter Survey, or OHT-WTP Village Meter Survey pages; AC2: Each survey page displays: Survey Date, Scheme Name, Component Name, Total Water Data (KL), Meter Reading Start and End, FE/PE Survey Remark; AC3: GM can add GM Review Remark before making a decision; AC4: GM Decision options available: (a) Objection — triggers Contractor Remark entry + Document upload/view; (b) Approved — marks survey as accepted; (c) Any Concern — opens Contractor Remark + Upload Doc View; AC5: Decision status updates visible in survey list with timestamp and GM user ID; AC6: Workflow tested end-to-end for all three survey types (Intake, WTP, OHT) in staging and production

## FHTC US
Jal Rekha – Cycle 4 User Stories ¦ FHTC MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
FHTC FE Reports - Development | US-FHTC-C4-001 | As a developer, I want FHTC FE report pages created, APIs integrated, and existing queries/SPs modified so that FE and GM users have accurate tap connection reports. | AC1: New FHTC web pages created for FE reports; AC2: Mobile application API integration completed; AC3: Query/SP creation and modification for FHTC reports done; AC4: SIT testing, test cases, and test scenarios created; AC5: UAT/Prod/CR testing completed with all defects resolved
FHTC CR - Search & Reports | US-FHTC-C4-002 | As an FE and Contractor user, I want search functionality and customized summary report changes in FHTC so that I can locate specific tap connection records quickly. | AC1: Search functionality added to FE and Contractor login pages; AC2: Customized and summary report changes implemented; AC3: FHTC Loop functionality implemented for connected scheme validation; AC4: Report filter issues at column level resolved for GM/Contractor reports; AC5: Staging and production deployment with regression testing
FHTC - AI Module Tap Connection | US-FHTC-C4-003 | As a data scientist, I want AI/ML models implemented for FHTC Tap Connection monitoring so that predictive analytics can identify non-functional connections proactively. | AC1: ML model implemented for tap connection monitoring buffer region with other validations; AC2: Data Processing of FHTC Tap connections using AI models completed; AC3: Machine Learning Predictive Model implementation documented (effort captured, pending full deployment); AC4: Requirement gathering for AI module completed; AC5: Model training data processed from existing FHTC records

## Master US
Jal Rekha – Cycle 4 User Stories ¦ MASTER MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Master GM - Pipeline & Wireframes | US-MST-C4-001 | As a GM user, I want Pipeline Master data management with updated wireframes in the Master module so that infrastructure data is accurately maintained. | AC1: Pipeline Master data entry page created; AC2: New wireframes suggested by department implemented; AC3: Wireframe of Pipeline master data approved by stakeholders; AC4: GET/SET data access methods for Master GM created; AC5: SIT and UAT/Prod/CR testing completed
Master CR - Scheme Village OHT & Schema | US-MST-C4-002 | As a data admin, I want Scheme Village OHT Mapping and Bulk Consumer Master updated with delete functionality so that master data management is complete. | AC1: Scheme Village OHT Mapping and Report updations completed; AC2: Bulk Consumer Master (Add-Update-Get-Delete) implemented; AC3: Dhara Mapped Summary report changes in Abstract report applied; AC4: Dhara Master DWSR updations completed; AC5: Internal testing and CR testing for all master changes completed; AC6: Option for manual entry for Components added

## Material Testing US
Jal Rekha – Cycle 4 User Stories ¦ MATERIAL TESTING MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Material Testing - GM/Contractor Login - Development | US-MAT-C4-001 | As a development team, I want Material Testing module built with complete backend, frontend, and mobile support so that construction material quality is systematically recorded. | AC1: DB schema, master tables, and design tables created for Material Testing; AC2: Business Logic APIs for all workflows (Submit → GM → SQC → FE → GM Approval) created; AC3: GET/SET data access methods, function/SP development completed; AC4: New web pages and UI updates for GM and Contractor login; AC5: Mobile development for field engineers completed; AC6: SQC/TPIA login pages and APIs created
Material Testing - GM/Contractor Login - Testing | US-MAT-C4-002 | As a QA engineer, I want comprehensive testing of Material Testing module including wireframing, workflows, and production validation so that the module is ready for PHED use. | AC1: Wireframing and workflow documentation completed; AC2: Requirement gathering and analysis documented with stakeholder sign-off; AC3: Test case and scenario creation completed for all login types; AC4: Internal, SIT, staging, and UAT/PROD/CR testing completed; AC5: All production bugs resolved; AC6: Data validation and integrity checks verified in production
Material Testing - FE Login | US-MAT-C4-003 | As a Field Engineer, I want to receive material testing assignments and submit field test results through the mobile application so that testing data is captured at the site. | AC1: FE receives assignment notification on mobile app; AC2: Test result entry form with photo upload functional; AC3: GPS coordinates captured and validated for each test; AC4: Internal testing completed; AC5: UAT/Prod/CR testing completed with all critical defects resolved

## Nirmal US
Jal Rekha – Cycle 4 User Stories ¦ NIRMAL MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Nirmal FE Mobile - Development | US-NRM-C4-001 | As a Field Engineer, I want the Nirmal mobile app enhanced with geofencing, new water sampling module, and WTP/Raw Water reporting so that water quality monitoring is comprehensive. | AC1: Water Sampling Collection by Contractor functional; AC2: Geofencing implemented with 200m buffer for WTP/Intake sample collection; AC3: New module added to mobile application for Nirmal testing; AC4: New web pages created/modified for Nirmal reports; AC5: Nirmal Reports (Beneficiary, OHT, WTP, RawWater) accessible from web; AC6: SIT, UAT/Prod/CR testing completed
Nirmal FE Mobile - API & Wireframe | US-NRM-C4-002 | As a developer, I want API creation, UI updates, and unit testing for Nirmal FE mobile completed so that all Nirmal module endpoints are functional and stable. | AC1: API creation for all Nirmal mobile endpoints completed; AC2: UI updated in existing Nirmal mobile pages; AC3: Requirement gathering and wireframe completed for new features; AC4: Unit testing for module completed; AC5: Testing of Nirmal module completed with defect log maintained
Nirmal GM - Report Modification | US-NRM-C4-003 | As a GM user, I want Nirmal reports created/modified and beneficiary report issue resolved so that water quality data is accurately represented. | AC1: Report creation/modification for GM Nirmal login completed; AC2: Beneficiary report issue identified, root cause analysed, and fixed; AC3: Report loads within 5 seconds for 1000+ records; AC4: Export to Excel/PDF functional; AC5: Report changes tested and validated in production

## O&M Billing US
Jal Rekha – Cycle 4 User Stories ¦ O&M BILLING MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
O&M Billing GM - Development & Reports | US-OM-C4-001 | As a GM user, I want O&M Billing module with new web pages, reports, and partial billing support developed so that billing operations are accurate and auditable. | AC1: New web pages and UI updates for GM login completed; AC2: Partial O&M Bills functionality implemented; AC3: Bug fixes from frontend and database applied; AC4: GET/SET data access methods and Service/API created; AC5: Database architecture with master check designed; AC6: SIT and UAT/Prod/CR testing completed; AC7: Test cases and scenarios documented
O&M Billing GM - Requirement & CR | US-OM-C4-002 | As a BA/PM, I want requirement gathering, analysis, and change request implementation for O&M Billing GM module so that department expectations are met and GM/Contractor flow is finalized. | AC1: Requirement gathering and analysis completed for GM and Contractor flow; AC2: Internal meetings with team and department conducted and minuted; AC3: Census Population get from Scheme Village Master implemented; AC4: GM HSC Change implemented; AC5: Monitoring changes requirement documented
O&M Billing Workflow | US-OM-C4-003 | As a higher official, I want O&M Billing workflow between GM and higher officials defined and implemented so that billing approvals follow a structured escalation path. | AC1: Workflow documented with all roles (Contractor → GM → Higher Officials); AC2: Workflow requirement gathering completed; AC3: Approval hierarchy implemented with notifications at each stage; AC4: Workflow tested end-to-end with all role scenarios; AC5: Workflow diagram reviewed and approved by department
O&M Billing CR - Contractor | US-OM-C4-004 | As a contractor, I want bill generation flow, abstract page generation, complaint and pressure redressal sheets, and summary page changes implemented so that contractor billing is complete and compliant. | AC1: Contractor Bill generation flow updated with Approved Reports; AC2: 'Generate Abstract Page (Complaint Redressal Sheet)' and 'Pressure Redressal Sheet' enabled post Save & Submit; AC3: Generate Summary Page for Contractor side implemented; AC4: CR in Contractor Summary Page Abstract Report applied; AC5: Complaint Date column modification completed; AC6: Updation and validation addition in Dhara Reports from Contractor side done

## Sahbhagita US
Jal Rekha – Cycle 4 User Stories ¦ SAHBHAGITA MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Sahbhagita GM - Reports & Approval | US-SAH-C4-001 | As a GM user, I want Sahbhagita survey approval page and updated reports so that community participation surveys can be reviewed and approved formally. | AC1: New Survey Approval page created with pending survey list; AC2: Approve and Reject buttons functional with mandatory remarks on rejection; AC3: Report modifications visible in Sahbhagita Reports menu; AC4: Bug fixes from frontend applied; AC5: SIT and UAT/Prod/CR testing completed; AC6: Upload Activities through Web Portal functional
Sahbhagita CR - RA Bill & Save as Draft | US-SAH-C4-002 | As a PM user, I want RA Bill functionality on CP Manager and Save as Draft feature added to Sahbhagita module so that ISA billing and survey submissions are managed effectively. | AC1: RA Bill Functionality on CP Manager implemented; AC2: Save as Draft functionality added to Sahbhagita forms; AC3: ISA Bill Form linked to Scheme and District; AC4: Bill amount auto-calculated based on activity count and rate; AC5: Report changes tested and validated
Sahbhagita Report - New Web Page | US-SAH-C4-003 | As a developer, I want new Sahbhagita report web pages created so that GM and PM users can access community participation data in a structured format. | AC1: New web page created for Sahbhagita reports; AC2: Report layout improved with updated columns (Activity Type, Participation Count, NGO, ISA, Video Evidence); AC3: Filter options (Date range, Village, ISA, NGO) operational; AC4: Export to Excel/PDF functional; AC5: Report load time <3 seconds

## SVS US
Jal Rekha – Cycle 4 User Stories ¦ SVS MODULE – HAR GHAR JAL WATER SUPPLY MONITORING ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
SVS - Module Initiation & NIC API Integration | US-SVS-C4-001 | As a project manager, I want the SVS Water Supply Monitoring module initiated with formal requirement gathering and NIC Panchayat Darpan API finalized so that the development team has complete specifications and integration details before build begins. | AC1: Project module initiation meeting conducted and MoM documented with action owners; AC2: Requirement gathering sessions completed with PHE department stakeholders; AC3: Internal meeting conducted to finalize API endpoints and data contract from NIC Panchayat Darpan; AC4: Village Master data structure confirmed and mapped to SVS fields; AC5: SVS Daily Water Supply Wireframe created, reviewed, and approved by department; AC6: Database schema designed with required tables and field-level mapping documented
SVS - Daily Water Supply Data Entry Form | US-SVS-C4-002 | As a GP user or PHE field officer, I want a structured daily water supply data entry form with District, Block, GP, Village, and Household Connections pre-filled so that I can quickly record supply status without re-entering location details every day. | AC1: Form displays District, Block, GP, and Village based on logged-in user's jurisdiction (pre-filled by default); AC2: Household Connections Established (स्थापित घरेलू नल कनेक्शन) field displayed and auto-populated from Village Master; AC3: Water Supply Date (जल प्रदाय दिनांक) shown as a date picker with default value as today's date; AC4: Form validates mandatory fields before allowing submission; AC5: Submission confirmation message shown on success; AC6: Record saved to database with user ID, timestamp, and village code
SVS - Water Supply Date Picker | US-SVS-C4-003 | As a GP user, I want a date picker control on the SVS water supply entry form so that I can accurately select the date of water supply without manual text entry errors. | AC1: Date picker control (calendar widget) displayed for Water Supply Date field (जल प्रदाय दिनांक); AC2: Default date is current system date; AC3: Future dates restricted — only today or past dates selectable; AC4: Date format stored as DD-MM-YYYY in database; AC5: Date picker works on both desktop and mobile browser; AC6: Selected date visible clearly in the form before submission
SVS - Water Supply Status - YES Flow | US-SVS-C4-004 | As a GP user, I want to record YES (हाँ) water supply status for my village on a given date so that the system reflects successful daily supply and the dashboard shows green supply status. | AC1: YES option selectable from Water Supply Status field (Yes / No / Partial radio buttons or dropdown); AC2: On selecting YES, no additional mandatory fields are required; AC3: Record saved with status = YES, date, village code, and user ID; AC4: Dashboard and summary report reflect YES count for the selected date; AC5: GP and PHE login can view YES supply records in daily report; AC6: No Reason or Remark field displayed when YES is selected
SVS - Water Supply Status - NO Flow with Reason | US-SVS-C4-005 | As a GP user, I want to record NO (नहीं) supply status with a mandatory reason selection and remarks box so that the department can track and address supply failures with root cause data. | AC1: Selecting NO status displays a Reason for No Supply dropdown/radio list with options: Tubewell Failure, OHT Not Filled By MVS Contractor, Motor Pump Not Working, Valve cum Pump Operator Problem, Electricity Supply Problem, Pipeline Damage, Any Other (with Remarks); AC2: Reason field is mandatory when status is NO — form cannot be submitted without selection; AC3: When 'Any Other' selected, a free-text Remarks box opens and becomes mandatory; AC4: Remarks text box also opens by default when status is NO (open box in no of remark); AC5: Record saved with status = NO, reason code, and remarks; AC6: GM and district-level dashboard shows NO supply count with reason breakdown per village
SVS - Water Supply Status - PARTIAL Flow | US-SVS-C4-006 | As a GP user, I want to record PARTIAL (आंशिक) supply status with the number of connections that received water and a mandatory remarks box so that partial supply incidents are tracked with quantitative data. | AC1: Selecting PARTIAL status displays the field 'Connections Supplied Water (जल प्रदाय कनेक्शन की संख्या)' as a mandatory numeric input; AC2: Number of connections supplied must be less than or equal to total Household Connections Established; AC3: Remarks text box opens automatically when PARTIAL is selected (open box in partial of remark); AC4: Remarks field is mandatory for PARTIAL status; AC5: Record saved with status = PARTIAL, connections supplied count, and remarks; AC6: Dashboard shows PARTIAL supply count and connections percentage at village level
SVS - Partial Edit Feature | US-SVS-C4-007 | As a GP user or PHE officer, I want to partially edit a previously submitted daily water supply record so that data corrections can be made without deleting and re-entering the full record. | AC1: Partial Edit option available on submitted supply records within a configurable edit window (e.g., same day or 24 hours); AC2: User can change Water Supply Status, Reason (for NO), Connections Supplied (for PARTIAL), or Remarks without modifying Date or Village; AC3: Edit action logs the original values and new values in an audit trail with editor user ID and timestamp; AC4: Edited records flagged as 'Modified' in reports with original and updated values traceable; AC5: Only authorized roles (GP user, PHE officer) can perform Partial Edit; AC6: Edit window enforced — records beyond the allowed window require supervisor approval to edit
SVS - Default Hierarchy Selection by Login | US-SVS-C4-008 | As a logged-in GP or PHE user, I want District, Block, and GP to be auto-selected by default based on my login credentials so that I do not need to manually navigate the location hierarchy every time I enter data. | AC1: On login, the system identifies the user's assigned District, Block, and GP from the user profile; AC2: District, Block, and GP fields in the data entry form are pre-filled and locked for GP-level users; AC3: PHE/Block-level users can see their default jurisdiction but may change Block or Village within their scope; AC4: District-level users see all Blocks and GPs with no default lock; AC5: Default selection is correctly applied in all SVS forms (Data Entry, Edit, Report filters); AC6: No manual re-selection required for GP user across multiple daily submissions
SVS - Hindi Interface (MP Shasan Labels) | US-SVS-C4-009 | As an MP government user, I want the SVS water supply entry form to display field labels in Hindi (MP Shasan standard) so that GP-level and rural users can use the system in their native language without language barriers. | AC1: All SVS form labels displayed in bilingual format (Hindi + English) or Hindi only based on language setting; AC2: Water Supply Date → 'जल प्रदाय दिनांक', Status → 'जल प्रदाय की स्थिति', YES → 'हाँ', NO → 'नहीं', PARTIAL → 'आंशिक' applied; AC3: Household Connections label shows 'स्थापित घरेलू नल कनेक्शन'; AC4: Reason dropdown options displayed in Hindi; AC5: MP Shasan (मध्यप्रदेश शासन) branding/header applied per department standard; AC6: Hindi rendering tested on Chrome and mobile Android browser without font issues
SVS - Remove Unwanted Fields (JJM, Village Status, Hand Over Community) | US-SVS-C4-010 | As a PHE department stakeholder, I want the JJM field, village status field, and hand over community field removed from the SVS supply monitoring form so that the form is focused, clutter-free, and aligned to current department requirements. | AC1: JJM (Jal Jeevan Mission) field removed from SVS data entry form and all related report columns; AC2: Village Status field removed from the SVS form; AC3: Hand Over Community field removed from SVS form; AC4: Database columns for removed fields retained (not deleted) but not exposed in UI or reports; AC5: Existing historical records with these fields remain accessible via admin view; AC6: Removal changes tested and verified in staging before production deployment; AC7: Report templates updated to exclude removed fields
SVS - Excel Report with LGD Code and Household Join | US-SVS-C4-011 | As a PHE data analyst or district officer, I want Excel downloadable reports from SVS that include the LGD Code and Household Connections data joined to each village record so that reports can be cross-referenced with national LGD data and household surveys. | AC1: SVS Excel download report includes LGD Code column for each village; AC2: Household Connections Established count joined from Village Master to the Excel report per village; AC3: LGD Code and Household data sourced from authorized master tables (IMS/Panchayat Darpan); AC4: Excel report columns: District, Block, GP, Village, LGD Code, Household Connections, Supply Date, Status, Reason (if NO), Connections Supplied (if PARTIAL), Remarks; AC5: Date range filter available for Excel download (daily, weekly, monthly); AC6: Excel download works within 10 seconds for up to 1000 village records
SVS - Dashboard: Village / Block / District Level Monitoring | US-SVS-C4-012 | As a PHE department official, I want a SVS monitoring dashboard showing daily water supply status (YES / NO / PARTIAL counts) at village, block, and district level with drill-down navigation so that supply performance is visible at all governance levels. | AC1: Dashboard displays total villages vs supply submitted count for the selected date; AC2: Status breakdown shown: YES count (green), NO count (red), PARTIAL count (amber), Not Submitted (grey); AC3: District → Block → GP → Village drill-down navigation functional; AC4: Date filter (single date or range) available on dashboard; AC5: Reason for NO supply breakdown visible as a sub-panel or tooltip at village level; AC6: Dashboard data refreshes automatically or on demand; AC7: Dashboard accessible to PHE, GM, District, and Block-level login roles with appropriate scope restriction; AC8: 1 Scheme = 1 Handpump monitoring aligned for SVS scheme type

## CMMI Doc US
Jal Rekha – Cycle 4 User Stories ¦ CMMI DOC MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
CMMI Doc - Data Collection & Documentation Cycle 4 | US-CMMI-C4-001 | As a SEPG team member, I want to collect data for Cycle 4 (Jan to May 2026) so that I can measure project performance metrics and prepare CMMI Level 5 audit artifacts. | AC1: Data collection sheet created with all required fields (Requirement Efforts, Design Efforts, Coding Effort, Code Review, Testing Effort); AC2: Data collected for all Cycle 4 modules (Anusharavan, Bharosa, Cube Testing, Dhara, FHTC, Material Testing, Nirmal, O&M Billing, Sahbhagita, SVS, Master, Asset Mapping); AC3: Defect data captured (Requirement Review, Design Review, Code Review, Internal Testing, UAT, Production); AC4: Productivity, DRE, and Cycle Time calculated automatically; AC5: Data validated for accuracy and completeness
CMMI Doc - Streamline Documentation | US-CMMI-C4-002 | As a quality manager, I want CMMI documentation streamlined for O&M Billing, Bharosa, and Material modules so that audit artifacts are consistent and complete. | AC1: Streamline documentation completed for O&M Billing, Bharosa, and Material Testing modules; AC2: CMMI documents created and reviewed per CMMI L5 standards; AC3: Induction training attended by relevant team members; AC4: Promote activity for CMMI L5 Audit completed; AC5: All documents archived in repository with version control
CMMI Doc - Phase 1 to 4 Completion | US-CMMI-C4-003 | As a SEPG team member, I want CMMI documentation completed across all four phases for Cycle 4 so that the project is fully prepared for CMMI Level 5 audit. | AC1: Phase 1 CMMI documentation completed (Planning, Estimation); AC2: Phase 2 CMMI documentation completed (Requirements, Design); AC3: Phase 3 CMMI documentation completed (Coding, Code Review); AC4: Phase 4 CMMI documentation completed (Testing, Deployment); AC5: All phases reviewed and approved by SEPG Head; AC6: Data collection for January to May cycle completed and baselined
Department Meetings - Requirement Gathering | US-CMMI-C4-004 | As a BA/PM, I want department meetings conducted for all module requirements and changes so that all stakeholder needs are documented and tracked. | AC1: Department meetings conducted for all modules (Nirmal, Bharosa, O&M Billing, Dhara, Cube Testing, Material Testing); AC2: Discussion on new material and cube testing modules documented; AC3: Requirement gathering for changes and updations completed across all modules; AC4: Meeting minutes with action items and owners distributed within 24 hours; AC5: Requirements tracked to implementation via traceability matrix

## Site Security US
Jal Rekha – Cycle 4 User Stories ¦ SITE SECURITY MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Site Security Audit | US-SEC-C4-001 | As a security team member, I want Jal Rekha site Fortify security audit conducted so that all security vulnerabilities are identified and remediated before production. | AC1: Fortify security audit tool configured and run on Jal Rekha codebase; AC2: All critical and high severity vulnerabilities identified and documented; AC3: Remediation plan created with owners and timelines; AC4: Site security audit report prepared and submitted to department; AC5: Dhara module specific security issues identified and resolved

## Sopan US
Jal Rekha – Cycle 4 User Stories ¦ SOPAN MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Sopan Contractor - Development & Testing | US-SOP-C4-001 | As a contractor, I want the Sopan Contractor module with dashboard, data upload, and new web pages functional so that scheme-level contractor activities are properly managed. | AC1: Dashboard creation for Sopan Contractor completed; AC2: Upload Activities through Web Portal functional; AC3: New web pages and data access methods (GET/SET) created; AC4: OHT data correction completed; AC5: Bug fixes from database applied; AC6: Requirement gathering completed; AC7: SIT, UAT/Prod/CR testing and testing of new functionality completed

## User Role US
Jal Rekha – Cycle 4 User Stories ¦ USER ROLE MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
User & Role Management - Testing | US-URM-C4-001 | As a QA engineer, I want functional and SIT testing of User and Role Management module completed so that all access controls and permissions are verified before release. | AC1: Functional testing completed for all user roles across all modules; AC2: SIT testing completed; AC3: Permission matrix verified for all role-module combinations; AC4: No unauthorized access identified; AC5: Test report submitted and reviewed