## INDEX
JAL REKHA – CYCLE 4 USER STORIES REGISTER (Jan 2026 – May 2026)
Prepared for: CMMI Level 5 Audit ¦ Project: Jal Rekha ¦ Department: PHED, Madhya Pradesh
Sr. No. | Sheet Name | Module / Area | No. of User Stories
1 | Anusharavan US | Anusharavan (RFI, Stages, Reports) | 6
2 | Asset Mapping US | Asset Mapping (GIS, Survey) | 3
3 | Bharosa US | Bharosa Factory Testing (Web + Mobile) | 4
4 | Cube Testing US | Cube Testing (Contractor / FE / GM / SQC) | 7
5 | Daily Inspection US | Daily Inspection | 2
6 | Dashboard US | Dashboard & Public Reports | 4
7 | Dhara US | Dhara (Reports, Meter, Mobile) | 12
8 | FHTC US | FHTC + AI Tap Connection | 11
9 | Master US | Master Module (GM / CR / Schema) | 11
10 | Material Testing US | Material Testing (GM / Contractor / FE) | 11
11 | Nirmal US | Nirmal (FE Mobile, GM, CR) | 5
12 | O&M Billing US | O&M Billing (GM / Contractor / Workflow) | 13
13 | Sahbhagita US | Sahbhagita (GM / CR / Reports) | 4
14 | SVS US | SVS Water Supply Monitoring – Har Ghar Jal | 12
15 | CMMI Doc US | CMMI Documentation + Dept Meetings | 4
16 | Site Security US | Site Security Audit | 1
17 | Sopan US | Sopan Contractor | 1
18 | User Role US | User & Role Management | 1
TOTAL USER STORIES – CYCLE 4 |  |  | 112

## Anusharavan US
Jal Rekha – Cycle 4 User Stories ¦ ANUSHARAVAN MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Anusharavan - NEW Stage Changes | US-ANS-C4-001 | As a system user, I want new RFI stages added to Anusharavan module so that the inspection workflow captures all required stages accurately. | AC1: New stages defined and added in RFI workflow configuration; AC2: Stage transitions validated with correct role permissions; AC3: Contractor and FE mobile app reflects new stages; AC4: GM dashboard displays stage-wise status counts; AC5: Notifications triggered on each stage change
Anusharavan - NEW Stage Changes | US-ANS-C4-002 | As a Field Engineer (FE), I want PIU inspection details added to the RFI form so that I can capture field-level data accurately during inspection. | AC1: FE inspection detail fields (PIU, Inspection Date, GPS, Remarks) added to RFI form; AC2: Mandatory field validation enforced before submission; AC3: Inspection date auto-populated but editable; AC4: PIU-wise inspection data visible in GM reports; AC5: Data persists across sessions
Anusharavan - Stage Updation | US-ANS-C4-003 | As a developer, I want existing RFI stages updated and history screen search enhanced so that users can quickly locate past inspection records. | AC1: History screen search functional for Contractor and FE login by scheme, date, and status; AC2: Search results load within 3 seconds; AC3: Post-fix verification of pipeline details on History Detail screen completed; AC4: Play Store live build tested and verified; AC5: No regression in existing stage functionality
Anusharavan - Report Creation/Modification | US-ANS-C4-004 | As a GM user, I want customized RFI reports with FE inspection details included so that I can generate PIU-wise performance reports. | AC1: Customized report includes FE inspection columns (PIU, Inspector Name, Inspection Date); AC2: Report filters by PIU, Scheme, Date Range operational; AC3: Export to Excel and PDF functional with all columns; AC4: Summary report shows aggregate counts per PIU; AC5: Report loads within 5 seconds for 500+ records
Anusharavan - Testing & Video | US-ANS-C4-005 | As a QA engineer, I want complete testing of Anusharavan module changes including a demo video so that all functionalities are validated before production release. | AC1: Test cases created for all new stage changes and report modifications; AC2: Internal testing pass rate 100% before UAT; AC3: UAT conducted with PHED stakeholders; AC4: All production defects logged and resolved; AC5: Demo video created covering new stages, inspection entry, and report generation
Anusharavan CR - FE Inspection PIU & Report | US-ANS-C4-006 | As a contractor, I want updated RFI workflow with FE Inspection date visible in PIU pending-for-action web page so that I can track pending inspections efficiently. | AC1: FE Inspection Date column added to PIU Pending for Action web page; AC2: Data sourced correctly from inspection records; AC3: Column sortable and filterable; AC4: Customized report updated to include FE Inspection date; AC5: CR changes tested in staging before production deployment

## Asset Mapping US
Jal Rekha – Cycle 4 User Stories ¦ ASSET MAPPING MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Asset Mapping - Bug Fixing & Redesign | US-AST-C4-001 | As a user, I want the Asset Mapping module redesigned and deployed to live server so that the interface is modern and all known bugs are resolved. | AC1: Redesigned pages deployed on live server; AC2: OHT search box functional with real-time filtering on map; AC3: All frontend bugs identified in previous cycle fixed; AC4: Accuracy field changes for Asset Mapping implemented; AC5: Data GET method updated per new specifications
Asset Mapping - Data Correction & Reports | US-AST-C4-002 | As an SQC/TPIA/Contractor user, I want dedicated report pages in Asset Mapping so that I can view and download survey and GIS data efficiently. | AC1: Report creation for SQC, TPIA, and Contractor login completed; AC2: Survey data download functionality (D&D format) operational; AC3: Field survey data correction tools available with audit trail; AC4: OHT village testing bug resolved; AC5: Move OHTs feature functional with validation; AC6: Video creation for module demonstration completed
Asset Mapping CR - GPS Accuracy Field, Move OHTs & Survey Download | US-AST-C4-003 | As a developer and SQC/TPIA user, I want GPS accuracy field added to Asset Mapping, Move OHTs functionality implemented, and field survey data download (D&D format) enabled so that field survey data quality is measurable and OHT records can be repositioned without data loss. | AC1: GPS Accuracy field added to Asset Mapping API and local database for Anusharavan and Sahbhagita modules; AC2: New field to save location accuracy implemented for both asset survey and GP survey activities; AC3: Move OHTs functionality implemented with validation — moved OHT retains all mapping and survey data; AC4: Field survey data download in D&D format operational from SQC, TPIA, and Contractor login; AC5: OHT Village Testing bug resolved for production environment; AC6: Data correction tools for field survey available with audit trail; AC7: Asset Mapping module UI and OHT search on map tested in staging and production

## Bharosa US
Jal Rekha – Cycle 4 User Stories ¦ BHAROSA MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Bharosa - Factory Testing Web CR | US-BHR-C4-001 | As a developer, I want multiple document upload functionality added to the Bharosa Factory Testing web module so that inspectors can attach all evidence in one submission. | AC1: Multiple file upload (PDF, DOC, JPG, PNG) supported with progress indicator; AC2: Maximum 10 files per upload, each file ≤10MB; AC3: Uploaded documents viewable and downloadable from record; AC4: QAP document upload functionality included; AC5: UI updated in existing Bharosa web pages; AC6: Bug fixes applied to new functionality post-deployment
Bharosa - Factory Testing Web | US-BHR-C4-002 | As a system architect, I want database architecture designed and service APIs created for Bharosa Factory Testing so that all web and mobile components are supported by a robust backend. | AC1: DB schema designed with master check functionality; AC2: Service/API created for all Bharosa web pages (web and mobile); AC3: Factory Testing Contractor Login mobile page created; AC4: Unit, SIT, and UAT testing completed; AC5: Mobile app development and testing completed; AC6: Test cases and scenarios documented
Bharosa - Factory Testing Web | US-BHR-C4-003 | As a UI/UX designer, I want wireframes for Bharosa Factory Testing module created and UI enhanced so that development has clear specifications and the deployed UI is consistent. | AC1: Wireframes created for all screens including Inspector, GM, TPIA login; AC2: UI updated in existing pages per wireframe approval; AC3: Input field for unit added and unit details displayed correctly; AC4: Save as Draft, Image, and Video upload options implemented; AC5: Production deployment completed after successful testing
Bharosa CR - Factory Testing Mobile | US-BHR-C4-004 | As a mobile user, I want QAP document download functionality on the Bharosa mobile app so that field users can access quality assurance documents offline. | AC1: QAP document download feature added to mobile app; AC2: Download works for all supported formats (PDF, DOC); AC3: Offline access supported after download; AC4: Internal testing completed with zero critical defects; AC5: CR for mobile Bharosa factory testing applied and tested in production

## Cube Testing US
Jal Rekha – Cycle 4 User Stories ¦ CUBE TESTING MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Cube Testing Requirement - Gathering & Design | US-CUBE-C4-001 | As a business analyst, I want Cube Testing requirements gathered and wireframes created so that the development team has complete specifications for implementation. | AC1: Requirement gathering sessions conducted with Civil Engineers, Lab Technicians, and GM users; AC2: Wireframes created for web and mobile screens; AC3: Workflow documented (Sample Collection → Curing → 7-Day Test → 28-Day Test → Result → TPIA → GM Approval); AC4: DB schema, master and design tables defined; AC5: Business logic APIs and function/SP development completed
Cube Testing Requirement - Development | US-CUBE-C4-002 | As a developer, I want Cube Testing database functions, stored procedures, and web pages created so that the full testing lifecycle is supported on web and mobile. | AC1: DB schema with query optimization deployed; AC2: New web pages and UI updates completed per wireframes; AC3: Data validation and integrity checks implemented; AC4: Report creation/modification for Cube Testing functional; AC5: Internal testing and production deployment completed; AC6: Test cases, test scenarios, and test plan documents created
Cube Testing - Contractor Login | US-CUBE-C4-003 | As a contractor, I want to create cube inspection entries through the mobile/web application so that sample data is captured at the point of collection. | AC1: Contractor can create new cube inspection records (Component, Casting Date, Mix Design, Quantity); AC2: RFI Survey form API integrated with Cube Testing contractor login; AC3: Survey form with pagination and contractor history list functional; AC4: Requirement gathering and user stories created for contractor login; AC5: Internal and UAT/Prod testing completed with defects resolved
Cube Testing - FE Login | US-CUBE-C4-004 | As a Field Engineer, I want to record and submit cube test results after 7-day and 28-day curing periods so that compressive strength data is captured accurately. | AC1: FE Sync API integrated with FE Survey module; AC2: 7-day and 28-day check enforced before result submission; AC3: Cube inspection carried out by FE with GPS capture; AC4: FE Insert document functionality fixed for production issues; AC5: FE workflow tested end-to-end; AC6: Test scenarios and security test cases created
Cube Testing - GM / SQC / TPIA | US-CUBE-C4-005 | As a GM user, I want summary reports and Pending for Action page in Cube Testing so that I can monitor and approve cube test results across all schemes. | AC1: Summary reports created on GM login for 7-day and 28-day scenarios; AC2: GM Action Page with Pending for Action web page functional; AC3: RFI request status update and list view functional; AC4: Customized reports available from GM login; AC5: Bug fixes applied and production issues resolved
Cube Testing - SQC/TPIA | US-CUBE-C4-006 | As an SQC/TPIA user, I want web pages and APIs for SQC and TPIA login in Cube Testing so that I can verify and approve cube test results. | AC1: SQC login web pages and APIs created; AC2: TPIA login web pages and APIs created; AC3: Bug fixing in Cube Testing module completed; AC4: End-to-end testing of SQC/TPIA workflow completed; AC5: Test scenarios and test cases documented for SQC/TPIA login
Cube Testing CR | US-CUBE-C4-007 | As a department stakeholder, I want change requests for Cube Testing implemented including mandatory multiple image upload and manual component entry so that data quality is enhanced. | AC1: Mandatory multiple image upload functionality added to cube testing forms; AC2: Manual entry option for components added where dropdown is unavailable; AC3: New web page modifications per CR completed; AC4: CR testing conducted in staging and production; AC5: All CR items logged and tracked to closure

## Daily Inspection US
Jal Rekha – Cycle 4 User Stories ¦ DAILY INSPECTION MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Daily Inspection - Development & Fixes | US-DI-C4-001 | As a developer, I want Daily Inspection module bug fixes and new functionality implemented so that FE and GM users can perform inspections without technical issues. | AC1: Frontend, API, database, and mobile app bugs fixed with root cause documented; AC2: New web pages created/modified per requirements; AC3: GET/SET data access methods created and updated; AC4: Database architecture designed with master check functionality; AC5: Service/API created for all new inspection features; AC6: Production deployment and unit testing completed; AC7: Requirement gathering completed with stakeholder sign-off
Daily Inspection - GPS Accuracy Field & Mobile Enhancement | US-DI-C4-002 | As a Field Engineer, I want GPS accuracy field added to Daily Inspection mobile entries and the mobile application enhanced with accuracy validation so that inspection location data is reliable and meets geolocation quality standards. | AC1: GPS Accuracy field added to Daily Inspection API and local mobile database; AC2: Accuracy value captured automatically during GPS coordinate recording in the mobile app; AC3: Accuracy threshold validation implemented — submissions with accuracy below threshold flagged or blocked based on configuration; AC4: Accuracy field visible in GM and admin reports for quality monitoring; AC5: Daily Inspection mobile app changes deployed and tested on Android devices; AC6: Regression testing of existing Daily Inspection workflow completed after accuracy field addition

## Dashboard US
Jal Rekha – Cycle 4 User Stories ¦ DASHBOARD MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Dashboard - Data & Wireframe | US-DASH-C4-001 | As a PM user, I want Dashboard data verified and Excel reports modified for all Jal Rekha modules so that the management dashboard reflects accurate real-time data. | AC1: Data verification completed for all modules on dashboard; AC2: Modified Excel reports generated for all Jal Rekha modules; AC3: Wireframes created for new dashboard widgets; AC4: Requirement gathering for dashboard enhancements documented; AC5: All dashboard KPIs tested for accuracy
All Public Reports on Dashboard | US-DASH-C4-002 | As a public user, I want all Jal Rekha module reports accessible on the public dashboard so that scheme performance data is transparently available. | AC1: Public reports enabled for all applicable modules on dashboard; AC2: CR/Prod/UAT bug testing completed for public reports; AC3: Internal testing pass rate 100% before enabling public access; AC4: Report load time <5 seconds for public dashboard; AC5: No authentication required for public report access
Dashboard - Login Page & Module Pages UI Redesign | US-DASH-C4-003 | As a developer, I want the Jal Rekha portal login page and all module inner pages redesigned with a consistent card-based UI layout, updated sidebar menu icons, and full mobile responsiveness so that the application provides a modern and unified user experience across all modules. | AC1: Login page redesigned and responsive across different screen sizes and devices; AC2: Sidebar menu icons updated for improved visual consistency for all modules (Aakalan, Parinam, Bharosa, Sopan, Material Testing, Nirmal); AC3: Sidebar scroll color customized to align with design theme; AC4: Card-based HTML design pattern created as a reusable component for all inner pages; AC5: All table alignment issues on dashboard inner pages fixed; AC6: Modal popup design improved — alignment and data presentation inside popup tables corrected; AC7: Accessibility tool and popup overlapping issues resolved across all modules; AC8: Final UI testing and cross-device verification completed
Dashboard - SVS & GP Daily Water Supply Integration | US-DASH-C4-004 | As a department official, I want the SVS daily water supply data integrated into the Dhara and main dashboard so that GP-level water supply status (YES/NO/PARTIAL) is visible alongside existing scheme monitoring data, providing a consolidated daily supply view. | AC1: GP Daily Water Supply page linked from Dhara module dashboard; AC2: Village-level supply status (YES/NO/PARTIAL) counts displayed in dashboard summary widgets; AC3: Dashboard filter allows selection of District, Block, GP to scope supply status view; AC4: Non-submitted village count displayed distinctly (grey) alongside supply status counts; AC5: Dashboard data for SVS module visible on the public reports dashboard with date filter; AC6: Dashboard SVS supply data refreshes on demand or auto-updates every configured interval; AC7: Accessibility and mobile responsiveness tested for dashboard SVS integration

## Dhara US
Jal Rekha – Cycle 4 User Stories ¦ DHARA MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Dhara - Reports & UI Enhancement | US-DHR-C4-001 | As a GM user, I want updated DWSR, MWSR, UFW reports and new Approved Village Wise MWSR report so that I can monitor water supply performance at all levels. | AC1: DWSR Detailed and Datewise Report created with new pages; AC2: Approved Village Wise MWSR page created with service; AC3: Bulk Consumer MWSR Report created and integrated; AC4: HSC Summary Report page developed; AC5: Date filter enhancement in DWSR Report functional; AC6: UFW Report data corrections applied
Dhara - UI Update & Bug Fixes | US-DHR-C4-002 | As a developer, I want Dhara module inner pages redesigned and existing bugs fixed so that users experience a consistent and error-free interface. | AC1: New UI update applied to all Dhara inner pages; AC2: Bug fixes for report data issues (District data mismatch in DWSR DateWise Detailed Report) resolved; AC3: WTP Meter Mapping page issue and delete restriction changes fixed; AC4: Public Page Data Visibility Issue for PIU and Scheme 'ALL' selection resolved; AC5: SIT testing and UAT testing completed
Dhara - Meter Reading & Contractor Objection | US-DHR-C4-003 | As a GM and Contractor user, I want meter reading survey changes and contractor objection module implemented so that meter disputes are formally managed. | AC1: Contractor Objection Module UI and Modal created for Intake, WTP, ESR/OHT meters; AC2: Contractor Objection API and Database integrated; AC3: Meter reading survey updated for intake, WTP, OHT, and bulk for web and mobile; AC4: Approved status flow: FE → GM → Contractor enforced; AC5: Bulk Consumer and mapping added with update/recreate of Dhara reports
Dhara CR - Reports (MWSR, DWSR, UFW) | US-DHR-C4-004 | As a QA analyst, I want requirement gathering and internal testing for Dhara report changes so that MWSR, DWSR, and UFW reports are accurate and meet department expectations. | AC1: Requirement gathering of report changes completed and documented; AC2: Updated and recreated fetch for DWSR, MWSR, Bulk Consumer, Approved Reports, and UFW; AC3: Internal testing completed for all report changes; AC4: DWSR public report enhancements with new pages and services deployed; AC5: JavaScript modification for data loading issue resolved
Dhara - GM PIU User Change Request | US-DHR-C4-005 | As a GM PIU user, I want Dhara WTP meter reading issues resolved and intake meter reading survey changes implemented so that meter data is captured correctly. | AC1: WTP Meter Reading Issue identified and resolved for affected schemes; AC2: Intake meter reading survey changes implemented per department requirement; AC3: Bulk meter consumer reading survey form updated; AC4: Test case and scenario creation completed for all changes; AC5: Staging and production deployment completed
Dhara - Mobile Application | US-DHR-C4-006 | As a field user, I want a mobile application developed for Dhara module so that meter readings and survey data can be captured in the field. | AC1: Dhara mobile application development completed; AC2: All meter survey types (Intake, WTP, OHT, Bulk) supported on mobile; AC3: GPS capture and offline mode functional; AC4: Data sync with web portal on connectivity; AC5: Mobile app UAT/Prod testing completed; AC6: Knowledge transfer sessions conducted for field users
Dhara CR - OHT-WTP Village Meter Survey Rename & New Fields | US-DHR-C4-007 | As a GM and Contractor user, I want the OHT Meter Survey renamed to 'OHT-WTP Village Meter Survey' and new report fields added (Survey Date, Scheme, Component Name, Village Meter details, Reading Start/End, Total Clear Water Supplied, PE Remark) so that the survey captures complete village-level meter data accurately. | AC1: OHT Meter Survey module/page renamed to 'OHT-WTP Village Meter Survey' across web and mobile; AC2: New fields added to report (1. Survey Date, 2. Scheme, 3. Component Name, 4. Name of Village Meter, 5. Name of Village, 6. Habitation Name, 7. Local Name [new column], 8. Village Meter Status, 9. Village Meter Reading Start, 10. Village Meter Reading End, 11. Total Clear Water Supplied in Village [KL], 12. PE Survey Remark, 13. GM Remark); AC3: Conditional GM review flow: Is Objection? → Contractor Remark + Upload Doc; Is Approved? → Approved; Any Concern? → Contractor Remark + Upload Doc View; AC4: Database schema updated to support new columns; AC5: Existing OHT meter records migrated without data loss; AC6: Report tested for all 13 fields in staging and production
Dhara CR - GM ID Login Work Process Flow (Intake / WTP / OHT Meter Surveys) | US-DHR-C4-008 | As a GM user, I want a structured work process flow for reviewing Intake Meter Survey, WTP Meter Survey, and OHT Meter Survey pages in the Dhara module after login so that GM can systematically review all field data and take an approval decision (Objection / Approved / Any Concern). | AC1: GM login navigates to Dhara Module and can select Intake Meter Survey, WTP Meter Survey, or OHT-WTP Village Meter Survey pages; AC2: Each survey page displays: Survey Date, Scheme Name, Component Name, Total Water Data (KL), Meter Reading Start and End, FE/PE Survey Remark; AC3: GM can add GM Review Remark before making a decision; AC4: GM Decision options available: (a) Objection — triggers Contractor Remark entry + Document upload/view; (b) Approved — marks survey as accepted; (c) Any Concern — opens Contractor Remark + Upload Doc View; AC5: Decision status updates visible in survey list with timestamp and GM user ID; AC6: Workflow tested end-to-end for all three survey types (Intake, WTP, OHT) in staging and production
Dhara - GP Daily Water Supply Page | US-DHR-C4-009 | As a developer and GP user, I want a dedicated frm_GP_Daily_Water_Supply page in the Dhara module so that GP users can view and manage daily water supply status entries against their assigned villages in a card-based responsive layout. | AC1: frm_GP_Daily_Water_Supply page created with header, filter section, and card components; AC2: Cards display Village, Date, Supply Status, and Connection count per entry; AC3: Filter section includes District, Block, GP dropdowns populated from master data; AC4: Page is fully mobile-responsive for use on Android devices in the field; AC5: Input and text fields aligned with proper spacing for mobile usability; AC6: Page integrated with SVS water supply data for Dhara module dashboard view
Dhara CR - Meter Reading Approval Flow (FE → GM → Contractor) | US-DHR-C4-010 | As a department stakeholder, I want the Dhara meter reading approval process redesigned so that Field Engineer (FE) entries are first reviewed and approved by GM, then the Contractor is notified with a 3-day window to raise concerns, after which the record is auto-approved if no objection is raised. | AC1: FE submits meter reading → status set to 'Pending GM Review'; AC2: GM reviews and approves meter reading → status updated to 'GM Approved' and Contractor notified; AC3: Contractor has 3-day window to raise concern or objection on the approved reading; AC4: If Contractor raises concern within 3 days → GM review triggered again; AC5: If no concern raised within 3 days → record auto-approved and locked; AC6: All status transitions logged with user ID, timestamp, and comments; AC7: Approval flow applies to Intake, WTP, OHT, and Bulk Consumer meter readings on both web and mobile
Dhara CR - Bulk Consumer Meter Survey Form Changes | US-DHR-C4-011 | As a field user, I want the Bulk Consumer meter reading survey form updated so that each supply point under a village is shown separately with its local name, and the mobile app displays all supply points in a list format for a single beneficiary's data entry. | AC1: Bulk consumer supply points shown individually per village in the mobile form with local name visible; AC2: Single beneficiary can enter readings for all supply points associated to their village in list format; AC3: Supply point local name and component name shown clearly in the form; AC4: Reading fields (Start, End, Total Water KL) available per supply point; AC5: Contractor Dispute option visible on Contractor login for Bulk Consumer survey; AC6: Form layout tested on mobile Android for usability across various screen sizes; AC7: Changes deployed to both web view and mobile app versions
Dhara CR - Contractor Objection Module (All Meter Types) | US-DHR-C4-012 | As a Contractor user, I want to formally raise objections on Intake, WTP, OHT, and Bulk Consumer meter survey readings through a dedicated Contractor Objection module so that disputed readings are tracked, reviewed by GM, and resolved with an audit trail. | AC1: Contractor Objection modal/page created for Intake Meter Survey, WTP Meter Survey, OHT Meter Survey, and Bulk Consumer Meter Survey; AC2: Objection form includes: Reason for Objection (dropdown), Remarks (text), Document Upload option; AC3: Objection API and database tables created and integrated; AC4: GM receives notification on contractor objection and can respond with resolution or override; AC5: Objection status visible on both Contractor and GM logins (Pending / Resolved / Overridden); AC6: All objection records maintained in audit trail with timestamps; AC7: End-to-end testing of objection workflow completed for all four meter types

## FHTC US
Jal Rekha – Cycle 4 User Stories ¦ FHTC MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
FHTC FE Reports - Development | US-FHTC-C4-001 | As a developer, I want FHTC FE report pages created, APIs integrated, and existing queries/SPs modified so that FE and GM users have accurate tap connection reports. | AC1: New FHTC web pages created for FE reports; AC2: Mobile application API integration completed; AC3: Query/SP creation and modification for FHTC reports done; AC4: SIT testing, test cases, and test scenarios created; AC5: UAT/Prod/CR testing completed with all defects resolved
FHTC CR - Search & Reports | US-FHTC-C4-002 | As an FE and Contractor user, I want search functionality and customized summary report changes in FHTC so that I can locate specific tap connection records quickly. | AC1: Search functionality added to FE and Contractor login pages; AC2: Customized and summary report changes implemented; AC3: FHTC Loop functionality implemented for connected scheme validation; AC4: Report filter issues at column level resolved for GM/Contractor reports; AC5: Staging and production deployment with regression testing
FHTC - AI Module Tap Connection | US-FHTC-C4-003 | As a data scientist, I want AI/ML models implemented for FHTC Tap Connection monitoring so that predictive analytics can identify non-functional connections proactively. | AC1: ML model implemented for tap connection monitoring buffer region with other validations; AC2: Data Processing of FHTC Tap connections using AI models completed; AC3: Machine Learning Predictive Model implementation documented (effort captured, pending full deployment); AC4: Requirement gathering for AI module completed; AC5: Model training data processed from existing FHTC records
FHTC CR - Loop / Re-inspection Functionality (Contractor & Mobile) | US-FHTC-C4-004 | As a Contractor user, I want Loop (Re-inspection) functionality added to the FHTC module so that previously rejected tap connections can be re-submitted for inspection with a new RFI request, and I can view the history, accepted, and rejected lists from my login. | AC1: Re-inspection (Loop) functionality implemented for Contractor login in web and mobile; AC2: History Screen, Accepted List, Rejected List, and Re-inspection Form UI designed and API-integrated for Contractor; AC3: Re-inspection Form captures reason for re-submission, new geo-tagged photos, and updated connection details; AC4: New database function and API endpoint created for Contractor re-inspection workflow; AC5: FHTC Loop functionality tested end-to-end on mobile Android application; AC6: SIT, UAT/Prod testing completed with all defects resolved
FHTC CR - Loop / Re-inspection Functionality (FE, SQC, TPIA) | US-FHTC-C4-005 | As a Field Engineer, SQC, and TPIA user, I want Re-inspection (Loop) workflows added to my login in FHTC so that I can review, validate, and action re-inspection requests initiated by the Contractor. | AC1: FE login History Screen updated with re-inspection records and sync changes for offline support; AC2: Re-inspection list screen implementation and API integration completed for FE login; AC3: Re-inspection form UI and data submission implemented for FE login; AC4: SQC and TPIA review capability for re-inspection requests implemented; AC5: FHTC Loop functionality tested for all roles (FE, SQC, TPIA) in staging and production; AC6: Add View Logs functionality implemented for tracking inspection history per connection; AC7: Regression testing completed to ensure no impact on existing FHTC inspection flow
FHTC CR - GM/Contractor Reports & Excel Export Enhancement | US-FHTC-C4-006 | As a GM and Contractor user, I want FHTC reports with dynamic Excel export functionality so that I can download filtered tap connection reports with module-wise file naming, proper column headers, and non-export columns hidden. | AC1: GM and Contractor FHTC reports updated with report filter issues resolved at column level; AC2: Excel export updated with dynamic file name (module-wise), sheet name, and header title per export specification; AC3: Non-export columns (Action, Image, Document) hidden from Excel download; AC4: Customized summary report changes implemented for FHTC Contractor and FE login; AC5: Parinam report issue analyzed and fixed; AC6: Report load and export tested for 1000+ records within 10 seconds
FHTC CR - Search Functionality & UI Enhancement | US-FHTC-C4-007 | As an FE and Contractor user, I want search functionality added to FHTC history and report pages, along with overall UI enhancement, so that I can quickly locate specific tap connection records without scrolling through long lists. | AC1: Search functionality added to FE and Contractor login history pages; AC2: Search filters by scheme, village, status, and date range; AC3: FHTC module UI enhancement completed — improved navigation, table layout, and responsive design; AC4: Search results load within 3 seconds for up to 500 records; AC5: Mobile app search and UI updates deployed and tested; AC6: Internal and UAT/Prod testing completed with all critical defects resolved
FHTC CR - Mobile API Integration for GM Login & FE Sync | US-FHTC-C4-008 | As a developer, I want FHTC mobile API integration completed for GM Login and FE Sync so that GM can review tap connection submissions from the mobile app and FE Sync correctly pushes offline inspection records to the server. | AC1: FHTC Mobile API created for GM Login — GM can view pending tap connections, approve, and send back from mobile; AC2: New database function and API endpoint created for GM login contractor-level and FE-level data access; AC3: FE History Screen updated with sync changes for offline inspection records — sync status visible per record; AC4: FE Re-Inspection List API integration completed for offline and online modes; AC5: Mobile API response format standardised across GM, FE, Contractor, SQC, and TPIA login types; AC6: API authentication token handling tested and verified for all role-based mobile endpoints; AC7: SIT and UAT/Prod testing completed for all FHTC mobile API endpoints with defect tracker updated
FHTC CR - Loop (Re-inspection) for PIU Side, Reports & SQC/TPIA Review | US-FHTC-C4-009 | As a PIU administrator and SQC/TPIA user, I want the FHTC Loop (Re-inspection) functionality extended to PIU-side pages and SQC/TPIA review screens so that re-inspection requests are trackable end-to-end across all roles. | AC1: FHTC Loop functionality implemented for PIU login — PIU can see re-inspection requests per scheme with current status; AC2: SQC and TPIA review pages updated to flag records that are in Re-inspection (Loop) status; AC3: Re-inspection count added to FHTC Summary Report for GM and PIU views; AC4: FHTC Loop functionality for PIU side deployed — PIU can filter tap connections by Re-inspection status; AC5: SQC/TPIA can approve or reject a re-inspected tap connection with mandatory remarks; AC6: As per change request, FHTC Loop functionality tested for PIU side and Contractor Side in production; AC7: Defect log for Loop PIU functionality maintained; all critical defects resolved before production release
FHTC CR - Internal Testing, Bug Re-testing & Parinam Report Fix | US-FHTC-C4-010 | As a QA engineer, I want comprehensive internal testing, bug re-testing for all FHTC change requests, and the Parinam Report issue fixed so that all FHTC functionality is stable and report data is accurate before production release. | AC1: FHTC Internal Testing completed — all CRs (Loop, Search, GM Reports, AI Module) covered in test plan; AC2: Bug Re-testing performed after developer fixes — re-test pass rate 100% before UAT sign-off; AC3: Parinam Report issue identified (data count mismatch between FHTC and Parinam report) — root cause analysed and fixed; AC4: Test Case Creation for all FHTC CR items: Loop, Re-inspection, Search, GM/Contractor reports, API; AC5: Test Scenario Creation for FHTC module including edge cases (offline sync, partial submission, duplicate records); AC6: FHTC module regression test suite executed — no regression on existing tap connection submission flow; AC7: UAT/Prod/CR testing completed with all defects resolved and testing sign-off obtained from department
FHTC CR - Report Filter Issues, Excel Module Header & View Logs | US-FHTC-C4-011 | As a GM and Contractor user, I want FHTC report filter issues resolved at column level, Excel module header properly branded, and View Logs functionality added so that reports are accurate, identifiable, and inspection history is traceable per tap connection. | AC1: Report filter issues at column level resolved for GM and Contractor reports — filter applied correctly to all visible and hidden columns; AC2: Modified Excel export in Jal Nigam Portal by updating dynamic file name, sheet name, and header title per FHTC module branding; AC3: Non-export columns (Action, Image, Document) hidden from Excel download across all FHTC reports; AC4: View Logs functionality added to FHTC — each tap connection shows a timeline of inspection events (Submitted → FE Inspected → SQC Verified → GM Approved → Re-inspection if any); AC5: View Logs modal accessible from Contractor and GM login history pages; AC6: FHTC module overall UI enhancement completed — table layout, pagination controls, and responsive design updated; AC7: All report and UI changes deployed to production and verified by QA with regression test sign-off

## Master US
Jal Rekha – Cycle 4 User Stories ¦ MASTER MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Master GM - Pipeline & Wireframes | US-MST-C4-001 | As a GM user, I want Pipeline Master data management with updated wireframes in the Master module so that infrastructure data is accurately maintained. | AC1: Pipeline Master data entry page created; AC2: New wireframes suggested by department implemented; AC3: Wireframe of Pipeline master data approved by stakeholders; AC4: GET/SET data access methods for Master GM created; AC5: SIT and UAT/Prod/CR testing completed
Master CR - Scheme Village OHT & Schema | US-MST-C4-002 | As a data admin, I want Scheme Village OHT Mapping and Bulk Consumer Master updated with delete functionality so that master data management is complete. | AC1: Scheme Village OHT Mapping and Report updations completed; AC2: Bulk Consumer Master (Add-Update-Get-Delete) implemented; AC3: Dhara Mapped Summary report changes in Abstract report applied; AC4: Dhara Master DWSR updations completed; AC5: Internal testing and CR testing for all master changes completed; AC6: Option for manual entry for Components added
Master CR - Census Population Integration in Scheme Village Master | US-MST-C4-003 | As a data admin and GM user, I want Census Population (2011) and Projected Population (2025) auto-fetched and integrated into the Scheme Village Master during insert and edits so that demographic data supports O&M Billing calculations accurately. | AC1: Trigger function implemented to auto-fetch census data from census_village_population table during village insert in mvs_sc_covered_villages; AC2: Manual override flag implemented so saved manual values take priority over auto-fetched census data; AC3: Get_CensusVillageList query modified to show saved data first, then census data; AC4: Edit mode correctly reflects updated population values without regression; AC5: COALESCE and CASE-based null handling implemented to avoid null population errors; AC6: Insert, Update, and Fetch operations tested end-to-end for duplicate village mapping restriction; AC7: Census data auto-fetch also integrated into O&M Billing contract census section with auto-save flow
Master CR - Bulk Consumer Master (Add / Update / Get / Delete) | US-MST-C4-004 | As a data admin, I want complete CRUD (Add, Update, Get, Delete/Disable) functionality in the Bulk Consumer Master so that bulk water consumers (ULB, Industrial, Commercial) are managed accurately with proper audit controls and mapping support. | AC1: Bulk Consumer Master Add, Update, Get, and Delete/Disable operations implemented on web pages and via APIs; AC2: Delete/Disable functionality with validation — active supply point records prevented from deletion with an appropriate message; AC3: Urban/rural consumer classification correctly handled using is_consume_type field (not ulb_cd); AC4: ULB name displayed only for ULB consumers (is_consume_type = 1) in reports; AC5: Bulk Consumer Mapping page (Frm_BulkMeterMapping.aspx) updated with correct data binding; AC6: Multiple bulk consumer mappings from the same OHT source enabled (new rule replacing single-mapping restriction); AC7: All operations tested on Local and UAT environments before production deployment
Master CR - Bulk Consumer Supply Mapping & WTP Meter Integration | US-MST-C4-005 | As a data admin, I want Bulk Consumer Supply Mapping enhanced with WTP meter_id integration so that each bulk consumer supply point is accurately linked to its WTP meter, enabling correct billing and Dhara meter reading reports. | AC1: meter_id column added to mst_bulk_consumer_supply_mapping table for WTP meter tracking; AC2: GET_METER_LIST query added to fetch WTP meter list for mapping; AC3: INSERT_BULK_CONSUMER_SUPPLY_MAPPING updated to accept meter_id; AC4: GET_BULK_SUPPLY_POINT_REPORT and GET_BULK_CONSUMER_REPORT updated to show meter_id and meter_name (for WTP component_id=6 only, using CASE WHEN); AC5: meter_id NULL handling for OHT using NULLIF cast for backward compatibility; AC6: Duplicate row issue in report resolved using meter_id + component_id = 6 join condition; AC7: Dhara Mapped Summary / Abstract report updated with Bulk Consumer Master changes; AC8: WTP meter selection, meter_id, and meter_name verified in both reports on UAT
Master CR - OHT Village Mapping Bug Fixes & Abstract Report | US-MST-C4-006 | As a developer and data admin, I want OHT Village Mapping bug fixes applied and a new Bulk Meter Mapping Abstract Report created so that OHT re-mapping and bulk consumer mapping data is accurate and reportable. | AC1: Trigger function check_unique_habitation_cd() fixed by adding is_active = 1 filter to ignore inactive/deleted habitation records during re-mapping; AC2: Village deactivation and re-add to OHT mapping tested without habitation duplicate error; AC3: Get_ohsr_oht_vill_mapping query optimized: fixed non-sargable WHERE conditions, removed redundant DISTINCT, and resolved data type cast issues on join columns; AC4: HSC Summary Report (Get_HSC_Summary) created with metrics: Total Surveyed OHTs, Total OHTs in Dhara Master, Total Villages, Permitted Villages, Total HSC Count for permitted villages; AC5: Bulk Meter Update Fix implemented to correctly handle insert-delete vs direct-update pattern in UPDATE_SUPPLY_POINT_BY_MAPPINGID; AC6: Abstract Report for Bulk Meter Mapping created as a new page; AC7: All changes tested in Local and UAT before production deployment
Master CR - WTP Meter Mapping & Intake Data (Vistrit Module) | US-MST-C4-007 | As a data admin, I want WTP Meter Mapping and Intake Well data managed in the Master module (Vistrit Dhara module) so that each WTP is linked to a specific meter and intake readings can be traced to a named source, enabling accurate Dhara meter reports. | AC1: WTP Meter Mapping page created in Vistrit/Master module with Add, Edit, View, and Delete functions; AC2: Each WTP record linked to one or more meter IDs with effective dates for active/inactive tracking; AC3: Intake Well data (name, source, GPS coordinates) manageable from Master module; AC4: Meter list API (GET_METER_LIST) returns only active meters for the selected WTP; AC5: WTP meter mapping changes trigger auto-update of historical readings via trg_auto_update_wtp_meter_readings trigger; AC6: Vistrit module WTP Meter Mapping & Intake Data deployed to Production and verified; AC7: Bulk Consumer supply mapping updated to include meter_id from WTP Meter Mapping table
Master CR - Scheme Village Mapping Validation Rules & HSC Change Restriction | US-MST-C4-008 | As a data admin and GM user, I want strict validation rules enforced on Scheme Village Mapping so that duplicate village assignments are blocked, HSC changes follow a controlled process, and the mapping page name clearly reflects the operation being performed. | AC1: Duplicate village mapping restriction enforced — same village cannot be added under two active schemes simultaneously; AC2: Village mapping date validation implemented — mapping date must fall within scheme start and end dates; AC3: HSC Change Restriction implemented — GM can only modify HSC count within approved limits; changes beyond limit require supervisor approval; AC4: Scheme Village Mapping page name updated to clearly differentiate Add vs Edit vs View operations; AC5: OHT Village Mapping tab name confirmed or updated per department discussion; AC6: Validation messages displayed clearly for each rule violation with field-level highlighting; AC7: All validation rules tested in UAT with multi-scheme, multi-village, and edge-case scenarios
Master CR - Manual Component Entry Option (Material Testing & Cube Testing) | US-MST-C4-009 | As a Contractor user in Material Testing and Cube Testing modules, I want a manual text-entry option for Components wherever the dropdown list is unavailable or incomplete so that field data is never blocked due to missing master data. | AC1: Manual entry text field displayed when 'Other / Not in List' selected from Component dropdown; AC2: Manual component name saved alongside a flag (is_manual_entry = true) in the database; AC3: Manually entered components visible in GM and SQC/TPIA review pages with 'Manual Entry' indicator; AC4: Admin can promote manually entered components to the master dropdown after review; AC5: Manual entry option available in both Material Testing and Cube Testing Contractor login forms; AC6: Sub-Component search functionality extended to include manually entered components in search results; AC7: Data integrity maintained — manual entries stored per scheme and contractor without affecting standard master data
Master CR - DB Schema Objects: Views, PL/pgSQL Functions & Query Optimisation | US-MST-C4-010 | As a database administrator, I want Master module database schema updated with optimised views, PL/pgSQL functions, and stored procedures so that all master data queries perform within SLA and support all reporting and mapping use cases. | AC1: Schema objects (views, functions, procedures) created and updated for Scheme Village Master, OHT Master, and Bulk Consumer Master; AC2: Get_ohsr_oht_vill_mapping SP optimised — non-sargable WHERE conditions fixed, redundant DISTINCT removed, habitation aggregation moved to CTE; AC3: fn_bulk_meter_mapping function fixed — INSERT-DELETE pattern replaced with direct UPDATE to resolve duplicate key constraint on UPDATE_SUPPLY_POINT_BY_MAPPINGID; AC4: Data type cast issues on join columns resolved across all Master module SPs; AC5: New Get_HSC_Summary query developed for HSC Summary Report (Total OHTs surveyed, OHTs in Dhara master, total villages, permitted villages, HSC count); AC6: All schema objects versioned in SVN repository; AC7: Query execution time validated — all Master queries return within 3 seconds for 10,000+ record datasets on UAT
Master CR - Dhara OHT / Scheme / Bulk Consumer Report Validation & Co-ordination | US-MST-C4-011 | As a BA and data admin, I want Master module changes coordinated with Dhara reports so that OHT, Scheme, and Bulk Consumer data in Dhara reports always reflects the current Master data and count mismatches are eliminated. | AC1: Dhara Reports (Bulk, OHT, Scheme, DWSR) validated against Master module after each Master CR deployment; AC2: Bulk Consumer report columns confirmed after post-add display issue resolved; AC3: Dhara Mapped Summary report updated per Abstract report changes from Master module; AC4: Dhara Master DWSR updations completed — scheme-wise DWSR now reflects WTP and OHT master data accurately; AC5: OHT Village Mapping bulk consumer supply mapping validated — 4 unmapped consumers identified and mapped correctly for test scheme; AC6: Count reconciliation report created to compare Master data totals vs Dhara report totals; AC7: Co-ordination process documented — any Master CR triggers a Dhara report validation cycle before production release

## Material Testing US
Jal Rekha – Cycle 4 User Stories ¦ MATERIAL TESTING MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Material Testing - GM/Contractor Login - Development | US-MAT-C4-001 | As a development team, I want Material Testing module built with complete backend, frontend, and mobile support so that construction material quality is systematically recorded. | AC1: DB schema, master tables, and design tables created for Material Testing; AC2: Business Logic APIs for all workflows (Submit → GM → SQC → FE → GM Approval) created; AC3: GET/SET data access methods, function/SP development completed; AC4: New web pages and UI updates for GM and Contractor login; AC5: Mobile development for field engineers completed; AC6: SQC/TPIA login pages and APIs created
Material Testing - GM/Contractor Login - Testing | US-MAT-C4-002 | As a QA engineer, I want comprehensive testing of Material Testing module including wireframing, workflows, and production validation so that the module is ready for PHED use. | AC1: Wireframing and workflow documentation completed; AC2: Requirement gathering and analysis documented with stakeholder sign-off; AC3: Test case and scenario creation completed for all login types; AC4: Internal, SIT, staging, and UAT/PROD/CR testing completed; AC5: All production bugs resolved; AC6: Data validation and integrity checks verified in production
Material Testing - FE Login | US-MAT-C4-003 | As a Field Engineer, I want to receive material testing assignments and submit field test results through the mobile application so that testing data is captured at the site. | AC1: FE receives assignment notification on mobile app; AC2: Test result entry form with photo upload functional; AC3: GPS coordinates captured and validated for each test; AC4: Internal testing completed; AC5: UAT/Prod/CR testing completed with all critical defects resolved
Material Testing - Mobile App - Contractor Login | US-MAT-C4-004 | As a Contractor, I want Material Testing Contractor login implemented on the mobile application with RFI survey form, offline data storage, inspection request history, and detail screen so that material inspection is captured at the site without connectivity dependency. | AC1: Contractor Inspection Request Form with local database storage and Insert API Integration completed; AC2: Offline data list and detail screen UI designed and functional for Contractor login; AC3: Material Testing Contractor RFI Survey form pagination, offline mode, and sync API completed; AC4: Contractor history list with API integration and detail page UI built; AC5: FE inspection date added to Material Testing Module web pages on GM, SQC, and TPIA login; AC6: Material Testing Module overall module enhancement and testing completed for Contractor login; AC7: Internal testing, UAT, and production deployment completed with critical defects resolved
Material Testing - Mobile App - FE Login History, Detail & Form Screens | US-MAT-C4-005 | As a Field Engineer, I want Material Testing FE login mobile app screens implemented including inspection form, history list, and detail screen so that FE can review, carry out, and submit material testing assignments directly from the field. | AC1: FE Login History and Detail screen UI and API Integration completed; AC2: FE Inspection Form screen with material testing parameter UI and API changes functional; AC3: Save as Draft and OHT Search functionality added to FE login; AC4: FE Login mobile – Sync data API integration completed; AC5: Material and Cube Testing Sub-component search functionality added for FE login; AC6: FE login UI enhancement completed for offline and online modes; AC7: Material Testing FE Login module uploaded on Play Store and production tested
Material Testing CR - Sub-Component Search & Production Bug Fixes | US-MAT-C4-006 | As a developer and QA engineer, I want sub-component search functionality added to Material Testing and Cube Testing, and all production bugs fixed so that users can quickly find specific components and test data entry is accurate. | AC1: Sub-Component search functionality added to Material Testing and Cube Testing forms (web and mobile); AC2: Material Testing production issues fixed including API token issue in UAT, null value handling in sync API; AC3: Bug fixing in Material Testing database (query optimization, type mismatch, function modification) completed; AC4: Material Testing module deployed to UAT environment after unit testing with Sunil Sir; AC5: Resolving issue in Material Testing UAT API token issue completed; AC6: Code review and UAT deployment completed; AC7: Final production build tested for regression across all Material Testing roles
Material Testing - HLD/LLD Documentation & CMMI Artifacts | US-MAT-C4-007 | As a QA and CMMI team member, I want HLD, LLD, code review checklists, DAR documents, and unit test cases created for the Material Testing module so that complete CMMI Level 5 documentation is in place for audit readiness. | AC1: Material Testing HLD (High-Level Design) document created and reviewed; AC2: Material Testing LLD (Low-Level Design) document created with logic, validations, and calculation details; AC3: Code Review Checklist document created for Material Testing module per CMMI standards; AC4: DAR (Design Analysis and Resolution) document created for Material Testing covering issue analysis, impact, and resolution; AC5: Unit test cases recreated for all Material Testing web pages as per BRTM document; AC6: All CMMI artifacts uploaded to SVN repository with version control; AC7: Defects locked in Promot for Material Testing per CMMI audit requirements
Material Testing - SQC / TPIA Login Web Pages, APIs & End-to-End Testing | US-MAT-C4-008 | As an SQC and TPIA user, I want dedicated web pages and backend APIs for my login in the Material Testing module so that I can review contractor inspection submissions, add verification remarks, and approve or reject test results as per the Anusharavan-defined workflow. | AC1: SQC login web pages created with Pending for Action list, Inspection Detail view, Approve/Reject actions; AC2: TPIA login web pages and APIs created with role-specific scope (TPIA sees only schemes assigned to their organisation); AC3: SQC and TPIA review workflow implemented per Anusharavan flow — Contractor submits → FE carries → SQC verifies → TPIA final verification → GM approval; AC4: FE Inspection Date displayed on GM, SQC, and TPIA login web pages; AC5: Business Logic APIs created for SQC: Get Pending List, Get Inspection Detail, Update Status (Approve/Reject with remarks); AC6: Test Scenarios and Test Cases created for SQC and TPIA login flows; AC7: Internal testing, SIT, and UAT/Prod testing completed with defects resolved and logged in defect tracker
Material Testing - GM Login: PIU Pending Page, Customised Report & Data Access | US-MAT-C4-009 | As a GM user, I want a GM login Pending-for-PIU page, a customised Material Testing report, and role-based data access configured so that I can monitor all material inspection activities across my jurisdiction and take action on pending records. | AC1: GM login Pending-for-PIU page created showing all inspection records awaiting PIU action, filterable by scheme, date, and material type; AC2: Customised Material Testing report for GM login includes columns: Scheme, Component, Material Type, Contractor, Inspection Date, FE, SQC Status, TPIA Status, Final Result; AC3: Role-based data access implemented — GM sees only schemes under their PIU jurisdiction; AC4: GM can generate Material Testing summary report filtered by date range, scheme, material type, and result (Pass/Fail); AC5: Report export to Excel/PDF functional with proper headers and column widths; AC6: Analysis of SQC TPIA login flows documented and suggested implementation changes shared with team; AC7: GM login Material Testing pages deployed to UAT and verified against data in production environment
Material Testing - Database Functions, SPs & Null Value Handling | US-MAT-C4-010 | As a database administrator, I want all Material Testing database functions, stored procedures, and API null-value handling implemented and tested so that data integrity is maintained across mobile sync, web insert, and report generation operations. | AC1: Material Testing DB schema with master check functionality deployed with required tables (mst_material_type, mat_inspection_master, mat_inspection_details); AC2: Business Logic functions and stored procedures created for all workflows (Insert, Get, Update, Sync); AC3: Material Testing Sync data null values handled in API and Database — null fields given default values before insert; AC4: Material Testing Get Data API for Mobile App created and OHT ID parameter added to Insert API; AC5: API issue for Material Testing Mobile App resolved — token validation, null field handling, and sync-response format corrected; AC6: Merge code of Material Testing Mobile API after changes completed and verified on local and UAT servers; AC7: Function development and modification completed for all Material Testing SP queries with query optimisation; AC8: Database-level bug fixes documented with root cause and resolution notes for CMMI process records
Material Testing - FE Inspection Date Addition, Production Build & Play Store Upload | US-MAT-C4-011 | As a QA engineer and release manager, I want FE Inspection Date added to GM/SQC/TPIA web pages and the Material Testing mobile app build tested and uploaded to Play Store so that the module is fully released to production and field users can access the latest version. | AC1: FE Inspection Date field added to Material Testing module web pages on GM, SQC, and TPIA login — sourced from FE inspection submission timestamp; AC2: FE Inspection Date column sortable and filterable in Pending-for-Action and customised report pages; AC3: Material Testing mobile app merged, tested, and uploaded to Play Store after unit testing; AC4: Production Testing and Build Deployment completed — production app verified for correct data flow end-to-end; AC5: Regression testing completed for all Material Testing logins (Contractor, FE, GM, SQC, TPIA) after FE Inspection Date addition; AC6: Production bugs from regression identified, logged, and resolved within SLA; AC7: Material Testing Promot updated with production deployment status and defect closure records for CMMI audit

## Nirmal US
Jal Rekha – Cycle 4 User Stories ¦ NIRMAL MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Nirmal FE Mobile - Development | US-NRM-C4-001 | As a Field Engineer, I want the Nirmal mobile app enhanced with geofencing, new water sampling module, and WTP/Raw Water reporting so that water quality monitoring is comprehensive. | AC1: Water Sampling Collection by Contractor functional; AC2: Geofencing implemented with 200m buffer for WTP/Intake sample collection; AC3: New module added to mobile application for Nirmal testing; AC4: New web pages created/modified for Nirmal reports; AC5: Nirmal Reports (Beneficiary, OHT, WTP, RawWater) accessible from web; AC6: SIT, UAT/Prod/CR testing completed
Nirmal FE Mobile - API & Wireframe | US-NRM-C4-002 | As a developer, I want API creation, UI updates, and unit testing for Nirmal FE mobile completed so that all Nirmal module endpoints are functional and stable. | AC1: API creation for all Nirmal mobile endpoints completed; AC2: UI updated in existing Nirmal mobile pages; AC3: Requirement gathering and wireframe completed for new features; AC4: Unit testing for module completed; AC5: Testing of Nirmal module completed with defect log maintained
Nirmal GM - Report Modification | US-NRM-C4-003 | As a GM user, I want Nirmal reports created/modified and beneficiary report issue resolved so that water quality data is accurately represented. | AC1: Report creation/modification for GM Nirmal login completed; AC2: Beneficiary report issue identified, root cause analysed, and fixed; AC3: Report loads within 5 seconds for 1000+ records; AC4: Export to Excel/PDF functional; AC5: Report changes tested and validated in production
Nirmal CR - Beneficiary Report Change Request (Remarks + Multi-Popup + Role-Based View) | US-NRM-C4-004 | As a GM and Contractor user, I want the Nirmal Beneficiary Report updated with remarks functionality, corrected multi-popup behavior for failed samples, role-based scheme visibility for Contractor login, and all report changes deployed to production so that water quality data is accurately represented. | AC1: Remarks field added to Nirmal Beneficiary Report for both Contractor and GM login with API save and fetch; AC2: Multi-popup UI for failed sample records corrected — proper data binding and navigation across popups; AC3: Contractor login restricted to showing only schemes mapped to the logged-in contractor across all Nirmal reports; AC4: Function and textual changes implemented in all Nirmal reports (Beneficiary, OHT, WTP, Raw Water); AC5: WTP water intake FRC test data issue (residual chlorine value disabled) fixed in production; AC6: OHT Nirmal module issue (Agar Malwa contractor login) resolved; AC7: All Nirmal changes deployed and verified in production
Nirmal CR - WTP, OHT & Raw Water Reports + Production Defect Fixes | US-NRM-C4-005 | As a GM and developer, I want Nirmal WTP Report, OHT Report, and Raw Water Report developed with change requests applied and all production bugs resolved so that water quality test reports are complete, accurate, and accessible from the GM web portal. | AC1: Nirmal WTP Report and Raw Water Report developed with CR and deployed to UAT and production after unit testing; AC2: Nirmal OHT Report developed with CR applied, moved to production after unit testing; AC3: Error in Nirmal Reports WTP count mismatch on Customized Report and WTP Report resolved; AC4: Nirmal Change Request — Beneficiary History Report UI design and API integration completed; AC5: Nirmal reports function creation and modification completed in database; AC6: Requirement gathering and table/function creation for Nirmal reports completed with stakeholder sign-off; AC7: Report load time under 5 seconds for 1000+ records; report export to Excel/PDF functional

## O&M Billing US
Jal Rekha – Cycle 4 User Stories ¦ O&M BILLING MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
O&M Billing GM - Development & Reports | US-OM-C4-001 | As a GM user, I want O&M Billing module with new web pages, reports, and partial billing support developed so that billing operations are accurate and auditable. | AC1: New web pages and UI updates for GM login completed; AC2: Partial O&M Bills functionality implemented; AC3: Bug fixes from frontend and database applied; AC4: GET/SET data access methods and Service/API created; AC5: Database architecture with master check designed; AC6: SIT and UAT/Prod/CR testing completed; AC7: Test cases and scenarios documented
O&M Billing GM - Requirement & CR | US-OM-C4-002 | As a BA/PM, I want requirement gathering, analysis, and change request implementation for O&M Billing GM module so that department expectations are met and GM/Contractor flow is finalized. | AC1: Requirement gathering and analysis completed for GM and Contractor flow; AC2: Internal meetings with team and department conducted and minuted; AC3: Census Population get from Scheme Village Master implemented; AC4: GM HSC Change implemented; AC5: Monitoring changes requirement documented
O&M Billing Workflow | US-OM-C4-003 | As a higher official, I want O&M Billing workflow between GM and higher officials defined and implemented so that billing approvals follow a structured escalation path. | AC1: Workflow documented with all roles (Contractor → GM → Higher Officials); AC2: Workflow requirement gathering completed; AC3: Approval hierarchy implemented with notifications at each stage; AC4: Workflow tested end-to-end with all role scenarios; AC5: Workflow diagram reviewed and approved by department
O&M Billing CR - Contractor | US-OM-C4-004 | As a contractor, I want bill generation flow, abstract page generation, complaint and pressure redressal sheets, and summary page changes implemented so that contractor billing is complete and compliant. | AC1: Contractor Bill generation flow updated with Approved Reports; AC2: 'Generate Abstract Page (Complaint Redressal Sheet)' and 'Pressure Redressal Sheet' enabled post Save & Submit; AC3: Generate Summary Page for Contractor side implemented; AC4: CR in Contractor Summary Page Abstract Report applied; AC5: Complaint Date column modification completed; AC6: Updation and validation addition in Dhara Reports from Contractor side done
O&M Billing CR - Complaint Redressal Sheet & PDF Generation | US-OM-C4-005 | As a GM user, I want the Complaint Redressal Sheet in O&M Billing corrected with accurate column names, Penalty Relaxation logic, Event Occurrence calculation, and PDF generation so that the sheet is audit-ready and accurately reflects billing penalties. | AC1: Complaint Received Date column renamed from 'by Contractor' to 'to Contractor' across the sheet; AC2: Penalty Relaxation display changed from True/False to Yes/No with default value set to No; AC3: Event Occurrence calculation corrected on both complaint listing and billing calculation screens; AC4: Calendar restriction logic implemented — date selection restricted to end of month prior to billing month; AC5: PDF generation implemented for Residual Pressure section and Bulk Consumer report with proper headers, data binding, and pagination; AC6: Serial-wise display verified for Entries D/G/T; AC7: DB-side changes validated and UAT/production deployment completed
O&M Billing CR - Power Consumption Sheet, Summary Page & RA Bill Number | US-OM-C4-006 | As a GM and Contractor user, I want the O&M Billing Power Consumption Sheet, Summary Page, and RA Bill Number auto-generation implemented so that all billing tabs show correct calculations, and each bill has a unique auto-generated reference number. | AC1: Power Consumption Sheet tab development with data validation and PDF button visibility logic completed; AC2: Summary Page — Gross O&M Bill with editable deduction fields and Draft Save implemented; AC3: Village Summary calculation logic redesigned based on HSC proportion; AC4: CPIW billing table and Yearly Factor implemented for Summary page; AC5: Auto-generate RA Bill Number developed with series-based logic and dynamic bill reference; AC6: Summary page Final Bill Submission implemented — draft state correction and final submission UI restriction applied; AC7: Net Payable Bill calculation issue and Deduction Display bug fixed; AC8: Power Consumption Sheet PDF service created and verified
O&M Billing CR - Bulk Consumer in Billing & Abstract Report | US-OM-C4-007 | As a GM and Contractor user, I want Bulk Consumer data integrated into the O&M Billing module with a Bulk Consumer Summary and Abstract Report so that billing calculations reflect all bulk water consumers accurately. | AC1: Bulk Consumer Summary added to O&M Billing with deduction logic and draft-based CRUD support; AC2: Deduction applicability, remarks, and net amount handling implemented for bulk consumers; AC3: GET and SAVE logic updated to show saved data first then calculate; AC4: Dhara Scheme and Bulk Consumer name changes applied, duplicate records removed, and validations added; AC5: Creating Village-wise supply point MWSR, Approved Village Supply Point Village MWSR, and Bulk Supply Point MWSR reports implemented; AC6: Date-wise DWSR Report created in O&M Billing; AC7: Dhara/Nirmal approved reports included in O&M Billing Contractor bill generation flow; AC8: Abstract Report with complaint redressal and pressure redressal sheet auto-enabled post Save & Submit
O&M Billing CR - Contractor Approval Page & Document Upload | US-OM-C4-008 | As a Contractor user, I want a dedicated Contractor Approval Page in O&M Billing with document upload integration so that Contractors can review, approve, and submit bills with supporting documents for final billing closure. | AC1: Contractor Approval Page developed per revised requirement with structure and service creation; AC2: Contractor Bill Approval Module developed with document upload integration for Contractor login; AC3: Dynamic button visibility implemented for draft vs final submission state; AC4: New service created for Contractor Approval summary page with CPWI, Yearly Factor, and mapped parameters; AC5: Generate Abstract Page (Complaint Redressal Sheet) and Pressure Redressal Sheet buttons enabled post Contractor Save & Submit; AC6: Generate Summary Page for Contractor side implemented with correct bill amount and activity count; AC7: Complaint Date column modification and validation addition completed; AC8: End-to-end Contractor billing flow tested from bill generation to final submission
O&M Billing CR - Residual Pressure Tab, PDF Service & Data Binding | US-OM-C4-009 | As a GM user, I want the Residual Pressure tab in O&M Billing fully functional with PDF generation, correct header structure, and data binding from API so that the residual pressure sheet is exportable and meets department audit requirements. | AC1: Residual Pressure tab created and styled inside the O&M Billing accordion block; AC2: PDF service created for Residual Pressure report with dynamic header, proper table formatting, and pagination; AC3: RA Bill Number printed dynamically on the Residual Pressure PDF header; AC4: Data binding from GetDataByBillNo API to Residual Pressure PDF verified — all fields populated correctly; AC5: Bulk Consumer report PDF also generated from the same PDF service with separate layout; AC6: Print HTML view design issue fixed — sub-header menu alignment and table wrap resolved; AC7: PDF generation tested for multiple billing months with correct serial-wise data display; AC8: PDF button visibility logic implemented — button visible only after bill is in Final Submit state
O&M Billing CR - Village Summary, Deduction Logic & HSC Proportion Calculation | US-OM-C4-010 | As a GM user, I want the O&M Billing Village Summary tab to correctly calculate deductions based on HSC proportion and apply draft-based save/edit so that each village's net payable amount reflects actual supply performance before final submission. | AC1: Village Summary calculation logic redesigned using HSC proportion formula (Village HSC / Total Scheme HSC × Gross Bill); AC2: Deduction logic implemented per village — applicable deductions (penalty, downtime, non-supply) applied before net amount calculation; AC3: Draft Save of Village Summary data implemented — users can save partial deduction entries without final submission; AC4: SaveVillageDeductionDetails service created with editable fields and collapse button support; AC5: GET logic updated to return previously saved draft data first before recalculating; AC6: Net Payable Bill calculation bug fixed — incorrect subtraction of inapplicable deductions resolved; AC7: Deduction Display issue fixed — only deductions with applicable = Yes shown in summary; AC8: Village Summary tested across minimum 5 scheme scenarios including schemes with Bulk Consumers
O&M Billing CR - CPWI Yearly Factor, CPI-IW Logic & Billing Calculation | US-OM-C4-011 | As a GM and higher official, I want CPWI (Consumer Price Index for Water) and Yearly Factor calculations integrated into O&M Billing so that bill amounts are inflation-adjusted per contract terms and the Summary tab displays the correct base rate for each billing period. | AC1: CPWI billing table created with index values per billing year; AC2: Yearly Factor calculation implemented — factor applied to base O&M rate for each year of the contract period; AC3: CPI-IW value for 1st year applied correctly on the 1st tab of Summary page per department logic; AC4: CPWI and Yearly Factor both displayed as separate line items on the Summary page; AC5: New service created to fetch and map CPWI and Yearly Factor parameters per scheme and billing month; AC6: Bill amount auto-calculated from CPWI-adjusted rate × HSC count × supply factor; AC7: Summary page Total Count and Yearly Factor display verified for at least 3 active billing schemes; AC8: Calculation logic documented in LLD and reviewed by department before production deployment
O&M Billing CR - Contract Details Page, GetDataByBillNo API & Bill Validation | US-OM-C4-012 | As a developer and GM user, I want the O&M Billing Contract Details page updated with census removal, DataTable fix, and the GetDataByBillNo API corrected so that bill detail retrieval is accurate and the contract details page renders correctly across all browsers. | AC1: Manual add/delete of census population removed from O&M Contract Details page — census now auto-fetched from Scheme Village Master; AC2: DataTable rendering issue on Contract Details page fixed — columns aligned and scrollable on large datasets; AC3: 'Cancel/Delete' button handling updated to prevent accidental deletion of submitted bill records; AC4: GetDataByBillNo API data mismatch issue identified and resolved — response now returns correct bill-wise data including village, deduction, and bulk consumer rows; AC5: Auto-generate RA Bill Number logic developed with series-based numbering (format: SCHEME/YEAR/SEQUENCE); AC6: Dynamic RA Bill No. generation tested for sequential numbering across multiple billing months without duplication; AC7: Contract Details page update deployed to UAT and regression-tested for all existing contract scenarios
O&M Billing CR - Higher Official Monitoring Reports & Approval Escalation | US-OM-C4-013 | As a higher official (SE/CE level), I want O&M Billing monitoring reports and a defined approval escalation workflow so that bills above a threshold value or flagged by GM are escalated to appropriate authority before payment release. | AC1: Monitoring changes requirement documented and approved by department — escalation thresholds defined per bill amount and scheme category; AC2: Higher Official login page created with scheme-wise pending bill list; AC3: Escalation flow implemented: Contractor submits → GM reviews → Higher Official approves (above threshold) or GM approves (below threshold); AC4: Approval hierarchy configured with notifications at each stage via system alert or email; AC5: O&M Billing workflow diagram created covering Contractor → GM → SE/CE roles and updated per department input; AC6: Monitoring dashboard for Higher Officials shows total bills pending, approved, and rejected with scheme filter; AC7: Bill approval action (Approve/Send Back) logged with role, user ID, timestamp, and remarks; AC8: End-to-end workflow tested for all role combinations in staging environment

## Sahbhagita US
Jal Rekha – Cycle 4 User Stories ¦ SAHBHAGITA MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Sahbhagita GM - Reports & Approval | US-SAH-C4-001 | As a GM user, I want Sahbhagita survey approval page and updated reports so that community participation surveys can be reviewed and approved formally. | AC1: New Survey Approval page created with pending survey list; AC2: Approve and Reject buttons functional with mandatory remarks on rejection; AC3: Report modifications visible in Sahbhagita Reports menu; AC4: Bug fixes from frontend applied; AC5: SIT and UAT/Prod/CR testing completed; AC6: Upload Activities through Web Portal functional
Sahbhagita CR - RA Bill & Save as Draft | US-SAH-C4-002 | As a PM user, I want RA Bill functionality on CP Manager and Save as Draft feature added to Sahbhagita module so that ISA billing and survey submissions are managed effectively. | AC1: RA Bill Functionality on CP Manager implemented; AC2: Save as Draft functionality added to Sahbhagita forms; AC3: ISA Bill Form linked to Scheme and District; AC4: Bill amount auto-calculated based on activity count and rate; AC5: Report changes tested and validated
Sahbhagita Report - New Web Page | US-SAH-C4-003 | As a developer, I want new Sahbhagita report web pages created so that GM and PM users can access community participation data in a structured format. | AC1: New web page created for Sahbhagita reports; AC2: Report layout improved with updated columns (Activity Type, Participation Count, NGO, ISA, Video Evidence); AC3: Filter options (Date range, Village, ISA, NGO) operational; AC4: Export to Excel/PDF functional; AC5: Report load time <3 seconds
Sahbhagita CR - ISA Login Issue, NGO Count & Role-Based PIU Dropdown | US-SAH-C4-004 | As a GM and PM user, I want the Sahbhagita ISA login page issue resolved, NGO count segregation corrected in summary page, and role-based PIU dropdown with search validation added to reports so that community participation data is accurately categorized and reportable. | AC1: ISA login page issue (ISO schemes not showing per mapped scheme) identified, root-caused, and fixed; AC2: Sahbhagita Summary Page NGO count segregation issue fixed — NGO, ISA, and Community counts now displayed separately; AC3: Role-based PIU dropdown added to Sahbhagita report pages with search validation; AC4: Sahbhagita Report — Role-based PIU filter operational for GM and PM login with scope restriction; AC5: Sahbhagita CP Manager Page — RA Bill Approval module enhancement completed; AC6: All bug fixes tested in staging and production with regression testing completed; AC7: Report layout updated per department feedback with correct column representation

## SVS US
Jal Rekha – Cycle 4 User Stories ¦ SVS MODULE – HAR GHAR JAL WATER SUPPLY MONITORING ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
SVS - Module Initiation & NIC API Integration | US-SVS-C4-001 | As a project manager, I want the SVS Water Supply Monitoring module initiated with formal requirement gathering and NIC Panchayat Darpan API finalized so that the development team has complete specifications and integration details before build begins. | AC1: Project module initiation meeting conducted and MoM documented with action owners; AC2: Requirement gathering sessions completed with PHE department stakeholders; AC3: Internal meeting conducted to finalize API endpoints and data contract from NIC Panchayat Darpan; AC4: Village Master data structure confirmed and mapped to SVS fields; AC5: SVS Daily Water Supply Wireframe created, reviewed, and approved by department; AC6: Database schema designed with required tables and field-level mapping documented
SVS - Daily Water Supply Data Entry Form | US-SVS-C4-002 | As a GP user or PHE field officer, I want a structured daily water supply data entry form with District, Block, GP, Village, and Household Connections pre-filled so that I can quickly record supply status without re-entering location details every day. | AC1: Form displays District, Block, GP, and Village based on logged-in user's jurisdiction (pre-filled by default); AC2: Household Connections Established (स्थापित घरेलू नल कनेक्शन) field displayed and auto-populated from Village Master; AC3: Water Supply Date (जल प्रदाय दिनांक) shown as a date picker with default value as today's date; AC4: Form validates mandatory fields before allowing submission; AC5: Submission confirmation message shown on success; AC6: Record saved to database with user ID, timestamp, and village code
SVS - Water Supply Date Picker | US-SVS-C4-003 | As a GP user, I want a date picker control on the SVS water supply entry form so that I can accurately select the date of water supply without manual text entry errors. | AC1: Date picker control (calendar widget) displayed for Water Supply Date field (जल प्रदाय दिनांक); AC2: Default date is current system date; AC3: Future dates restricted — only today or past dates selectable; AC4: Date format stored as DD-MM-YYYY in database; AC5: Date picker works on both desktop and mobile browser; AC6: Selected date visible clearly in the form before submission
SVS - Water Supply Status - YES Flow | US-SVS-C4-004 | As a GP user, I want to record YES (हाँ) water supply status for my village on a given date so that the system reflects successful daily supply and the dashboard shows green supply status. | AC1: YES option selectable from Water Supply Status field (Yes / No / Partial radio buttons or dropdown); AC2: On selecting YES, no additional mandatory fields are required; AC3: Record saved with status = YES, date, village code, and user ID; AC4: Dashboard and summary report reflect YES count for the selected date; AC5: GP and PHE login can view YES supply records in daily report; AC6: No Reason or Remark field displayed when YES is selected
SVS - Water Supply Status - NO Flow with Reason | US-SVS-C4-005 | As a GP user, I want to record NO (नहीं) supply status with a mandatory reason selection and remarks box so that the department can track and address supply failures with root cause data. | AC1: Selecting NO status displays a Reason for No Supply dropdown/radio list with options: Tubewell Failure, OHT Not Filled By MVS Contractor, Motor Pump Not Working, Valve cum Pump Operator Problem, Electricity Supply Problem, Pipeline Damage, Any Other (with Remarks); AC2: Reason field is mandatory when status is NO — form cannot be submitted without selection; AC3: When 'Any Other' selected, a free-text Remarks box opens and becomes mandatory; AC4: Remarks text box also opens by default when status is NO (open box in no of remark); AC5: Record saved with status = NO, reason code, and remarks; AC6: GM and district-level dashboard shows NO supply count with reason breakdown per village
SVS - Water Supply Status - PARTIAL Flow | US-SVS-C4-006 | As a GP user, I want to record PARTIAL (आंशिक) supply status with the number of connections that received water and a mandatory remarks box so that partial supply incidents are tracked with quantitative data. | AC1: Selecting PARTIAL status displays the field 'Connections Supplied Water (जल प्रदाय कनेक्शन की संख्या)' as a mandatory numeric input; AC2: Number of connections supplied must be less than or equal to total Household Connections Established; AC3: Remarks text box opens automatically when PARTIAL is selected (open box in partial of remark); AC4: Remarks field is mandatory for PARTIAL status; AC5: Record saved with status = PARTIAL, connections supplied count, and remarks; AC6: Dashboard shows PARTIAL supply count and connections percentage at village level
SVS - Partial Edit Feature | US-SVS-C4-007 | As a GP user or PHE officer, I want to partially edit a previously submitted daily water supply record so that data corrections can be made without deleting and re-entering the full record. | AC1: Partial Edit option available on submitted supply records within a configurable edit window (e.g., same day or 24 hours); AC2: User can change Water Supply Status, Reason (for NO), Connections Supplied (for PARTIAL), or Remarks without modifying Date or Village; AC3: Edit action logs the original values and new values in an audit trail with editor user ID and timestamp; AC4: Edited records flagged as 'Modified' in reports with original and updated values traceable; AC5: Only authorized roles (GP user, PHE officer) can perform Partial Edit; AC6: Edit window enforced — records beyond the allowed window require supervisor approval to edit
SVS - Default Hierarchy Selection by Login | US-SVS-C4-008 | As a logged-in GP or PHE user, I want District, Block, and GP to be auto-selected by default based on my login credentials so that I do not need to manually navigate the location hierarchy every time I enter data. | AC1: On login, the system identifies the user's assigned District, Block, and GP from the user profile; AC2: District, Block, and GP fields in the data entry form are pre-filled and locked for GP-level users; AC3: PHE/Block-level users can see their default jurisdiction but may change Block or Village within their scope; AC4: District-level users see all Blocks and GPs with no default lock; AC5: Default selection is correctly applied in all SVS forms (Data Entry, Edit, Report filters); AC6: No manual re-selection required for GP user across multiple daily submissions
SVS - Hindi Interface (MP Shasan Labels) | US-SVS-C4-009 | As an MP government user, I want the SVS water supply entry form to display field labels in Hindi (MP Shasan standard) so that GP-level and rural users can use the system in their native language without language barriers. | AC1: All SVS form labels displayed in bilingual format (Hindi + English) or Hindi only based on language setting; AC2: Water Supply Date → 'जल प्रदाय दिनांक', Status → 'जल प्रदाय की स्थिति', YES → 'हाँ', NO → 'नहीं', PARTIAL → 'आंशिक' applied; AC3: Household Connections label shows 'स्थापित घरेलू नल कनेक्शन'; AC4: Reason dropdown options displayed in Hindi; AC5: MP Shasan (मध्यप्रदेश शासन) branding/header applied per department standard; AC6: Hindi rendering tested on Chrome and mobile Android browser without font issues
SVS - Remove Unwanted Fields (JJM, Village Status, Hand Over Community) | US-SVS-C4-010 | As a PHE department stakeholder, I want the JJM field, village status field, and hand over community field removed from the SVS supply monitoring form so that the form is focused, clutter-free, and aligned to current department requirements. | AC1: JJM (Jal Jeevan Mission) field removed from SVS data entry form and all related report columns; AC2: Village Status field removed from the SVS form; AC3: Hand Over Community field removed from SVS form; AC4: Database columns for removed fields retained (not deleted) but not exposed in UI or reports; AC5: Existing historical records with these fields remain accessible via admin view; AC6: Removal changes tested and verified in staging before production deployment; AC7: Report templates updated to exclude removed fields
SVS - Excel Report with LGD Code and Household Join | US-SVS-C4-011 | As a PHE data analyst or district officer, I want Excel downloadable reports from SVS that include the LGD Code and Household Connections data joined to each village record so that reports can be cross-referenced with national LGD data and household surveys. | AC1: SVS Excel download report includes LGD Code column for each village; AC2: Household Connections Established count joined from Village Master to the Excel report per village; AC3: LGD Code and Household data sourced from authorized master tables (IMS/Panchayat Darpan); AC4: Excel report columns: District, Block, GP, Village, LGD Code, Household Connections, Supply Date, Status, Reason (if NO), Connections Supplied (if PARTIAL), Remarks; AC5: Date range filter available for Excel download (daily, weekly, monthly); AC6: Excel download works within 10 seconds for up to 1000 village records
SVS - Dashboard: Village / Block / District Level Monitoring | US-SVS-C4-012 | As a PHE department official, I want a SVS monitoring dashboard showing daily water supply status (YES / NO / PARTIAL counts) at village, block, and district level with drill-down navigation so that supply performance is visible at all governance levels. | AC1: Dashboard displays total villages vs supply submitted count for the selected date; AC2: Status breakdown shown: YES count (green), NO count (red), PARTIAL count (amber), Not Submitted (grey); AC3: District → Block → GP → Village drill-down navigation functional; AC4: Date filter (single date or range) available on dashboard; AC5: Reason for NO supply breakdown visible as a sub-panel or tooltip at village level; AC6: Dashboard data refreshes automatically or on demand; AC7: Dashboard accessible to PHE, GM, District, and Block-level login roles with appropriate scope restriction; AC8: 1 Scheme = 1 Handpump monitoring aligned for SVS scheme type

## CMMI Doc US
Jal Rekha – Cycle 4 User Stories ¦ CMMI DOC MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
CMMI Doc - Data Collection & Documentation Cycle 4 | US-CMMI-C4-001 | As a SEPG team member, I want to collect data for Cycle 4 (Jan to May 2026) so that I can measure project performance metrics and prepare CMMI Level 5 audit artifacts. | AC1: Data collection sheet created with all required fields (Requirement Efforts, Design Efforts, Coding Effort, Code Review, Testing Effort); AC2: Data collected for all Cycle 4 modules (Anusharavan, Bharosa, Cube Testing, Dhara, FHTC, Material Testing, Nirmal, O&M Billing, Sahbhagita, SVS, Master, Asset Mapping); AC3: Defect data captured (Requirement Review, Design Review, Code Review, Internal Testing, UAT, Production); AC4: Productivity, DRE, and Cycle Time calculated automatically; AC5: Data validated for accuracy and completeness
CMMI Doc - Streamline Documentation | US-CMMI-C4-002 | As a quality manager, I want CMMI documentation streamlined for O&M Billing, Bharosa, and Material modules so that audit artifacts are consistent and complete. | AC1: Streamline documentation completed for O&M Billing, Bharosa, and Material Testing modules; AC2: CMMI documents created and reviewed per CMMI L5 standards; AC3: Induction training attended by relevant team members; AC4: Promote activity for CMMI L5 Audit completed; AC5: All documents archived in repository with version control
CMMI Doc - Phase 1 to 4 Completion | US-CMMI-C4-003 | As a SEPG team member, I want CMMI documentation completed across all four phases for Cycle 4 so that the project is fully prepared for CMMI Level 5 audit. | AC1: Phase 1 CMMI documentation completed (Planning, Estimation); AC2: Phase 2 CMMI documentation completed (Requirements, Design); AC3: Phase 3 CMMI documentation completed (Coding, Code Review); AC4: Phase 4 CMMI documentation completed (Testing, Deployment); AC5: All phases reviewed and approved by SEPG Head; AC6: Data collection for January to May cycle completed and baselined
Department Meetings - Requirement Gathering | US-CMMI-C4-004 | As a BA/PM, I want department meetings conducted for all module requirements and changes so that all stakeholder needs are documented and tracked. | AC1: Department meetings conducted for all modules (Nirmal, Bharosa, O&M Billing, Dhara, Cube Testing, Material Testing); AC2: Discussion on new material and cube testing modules documented; AC3: Requirement gathering for changes and updations completed across all modules; AC4: Meeting minutes with action items and owners distributed within 24 hours; AC5: Requirements tracked to implementation via traceability matrix

## Site Security US
Jal Rekha – Cycle 4 User Stories ¦ SITE SECURITY MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Site Security Audit | US-SEC-C4-001 | As a security team member, I want Jal Rekha site Fortify security audit conducted so that all security vulnerabilities are identified and remediated before production. | AC1: Fortify security audit tool configured and run on Jal Rekha codebase; AC2: All critical and high severity vulnerabilities identified and documented; AC3: Remediation plan created with owners and timelines; AC4: Site security audit report prepared and submitted to department; AC5: Dhara module specific security issues identified and resolved

## Sopan US
Jal Rekha – Cycle 4 User Stories ¦ SOPAN MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
Sopan Contractor - Development & Testing | US-SOP-C4-001 | As a contractor, I want the Sopan Contractor module with dashboard, data upload, and new web pages functional so that scheme-level contractor activities are properly managed. | AC1: Dashboard creation for Sopan Contractor completed; AC2: Upload Activities through Web Portal functional; AC3: New web pages and data access methods (GET/SET) created; AC4: OHT data correction completed; AC5: Bug fixes from database applied; AC6: Requirement gathering completed; AC7: SIT, UAT/Prod/CR testing and testing of new functionality completed

## User Role US
Jal Rekha – Cycle 4 User Stories ¦ USER ROLE MODULE ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | User Story Description | Acceptance Criteria
User & Role Management - Testing | US-URM-C4-001 | As a QA engineer, I want functional and SIT testing of User and Role Management module completed so that all access controls and permissions are verified before release. | AC1: Functional testing completed for all user roles across all modules; AC2: SIT testing completed; AC3: Permission matrix verified for all role-module combinations; AC4: No unauthorized access identified; AC5: Test report submitted and reviewed