## KPI Dashboard
Jal Rekha – Cycle 4 KPI Register ¦ January 2026 – June 2026 ¦ CMMI Level 5 ¦ MPSeDC
# | KPI Name | Category | Planned Target | Actual (Cycle 4) | Unit | Measurement Method | Responsible | Data Source | Frequency | Status | Remarks
1 | Defect Removal Efficiency (DRE) | Process Quality | ≥ 80% | 77.8% | % | DRE = Defects removed before release / Total defects × 100 | QA / Tester | Defect tracker | Per Sprint | WIP | Monitoring closely; target 80%
2 | Requirement Review Defects | Process Quality | ≤ 22 per cycle | 22 | Count | Review checklist count per cycle | BA / Tester | Requirement Review Log | Per Cycle | Done | Met exactly
3 | Code Review Coverage | Process Quality | 100% of modules | 100% | % | % modules with peer code review complete | Dev Lead | SVN / Review records | Per Sprint | Done | All 17 modules covered
4 | UAT Defect Density | Process Quality | ≤ 5 defects/100 FPs | 3.2 | Defects/100 FP | UAT defects ÷ function points × 100 | QA Lead | UAT log | Per Sprint | Done | Within target
5 | System Test Pass Rate | Process Quality | ≥ 95% | 96.8% | % | Test cases passed ÷ total executed × 100 | Tester | Test case tracker | Per Sprint | Done | On target
6 | Regression Test Coverage | Process Quality | ≥ 90% | 92% | % | Regression test cases run ÷ total test cases | Tester | Test suite | Per Sprint | Done | Satisfactory
7 | Productivity (Function Points/Person-Day) | Productivity | 0.20 FP/PD | 0.185 FP/PD | FP/PD | FPs delivered ÷ person-days consumed | Dev Team | Timesheet + FP count | Monthly | WIP | Slightly below; within UCL
8 | Code Rate (LOC/Person-Day) | Productivity | 0.40 | 0.31 | LOC/PD | Lines of code ÷ person-days | Dev Team | SVN commit stats | Monthly | WIP | Monitoring; As-IS mean 0.314
9 | Test Rate (Test Cases/Person-Day) | Productivity | 0.85 | 0.73 | TC/PD | Test cases executed ÷ person-days | Tester | Test tracker | Monthly | Done | Within UCL
10 | Sprint Velocity (FPs/Sprint) | Schedule | Target per sprint plan | ≥95% of plan | FP | FPs completed vs. planned per sprint | PM | Sprint board | Per Sprint | Done | Maintained across Sprints 12–16
11 | Schedule Variance (SV) | Schedule | 0% (On Time) | 0 – +2% | % | (Actual completion date – Planned date) ÷ Planned × 100 | PM | Gantt chart | Monthly | Done | No significant delay
12 | Milestones Met On Time | Schedule | 100% | 100% | % | Milestones delivered on schedule ÷ total milestones × 100 | PM | Project milestones doc | Monthly | Done | All major milestones met
13 | Change Request Turnaround Time | Schedule | ≤ 5 working days | 4.2 days | Days | Avg days from CR logging to deployment | BA + Dev Team | CR Log | Per CR | Done | On target
14 | Effort Variance (EV) | Effort | ≤ ±10% | –2.3% | % | (Actual hrs – Planned hrs) ÷ Planned hrs × 100 | PM | Timesheet | Monthly | Done | Slight under; no concern
15 | Cycle Time (hours/FP) | Effort | 0.68 | 0.68 | Hrs/FP | Total effort hrs ÷ FPs delivered | Dev Team | Timesheet | Monthly | Done | Matches As-IS mean
16 | Resource Utilisation | Effort | 85–95% | 89% | % | Billable hrs ÷ available hrs × 100 | PM | Timesheet | Monthly | Done | Optimal
17 | Total Effort (Hrs) Consumed | Effort | ≤ 2600 hrs | ~2580 hrs | Hrs | Sum of all timesheet hours (Jan–Jun) | PM | Date-wise timesheet | Monthly | Done | Within planned budget
18 | Module Delivery Rate | Delivery | 17 modules (Cycle 4) | 17 modules | Count | Modules completed and released to production | PM / BA | CR Log + Release notes | Per Cycle | Done | All 17 tracked
19 | User Stories Completed | Delivery | 94 USPs | 94 USPs | Count | User stories completed and accepted in UAT | BA / QA | User Story tracker | Per Sprint | Done | All 94 USPs done
20 | CRs Logged & Resolved (Cycle 4) | Delivery | All CRs ≥ V1.5 | 78 CRs | Count | Count of CRs logged, resolved, released | BA | CR Log V1.5 | Per Cycle | Done | 78 CRs across all modules
21 | Play Store Release Count | Delivery | ≥ 5 mobile releases | 6 releases | Count | Mobile app Play Store updates released | Dev Team | Play Store console | Per Sprint | Done | Anusharavan, Cube, Bharosa, Material, FHTC, Nirmal
22 | BRTM Traceability Coverage | Delivery | 100% | 100% | % | Req IDs traceable to design/code/test/UAT | BA | BRTM V1.0 | Per Cycle | Done | 94 rows mapped
23 | CMMI Documentation Completeness | CMMI L5 | 100% | 100% | % | CMMI docs prepared ÷ required docs × 100 | BA / QA | CMMI tracker | Per Month | Done | All Cycle 4 docs ready
24 | Review Meeting Compliance | CMMI L5 | Monthly (12 meetings) | 6 monthly MoMs | Count | MoM meetings held with MD Sir and team | PM / BA | MoM register | Monthly | Done | Jan–Jun 2026 all covered
25 | MQAS Audit Findings Closure Rate | CMMI L5 | 100% closure | Pending MQAS review | % | MQAS findings closed ÷ total findings × 100 | QA Lead | MQAS findings log | Per Audit | Pending | Scheduled post Jun 2026
26 | Stakeholder Sign-off Rate | Stakeholder | 100% per sprint | 100% | % | Sprint sign-offs obtained ÷ sprint deliveries × 100 | PM / BA | Sprint sign-off log | Per Sprint | Done | All sprints signed off
27 | Department Change Request Acceptance Rate | Stakeholder | ≥ 95% of CRs accepted | 97% | % | CRs accepted by dept ÷ total CRs raised × 100 | BA | CR Log | Per Cycle | Done | Only 3 CRs deferred
28 | MD Meeting Action Item Closure Rate | Stakeholder | ≥ 90% per MoM | 88% | % | Action items closed ÷ total action items per MoM × 100 | PM / BA | MoM action tracker | Monthly | WIP | 2 items (Mohkhed bug, Sujalam Bharat) pending
29 | Open Risk Count | Risk | ≤ 3 open risks at any time | 3 open | Count | Open risks in risk register at month-end | PM | Risk Register (PSRs) | Monthly | WIP | CMMI MQAS, Sujalam Bharat, Mohkhed bug
30 | Risk Mitigation Coverage | Risk | 100% | 100% | % | Risks with mitigation plan ÷ total risks × 100 | PM / BA | PSR Risk Register | Monthly | Done | All risks have documented mitigation

## KPI Summary
KPI Summary – Cycle 4
Category | Total KPIs | Done | WIP | Pending
Process Quality | 6 | 5 | 1 | 0
Productivity | 3 | 1 | 2 | 0
Schedule | 4 | 4 | 0 | 0
Effort | 4 | 4 | 0 | 0
Delivery | 5 | 5 | 0 | 0
CMMI L5 | 3 | 2 | 0 | 1
Stakeholder | 3 | 2 | 1 | 0
Risk | 2 | 1 | 1 | 0