## JantoApr
Sign-Off: |  | I hereby agree and approve that the specifications in this document constitute the complete scope of this project and will consequently meet the business and functional needs. Any requirement not explicitly mentioned in the specifications will be considered out of scope for this project. After approval, any additions and changes to this document or referred objects will be pursued through the change request process.
Work Status
S.NO | Module | Task | Status
1 | Dhara Module | Mobile Application: New Features Implemented to capture meter status with the categories like Functional Meter, Meter Replaced, Non-Functional Meter, No Water Supplied | Completed
2 | Dhara Module | New Reports Developed: Monthly Water Supply Report | Completed
3 | Dhara Module | New Reports Developed: Village-Wise MWSR Report | Completed
4 | Dhara Module | The existing MWSR Report has been renamed to UFW Report | Completed
5 | Dhara Module | Drill-down feature added to the reports for better data navigation. | Completed
6 | Sopan Module | New Features Added: Upload functionality for Panchnama Report and Approved Design & Drawing Report. Option provided for users to upload additional supporting documents. | Completed
7 | Sopan Module | New report created for the OHT details monitoring | Completed
8 | Sopan Module | Feature developed for capturing intake details. (Document upload functionality for this will be completed by end of day.) | Completed /UAT
9 | Asset Mapping | New functionality added to download Executed and Planned data. | Completed
10 | Asset Mapping | OHT (Overhead Tank) labels have been added for improved visualization | Completed
11 | Nirmal | Contractors can now capture water sample data directly in the system. | Completed
Currently in Progress
12 | Dhara | Developing meter reading editing functionality for GM login. | In Progress
13 | Sopan | Continuing development in Sopan Module for capturing WTP (Water Treatment Plant) details. | In Progress
For Department
Name
Approved By
Designation
Organization
Signature with Seal
Date

## AprtoJun
Sign-Off: |  | I hereby agree and approve that the specifications in this document constitute the complete scope of this project and will consequently meet the business and functional needs. Any requirement not explicitly mentioned in the specifications will be considered out of scope for this project. After approval, any additions and changes to this document or referred objects will be pursued through the change request process.
Work Status
S.NO | Module | Task | Status
1 | Anushravan | Mobile application links with Sopan OHTs, once contractor add details in Sopan then only able to raise RFI | Completed
2 | Anushravan | OHT name added in RFI | Completed
3 | Asset Maping / Dhara | Renaming of OHTs | Completed
4 | Asset Mapping | New functionality added to download Executed and Planned data. | Completed
5 | Asset Mapping | OHT (Overhead Tank) labels have been added for improved visualization | Completed
6 | Asset Mapping | OHT,Intake,WTP, movement functionality | Completed
7 | Asset Mapping | As Built Survey data 3 schemes- publish | Completed
8 | Asset Mapping / Dhara | Deleting Duplicate Entries of Components | Completed
9 | Bharosa | Factory Testing | I.P
10 | Changes User management | Multiple scheme Sqc & Tpia id - change in RFI flow | Completed
11 | Dhara | GM given all option -Dhara Entry | Completed
12 | Dhara | Mobile Application: New Features Implemented to capture meter status with the categories like Functional Meter, Meter Replaced, Non-Functional Meter, No Water Supplied | Completed
13 | Dhara | New Reports Developed: Monthly Water Supply Report | Completed
14 | Dhara | New Reports Developed: Village-Wise MWSR Report | Completed
15 | Dhara | The existing MWSR Report has been renamed to UFW Report | Completed
16 | Dhara | Drill-down feature added to the reports for better data navigation. | Completed
17 | Dhara | Developing meter reading editing functionality for GM login. | Completed
18 | Dhara | Billing of O&M Contractors | Completed
19 | Dhara | Mapping of villages with different components | Completed
20 | Dhara | Same Village issue identified and resolved | Completed
21 | Dhara | Date Range option in meter reading approval pages | Completed
22 | Dhara | The report of Dhara is visible to the contractor | Completed
23 | Dhara | Work needs to start on the Sub Meter Option on Web | Pending
24 | Dhara | On the web, we also need to provide the option to select the meter type during editing at GM login | Completed
25 | Dhara Module | Resolve the issues of 2 OHTs during mapping | Completed
26 | Dhara Module | Correction of Dhara Reports | Completed
27 | Dhara Module updation | Updation Dhara module | Completed
28 | Dhara Reading approved | Date wise Dhara reading approved | Completed
29 | FSTC Module | Work started on the FSTC Module, API received for the integration with Jal Samagra | I.P
30 | Geoportal | Search option | Completed
31 | Master | Pipeline master | Completed
32 | Nirmal | Functionality for contractor to take water samples | Completed
33 | Nirmal | In Nirmal, we need to change the parameters range | Completed
34 | Pile Line master in Mobile | Generate RFI Contractor (Pipe line Master Data) | Completed
35 | Pile Line master web | Show in Report Pipe line master data (RFI) | Completed
36 | Pipeline Master | Reports of pipeline master with drop down functionality | Completed
37 | Pipeline Master | CWPM, CWGM need to add zones numbers | Completed
38 | Pipeline Master | Zone number added in CWPM component | Completed
39 | Reports | All reports are made available to all logging with there respect to there area | Completed
40 | Sc Name short in Application | Short Name of Schemes | Completed
41 | Shabhagita | Activity Upload through Web Portal | Completed
42 | Shabhagita | Multiple Photo Upload | Completed
43 | Shabhagita | Activity Delete Option for GM | Need to Discuss-No need
44 | Shabhagita | New Report need to add in Shabhagita | Completed
45 | Sopan | New Features Added: Upload functionality for Panchnama Report and Approved Design & Drawing Report. Option provided for users to upload additional supporting documents. | Completed
46 | Sopan | New report created for the OHT details monitoring | Completed
47 | Sopan | Feature developed for capturing intake details. | Completed
48 | Sopan | Functionality to Edit Planned Dates at GM login | Completed
49 | Sopan | Functionality to Add Actual Dates at GM login | Completed
50 | Sopan | Functionality for GM to add remarks | Completed
51 | Sopan | Sopan Module for capturing WTP (Water Treatment Plant) details. | Completed
52 | Sopan | Sopan module for capturing Intermediate Pumping Station (IPS) Details | Completed
53 | Sopan | Option to finalize plan start and plan completion | Completed
54 | Sopan Module WTP | Need to provide the functionality for finalized the planed date at GM login | Completed
55 | Sopan Module WTP | Design and Panchnama (Each activity) | Completed
56 | Sopan Report | Report Hyperlink | Completed
For Department
Name
Approved By
Designation
Organization
Signature with Seal
Date

## SeptoOct
Sign-Off: |  | I hereby agree and approve that the specifications in this document constitute the complete scope of this project and will consequently meet the business and functional needs. Any requirement not explicitly mentioned in the specifications will be considered out of scope for this project. After approval, any additions and changes to this document or referred objects will be pursued through the change request process.
Work Status
S.NO | Module | Task | Status
1 | Dhara Module | Mobile Application: New Features Implemented to capture meter status with the categories like Functional Meter, Meter Replaced, Non-Functional Meter, No Water Supplied | Completed
2 | Dhara Module | New Reports Developed: Monthly Water Supply Report | Completed
3 | Dhara Module | New Reports Developed: Village-Wise MWSR Report | Completed
4 | Dhara Module | The existing MWSR Report has been renamed to UFW Report | Completed
5 | Dhara Module | Drill-down feature added to the reports for better data navigation. | Completed
6 | Sopan Module | New Features Added: Upload functionality for Panchnama Report and Approved Design & Drawing Report. Option provided for users to upload additional supporting documents. | Completed
7 | Sopan Module | New report created for the OHT details monitoring | Completed
8 | Sopan Module | Feature developed for capturing intake details. | Completed
9 | Asset Mapping | New functionality added to download Executed and Planned data. | Completed
10 | Asset Mapping | OHT (Overhead Tank) labels have been added for improved visualization | Completed
11 | Sopan | Functionality to Edit Planned Dates at GM login | Completed
12 | Sopan | Functionality to Add Actual Dates at GM login | Completed
13 | Nirmal | Functionality for contractor to take water samples | Completed
14 | Asset Maping / Dhara | Renaming of OHTs | Completed
15 | Master | Pipeline master | Completed
16 | Asset Mapping / Dhara | Deleting Duplicate Entries of Components | Completed
17 | Sopan | Functionality for GM to add remarks | Completed
18 | Pipeline Master | Reports of pipeline master with drop down functionality | Completed
19 | Geoportal | Search option | Completed
20 | Asset Mapping | OHT,Intake,WTP, movement functionality | Completed
21 | Dhara | Developing meter reading editing functionality for GM login. | Completed
22 | Sopan Module WTP | Need to provide the functionality for finalized the planed date at GM login | UAT
23 | Sopan Module WTP | Design and Panchnama (Each activity) | UAT
24 | Sopan | Sopan Module for capturing WTP (Water Treatment Plant) details. | Completed
25 | Shabhagita | Activity Upload through Web Portal | Completed
26 | Shabhagita | Multiple Photo Upload | Completed
27 | Shabhagita | Activity Delete Option for GM | Need to Discussed
28 | Pile Line master web | Show in Report Pipe line master data (RFI) | Completed
29 | Pile Line master in Mobile | Generate RFI Contractor (Pipe line Master Data) | Apk uplod in Play store
30 | Dhara Module updation | Updation Dhara module | Progress
31 | Changes User management | Multiple scheme Sqc & Tpia id - change in RFI flow | Need to Discussed
32 | Dhara Reding approved | Date wise Dhara reading approved | Completed
33 | Dhara | Billing of O&M Contractors | Final Stage
34 | O&M Billing - GM | 1) GM of O&M module Login and fill basic details 2) GM Advance form details SLBM features & other additional functionalities, scheme status 3) GM Scheme status and financial calculation for billing 4) GM uploads documents and data is fetched from Dhara and Nirmal module 5) GM under a scheme assign it to a Contractor 6) Contractor generate Bill 7) GM PIU or SQC Edit it and forward to GM of O&M then to PMC 8) All can check remarks then forward to Deputy Manager will only processs final bill amount with further remarks 9) PMC recommendations letter annexure duly verified | Completed
35 | O&M Billing - Contractor | 1) Contractor Basic details, Advance details 2) Fill Financial Calculations as per CPI 3) O&M Billing PIU and SQC page development 4) O&M Billing Manpower page development & Residual Pressure SP 5) O&M Mapping Bulk users, Gross Bill Deduction, & Net Payable Bill 6) O&M Billing Process for RM & Village & Mapping Management Norms 7) Dhara water supply entries from Portal | Completed
36 | O&M Billing - Workflow b/w O&M GM & Higher officials | 1) Establish flow between GM, Contractor 2) GM O&M, CGM, PD, CFO, CA then MD final approval of bill and status 3) Retrieve all RA bill data correctly & Prepare test data in om_ra_bill table 4) RA Bill is based on scheme id & contractor id, always choose bill month & increment after first year and next month 1 days 5) Edit option and resend to PIU GM then GM send to Contractor. | Completed
37 | Change request O&M Billing | 1) Save as Draft at time of entry by GM 2) Census Population location hierarchy needs to be corrected and Next change to make Census population open 3) SLBM Section fields Quality, Quantity, Pressure, UFW, and Complaint, an "Other" option should be added to both the Norms and Penalty dropdowns 4) Changes for Penalty label (Name, Radio button) 5) Type of Increment for CPIW & Yearly calculation changes 6) Scheme Status section ( View Document, Eligibility Increment, Year month update for O & M start & end date) 7) GST services option open for O &M 8) Document upload Yes/No where if done then freeze the screen | Completed
For Department
Name
Approved By
Designation
Organization
Signature with Seal
Date

## JultoAug
Sign-Off: |  | I hereby agree and approve that the specifications in this document constitute the complete scope of this project and will consequently meet the business and functional needs. Any requirement not explicitly mentioned in the specifications will be considered out of scope for this project. After approval, any additions and changes to this document or referred objects will be pursued through the change request process.
Work Status
S.NO | Module | Task | Status
1 | Dhara Module | Mobile Application: New Features Implemented to capture meter status with the categories like Functional Meter, Meter Replaced, Non-Functional Meter, No Water Supplied | Completed
2 | Dhara Module | New Reports Developed: Monthly Water Supply Report | Completed
3 | Dhara Module | New Reports Developed: Village-Wise MWSR Report | Completed
4 | Dhara Module | The existing MWSR Report has been renamed to UFW Report | Completed
5 | Dhara Module | Drill-down feature added to the reports for better data navigation. | Completed
6 | Sopan Module | New Features Added: Upload functionality for Panchnama Report and Approved Design & Drawing Report. Option provided for users to upload additional supporting documents. | Completed
7 | Sopan Module | New report created for the OHT details monitoring | Completed
8 | Sopan Module | Feature developed for capturing intake details. | Completed
9 | Asset Mapping | New functionality added to download Executed and Planned data. | Completed
10 | Asset Mapping | OHT (Overhead Tank) labels have been added for improved visualization | Completed
11 | Sopan | Functionality to Edit Planned Dates at GM login | Completed
12 | Sopan | Functionality to Add Actual Dates at GM login | Completed
13 | Nirmal | Functionality for contractor to take water samples | Completed
14 | Asset Maping / Dhara | Renaming of OHTs | Completed
15 | Master | Pipeline master | Completed
16 | Asset Mapping / Dhara | Deleting Duplicate Entries of Components | Completed
17 | Sopan | Functionality for GM to add remarks | Completed
18 | Pipeline Master | Reports of pipeline master with drop down functionality | Completed
19 | Geoportal | Search option | Completed
20 | Asset Mapping | OHT,Intake,WTP, movement functionality | Completed
21 | Dhara | Developing meter reading editing functionality for GM login. | Completed
22 | Sopan Module WTP | Need to provide the functionality for finalized the planed date at GM login | Completed
23 | Sopan Module WTP | Design and Panchnama (Each activity) | Completed
24 | Sopan | Sopan Module for capturing WTP (Water Treatment Plant) details. | Completed
25 | Shabhagita | Activity Upload through Web Portal | Completed
26 | Shabhagita | Multiple Photo Upload | Completed
27 | Shabhagita | Activity Delete Option for GM | Need to Discuss-No need
28 | Pile Line master web | Show in Report Pipe line master data (RFI) | Completed
29 | Pile Line master in Mobile | Generate RFI Contractor (Pipe line Master Data) | Completed
30 | Dhara Module updation | Updation Dhara module | Completed
31 | Changes User management | Multiple scheme Sqc & Tpia id - change in RFI flow | Completed
32 | Dhara Reding approved | Date wise Dhara reading approved | Completed
33 | Dhara | Billing of O&M Contractors | Completed
34 | Sopan | Sopan module for capturing Intermediate Pumping Station (IPS) Details | Completed
35 | Dhara | Mapping of villages with different components | Completed
36 | Anushravan | Mobile application links with Sopan OHTs, once contractor add details in Sopan then only able to raise RFI | Completed
37 | Pipeline Master | CWPM, CWGM need to add zones numbers | Completed
38 | Dhara Module | Resolve the issues of 2 OHTs during mapping | Completed
39 |  | All reports are made available to all logging with there respect to there area | Completed
40 |  | Short Name of Schemes | Completed
41 | Dhara Module | Correction of Dhara Reports | Completed
42 | Pipeline Master | Zone number added in CWPM component | Completed
43 | Dhara | Same Village issue identified and resolved | Completed
44 |  | Field survey pipeline data received for Indore and Rajgard PIU (Working on distribution line) | Completed
45 | Dhara | Date Range option in meter reading approval pages | Completed
46 | Sopan | Option to finalize plan start and plan completion | Completed
47 | Sopan Report | Report Hyperlink | Completed
48 | Dhara | The report of Dhara is visible to the contractor | Completed
49 | Anushravan | OHT name added in RFI | Completed
50 | FSTC Module | Work started on the FSTC Module, API received for the integration with Jal Samagra | I.P
51 | Dhara | Work needs to start on the Sub Meter Option on Web | Pending
52 | Dhara | On the web, we also need to provide the option to select the meter type during editing at GM login | Completed
53 | Shabhagita | New Report need to add in Shabhagita | Completed
54 | Nirmal | In Nirmal, we need to change the parameters range | Completed
55 | Asset Mapping | As Built Survey data 3 schemes- publish | Completed
56 | Bharosa | Factory Testing | I.P
57 | Dhara | GM given all option -Dhara Entry | Completed
For Department
Name
Approved By
Designation
Organization
Signature with Seal
Date

## NovtoDec
Sign-Off: |  | I hereby agree and approve that the specifications in this document constitute the complete scope of this project and will consequently meet the business and functional needs. Any requirement not explicitly mentioned in the specifications will be considered out of scope for this project. After approval, any additions and changes to this document or referred objects will be pursued through the change request process.
Work Status
S.NO | Module | Task | Status
1 | Module Names in Hindi | HSC – परिणाम Parinam | Done
O&M – आकलन Aaklan
Master – विस्तृत Vistrit
2 | Dhara | 1. Dhara Report approve Villiage wise or OHT -Village wise for a Range of each | Done
|  | 2. OHT Meter survey - divivde into 2 columns i) OHT Reading ii) OHT Water supply Status | Done UAT Column add
3 | Bharosa | 1. Factory Testing - Add sub component item and its matching electrical component (updated list need to be provided by department | Done
|  | 2 Factory Testing - Add "Any Other" option in Sub component & Item drop down and then Surveyor can write name in textbox | Done
4 | Nirmal & it's Reports | 1. Action on failed samples - into 2 columns i) failed sample rectified & document upload by contractor will be approved by GM ( action on failed samples) | In Progress
|  | 2 "Raw water wise test report" name change to "Raw water test report" | Done
|  | 3 Remove 2 columns - No of samples failed and No of samples passed and Remove wise in the report | Done
|  | 4 WTP Water test report - change 0.2 to 0.5 level of chlorine | Done
|  | 7. In Nirmal Final Report results failed parameter should appear in "RED Color" | In Progress
5 | Anushravan | 1 RFI transfer to new SQC already discuss with Balkrishnan and he will send the details | In Progress
|  | 2 GM can remove SQC & TPIC RFIs & SQC TPIA can remove FE RFI's (if loop is not currently running) | Already Functional
|  | 3 Sorting to be done on - Reinspections and Rejected RFI's | Done
|  | 4 Contractor should see FE's Comments | Done
6 | Sahbhagita | 1) Show video at PM Manager ID login also, as it is visible to GM login | Done
7 | Issues | 1) Contractor when mapping - SQC/TPIA then their mobile number should be shown with their ID | Done
|  | 2) Chindwara and Ujjain issue of village not showing mapping issue | Done
3) Where Habitation not available there we can show village name
|  | 4) When reading is 0 zero & showing no water supply - Remove that condition | In Progress
|  | 5) DeGM Chhatarpur - Date on web & Sorting to be done on - Reinspections and Rejected RFI's & Contractor should see FE's Comments | Discussed Done
|  | 6) SQC's can Reset Password feature | Done
For Department
Name
Approved By
Designation
Organization
Signature with Seal
Date

## Dec
Sign-Off: |  | I hereby agree and approve that the specifications in this document constitute the complete scope of this project and will consequently meet the business and functional needs. Any requirement not explicitly mentioned in the specifications will be considered out of scope for this project. After approval, any additions and changes to this document or referred objects will be pursued through the change request process.
Work Status
S.NO | Module | Task | Status
1 | Module Names in Hindi | HSC – परिणाम Parinam | Done
O&M – आकलन Aaklan
Master – विस्तृत Vistrit
2 | Dhara | 1. Dhara Report approve Villiage wise or OHT wise for a Range of 10 days each | In Progress
|  | 2. OHT Meter survey - divivde into 2 columns i) OHT Reading ii) OHT Water supply Status | In Progress
|  | 3. FE Entry TL can add remarks and finally GM only can approve it | In Progress
|  | 4. CWGM village mapping directly link to WTP | In Progress
3 | Bharosa | 1. Factory Testing - Add sub component item and its matching electrical component (updated list need to be provided by department | In Progress
|  | 2 Factory Testing - Add "Any Other" option in Sub component drop down and then Surveyor can write name in textbox | In Progress
4 | Nirmal & it's Reports | 1. Action on failed samples - into 2 columns i) failed sample rectified ii) failed sample pending | In Progress
|  | 2. Document upload by contractor will be approved by GM ( action on failed samples) | In Progress
|  | 3 "Raw water wise test report" name change to "Raw water test report" | Done
|  | 4 Remove 2 columns - No of samples failed and No of samples passed | In Progress
|  | 5 WTP Water test report - change 0.2 to 0.5 level of chlorine | In Progress
|  | 6 Remark comments for failed samples | Done
|  | 7. In Nirmal Final Report results failed parameter should appear in "RED Color" | In Progress
5 | RFI | 1 RFI transfer to new SQC | In Progress
|  | 2 Sorting to be done on - Reinspections and Rejected RFI's | In Progress
|  | 3 Contractor should see FE's Comments | In Progress
6 | Sahbhagita | 1) Show video at PM Manager ID login also, as it is visible to GM login | Done
7 | Issues | 1) Contractor when mapping - SQC/TPIA then their mobile number should be shown with their ID | In Progress
|  | 2) Chindwara and Ujjain issue of village not showing mapping issue | In Progress
|  | 3) Where Habitation not available there we can show village name | In Progress
|  | 4) When reading is 0 zero & showing no water supply - Remove that condition | In Progress
|  | 5) Anmol DeGM Chhatarpur - Sorting to be done on - Reinspections and Rejected RFI's & Contractor should see FE's Comments | In Progress
|  | 6) SQC's can Reset Password feature | In Progress
8 | O&M Billing - GM | 1) GM 24 PIUs data should be shown to Kapil admin id after save and submit | Done
|  | 2) Kapil id should be renamed to - "GM PIU O&M" | Done
|  | 3) For 1 village multiple time mapping should not be shown | Done
|  | 4) GM PIU and contractor name not coming correctly | Done
|  | 5) Agreement value column name and data should come correctly | Done
|  | 6) Field data should not change after logout then again at login time such as it is happening for "Additional Facilities tab" | Done
|  | 7) After changing scheme name - old filled scheme data is seen ( Refresh is not happening just like logout feature) | Done
9 | O&M Billing - Contractor | 1) Contractor -Billing | In Progress
|  | 2) CPI Base year and month calculation happen instantly | In Progress
|  | 3) Remark should come at the end in below report columns | In Progress
|  | 4) "No of HSC" is coming. Instead of that "Additional affected HSCs" should come in below report | In Progress
|  | 5) Complaint resolved date - it is "Resolved" word please check | In Progress
|  | 6) Type of Complaint - "Demand that cannot be fulfilled as per the agreement" - this is the correct statement | In Progress
|  | 7) Event before 48 hours should not get edited and count increase happen after 48 hours | In Progress
|  | 8) Reason for relaxation only become mandatory after clicking YES | In Progress
|  | 9) Penalty Relaxation spelling correct it | In Progress
|  | 10) All above fields should be visible in below reports and upload documents show in report | In Progress
|  | 11) Power Consumption - "Upload document (electricity bills of Intake, IPS, WTP)" in Single pdf | In Progress
|  | 12) Additional facilities - CPI Increaments should be shown in Manpower penalty column. Also, In Manpower, Vehile, other sections entries Save then Non Editable (freeze ) option has to be given. Also, No of Mobile should be <= No of Manpower and apply check | In Progress
|  | 13) Upload supporting doc (Sub Meter Reading Proof) - this statement should be added in that Label | In Progress
For Department
Name
Approved By
Designation
Organization
Signature with Seal
Date

## DectoJan26
Sign-Off: |  | I hereby agree and approve that the specifications in this document constitute the complete scope of this project and will consequently meet the business and functional needs. Any requirement not explicitly mentioned in the specifications will be considered out of scope for this project. After approval, any additions and changes to this document or referred objects will be pursued through the change request process.
Work Status
S.NO | Module | Task | Status
1 | O&M Billing - GM | 1) GM 24 PIUs data should be shown to Kapil admin id after save and submit | Done
|  | 2) Kapil id should be renamed to - "GM PIU O&M" | Done
|  | 3) For 1 village multiple time mapping should not be shown | Done
|  | 4) GM PIU and contractor name not coming correctly | Done
|  | 5) Agreement value column name and data should come correctly | Done
|  | 6) Field data should not change after logout then again at login time such as it is happening for "Additional Facilities tab" | Done
|  | 7) After changing scheme name - old filled scheme data is seen ( Refresh is not happening just like logout feature) | Done
2 | O&M Billing - Contractor | 1) Contractor -Billing | Done
|  | 2) CPI Base year and month calculation happen instantly | Done
|  | 3) Remark should come at the end in below report columns | Done
|  | 4) "No of HSC" is coming. Instead of that "Additional affected HSCs" should come in below report | Done
|  | 5) Complaint resolved date - it is "Resolved" word please check | Done
|  | 6) Type of Complaint - "Demand that cannot be fulfilled as per the agreement" - this is the correct statement | Done
|  | 7) Event before 48 hours should not get edited and count increase happen after 48 hours | Done
|  | 8) Reason for relaxation only become mandatory after clicking YES | Done
|  | 9) Penalty Relaxation spelling correct it | Done
|  | 10) All above fields should be visible in below reports and upload documents show in report | In Progress
|  | 11) Power Consumption - "Upload document (electricity bills of Intake, IPS, WTP)" in Single pdf | In Progress
|  | 12) Additional facilities - CPI Increaments should be shown in Manpower penalty column. Also, In Manpower, Vehile, other sections entries Save then Non Editable (freeze ) option has to be given. Also, No of Mobile should be <= No of Manpower and apply check | In Progress
|  | 13) Upload supporting doc (Sub Meter Reading Proof) - this statement should be added in that Label | In Progress
For Department
Name
Approved By
Designation
Organization
Signature with Seal
Date