## Sheet1
S.NO | Module | Task | Status
1 | Anushravan | Mobile application links with Sopan OHTs, once contractor add details in Sopan then only able to raise RFI | Completed
2 | Anushravan | OHT name added in RFI | Completed
3 | Asset Maping / Dhara | Renaming of OHTs | Completed
4 | Asset Mapping | New functionality added to download Executed and Planned data. | Completed
5 | Asset Mapping | OHT (Overhead Tank) labels have been added for improved visualization | Completed
6 | Asset Mapping | OHT,Intake,WTP, movement functionality | Completed
7 | Asset Mapping | As Built Survey data 3 schemes- publish | Completed
8 | Asset Mapping / Dhara | Deleting Duplicate Entries of Components | Completed
9 | Bharosa | Factory Testing | I.P
10 | Changes User management | Multiple scheme Sqc & Tpia id - change in RFI flow | Completed
11 | Dhara | GM given all option -Dhara Entry | Completed
12 | Dhara | Mobile Application: New Features Implemented to capture meter status with the categories like Functional Meter, Meter Replaced, Non-Functional Meter, No Water Supplied | Completed
13 | Dhara | New Reports Developed: Monthly Water Supply Report | Completed
14 | Dhara | New Reports Developed: Village-Wise MWSR Report | Completed
15 | Dhara | The existing MWSR Report has been renamed to UFW Report | Completed
16 | Dhara | Drill-down feature added to the reports for better data navigation. | Completed
17 | Dhara | Developing meter reading editing functionality for GM login. | Completed
18 | Dhara | Billing of O&M Contractors | Completed
19 | Dhara | Mapping of villages with different components | Completed
20 | Dhara | Same Village issue identified and resolved | Completed
21 | Dhara | Date Range option in meter reading approval pages | Completed
22 | Dhara | The report of Dhara is visible to the contractor | Completed
23 | Dhara | Work needs to start on the Sub Meter Option on Web | Pending
24 | Dhara | On the web, we also need to provide the option to select the meter type during editing at GM login | Completed
25 | Dhara Module | Resolve the issues of 2 OHTs during mapping | Completed
26 | Dhara Module | Correction of Dhara Reports | Completed
27 | Dhara Module updation | Updation Dhara module | Completed
28 | Dhara Reading approved | Date wise Dhara reading approved | Completed
29 | FSTC Module | Work started on the FSTC Module, API received for the integration with Jal Samagra | I.P
30 | Geoportal | Search option | Completed
31 | Master | Pipeline master | Completed
32 | Nirmal | Functionality for contractor to take water samples | Completed
33 | Nirmal | In Nirmal, we need to change the parameters range | Completed
34 | Pile Line master in Mobile | Generate RFI Contractor (Pipe line Master Data) | Completed
35 | Pile Line master web | Show in Report Pipe line master data (RFI) | Completed
36 | Pipeline Master | Reports of pipeline master with drop down functionality | Completed
37 | Pipeline Master | CWPM, CWGM need to add zones numbers | Completed
38 | Pipeline Master | Zone number added in CWPM component | Completed
39 | Reports | All reports are made available to all logging with there respect to there area | Completed
40 | Sc Name short in Application | Short Name of Schemes | Completed
41 | Shabhagita | Activity Upload through Web Portal | Completed
42 | Shabhagita | Multiple Photo Upload | Completed
43 | Shabhagita | Activity Delete Option for GM | Need to Discuss-No need
44 | Shabhagita | New Report need to add in Shabhagita | Completed
45 | Sopan | New Features Added: Upload functionality for Panchnama Report and Approved Design & Drawing Report. Option provided for users to upload additional supporting documents. | Completed
46 | Sopan | New report created for the OHT details monitoring | Completed
47 | Sopan | Feature developed for capturing intake details. | Completed
48 | Sopan | Functionality to Edit Planned Dates at GM login | Completed
49 | Sopan | Functionality to Add Actual Dates at GM login | Completed
50 | Sopan | Functionality for GM to add remarks | Completed
51 | Sopan | Sopan Module for capturing WTP (Water Treatment Plant) details. | Completed
52 | Sopan | Sopan module for capturing Intermediate Pumping Station (IPS) Details | Completed
53 | Sopan | Option to finalize plan start and plan completion | Completed
54 | Sopan Module WTP | Need to provide the functionality for finalized the planed date at GM login | Completed
55 | Sopan Module WTP | Design and Panchnama (Each activity) | Completed
56 | Sopan Report | Report Hyperlink | Completed

## Sheet2
S.NO | Module | Task | Status
1 | Anushravan | OHT name added in RFI | Completed
2 | Asset Mapping | As Built Survey data 3 schemes- publish | Completed
3 | Bharosa | Factory Testing | I.P
4 | Dhara | GM given all option -Dhara Entry | Completed
5 | Dhara | The report of Dhara is visible to the contractor | Completed
6 | Dhara | Work needs to start on the Sub Meter Option on Web | Pending
7 | Dhara | On the web, we also need to provide the option to select the meter type during editing at GM login | Completed
8 | FSTC Module | Work started on the FSTC Module, API received for the integration with Jal Samagra | I.P
9 | Nirmal | In Nirmal, we need to change the parameters range | Completed
10 | Shabhagita | New Report need to add in Shabhagita | Completed
11 | Sopan Report | Report Hyperlink | Completed