## Gantt Chart
Jal Rekha – Cycle 4 Gantt Chart ¦ January 2026 – June 2026 ¦ MPSeDC / CMMI L5
[5 empty] | Jan 2026 |  |  |  | Feb 2026 |  |  |  | Mar 2026 |  |  |  |  | Apr 2026 |  |  |  | May 2026 |  |  |  |  | Jun 2026
# | Module | Task / Work Package | Owner | Hrs | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26
1 | Anusharavan | ── Full Module Lifecycle ── | BA/Dev | 84
1.1 |  | CR – RFI New Stages & Stage Updation | BA/Dev | 28
1.2 |  | UI Enhancement – Contractor & FE Login | BA/Dev | 20
1.3 |  | View Details/Log View & Inspection Request | BA/Dev | 20
1.4 |  | Accuracy field; Daily Inspection search | BA/Dev | 8
1.5 |  | UAT, regression, Play Store release | BA/Dev | 8
2 | Asset Mapping | ── Full Module Lifecycle ── | Dev | 42
2.1 |  | OHT village mapping production fix | Dev | 10
2.2 |  | OHT search box on map (GET/SET) | Dev | 16
2.3 |  | Asset mapping page redesign | Dev | 16
3 | Bharosa Factory Testing | ── Full Module Lifecycle ── | Dev/QA | 120
3.1 |  | Web – inner redesign, multi-doc upload, 3rd Party QAP | Dev/QA | 44
3.2 |  | Mobile – QAP download, Contractor login, Play Store | Dev/QA | 36
3.3 |  | CR – Report View (GM/PIU), DB architecture | Dev/QA | 24
3.4 |  | UAT, regression, final release | Dev/QA | 16
4 | Cube Testing (New) | ── Full Module Lifecycle ── | Dev/QA | 344
4.1 |  | Requirement Analysis, DB schema, Master tables | Dev/QA | 60
4.2 |  | Contractor Login – UI, API, 7/28-day RFI logic | Dev/QA | 80
4.3 |  | FE Login – wireframe, form, mobile API | Dev/QA | 80
4.4 |  | GM / SQC / TPIA – RFI status, read access | Dev/QA | 60
4.5 |  | CR – PDF upload, filter bed sub-component | Dev/QA | 40
4.6 |  | UAT, regression, Play Store deployment | Dev/QA | 24
5 | Daily Inspection | ── Full Module Lifecycle ── | Dev | 12
5.1 |  | Search by Survey ID | Dev | 4
5.2 |  | View Logs display bug fix (mobile) | Dev | 8
6 | Dashboard & Public Reports | ── Full Module Lifecycle ── | Dev/BA | 46
6.1 |  | Jal Rekha brochure wireframing | Dev/BA | 6
6.2 |  | Public DWSR report on dashboard | Dev/BA | 16
6.3 |  | Module sequence & Left Menu colour coding | Dev/BA | 24
7 | Dhara Module CR | ── Full Module Lifecycle ── | Dev/BA/QA | 340
7.1 |  | Intake/WTP/OHT Meter Survey re-sequencing | Dev/BA/QA | 96
7.2 |  | DWSR, MWSR, Bulk Consumer, UFW reports | Dev/BA/QA | 80
7.3 |  | GM Approval / Contractor Dispute / Auto-approve | Dev/BA/QA | 60
7.4 |  | DWSR hyperlinks, abstract, restrict schemes | Dev/BA/QA | 48
7.5 |  | New Dhara Report rollout; Mohkhed bug fix | Dev/BA/QA | 32
7.6 |  | Site Security Audit fixes; UFW correction | Dev/BA/QA | 24
8 | FHTC / Parinaam | ── Full Module Lifecycle ── | Dev/AI | 256
8.1 |  | Loop/Re-inspection form, History screen | Dev/AI | 84
8.2 |  | Stage 1/2/3 sequential flow | Dev/AI | 60
8.3 |  | Geo-fencing (30m), Accepted/Rejected | Dev/AI | 40
8.4 |  | AI/ML Tap Connection monitoring | Dev/AI | 48
8.5 |  | Public reports on Dashboard; UAT/release | Dev/AI | 24
9 | Master Module CR | ── Full Module Lifecycle ── | Dev/BA | 198
9.1 |  | Scheme Village & OHT Master – validations | Dev/BA | 66
9.2 |  | Bulk Consumer Master – CRUD, 2-screen split | Dev/BA | 48
9.3 |  | WTP Meter Mapping – new columns | Dev/BA | 36
9.4 |  | Pipeline Master; Vistrit Summary Report | Dev/BA | 48
10 | Material Testing CR | ── Full Module Lifecycle ── | Dev/QA | 180
10.1 |  | GM/Contractor Login – SQC/TPIA, reports | Dev/QA | 90
10.2 |  | FE Login – mobile API, OHT search | Dev/QA | 60
10.3 |  | UAT/Prod testing, Promot, Play Store | Dev/QA | 30
11 | Nirmal Module CR | ── Full Module Lifecycle ── | Dev/QA | 108
11.1 |  | FE Mobile – reports & FRC fix | Dev/QA | 58
11.2 |  | Water quality test, Pending Samples | Dev/QA | 36
11.3 |  | Contractor-only scheme; UAT & prod move | Dev/QA | 14
12 | O&M Billing CR | ── Full Module Lifecycle ── | Dev/BA/QA | 593
12.1 |  | GM – Power Consumption, Summary, RA Bill No. | Dev/BA/QA | 136
12.2 |  | Contractor – Excel, Residual Pressure, Net Payable | Dev/BA/QA | 117
12.3 |  | Dhara Report integration in O&M | Dev/BA/QA | 80
12.4 |  | Bill generation – 64 schemes, all PIUs | Dev/BA/QA | 60
12.5 |  | Redundant reports removal; DWSR hyperlink | Dev/BA/QA | 32
12.6 |  | O&M Billing Workflow (Firm→MD multi-level) | Dev/BA/QA | 120
12.7 |  | Power Consumption bill; Pump Transformer 10% | Dev/BA/QA | 48
13 | Sahbhagita CR | ── Full Module Lifecycle ── | Dev/BA | 172
13.1 |  | ISA payment; CR Manager Approve step | Dev/BA | 48
13.2 |  | RA Bill on CP Manager; Save as Draft | Dev/BA | 36
13.3 |  | Village-wise & Combined activity billing | Dev/BA | 48
13.4 |  | Generate Abstract – Select RA Bill; multi-select | Dev/BA | 40
14 | SVS Water Supply (New) | ── Full Module Lifecycle ── | Dev/BA | 140
14.1 |  | DB schema, Master tables, form design | Dev/BA | 40
14.2 |  | Web & Mobile – Yes/No/Partial form | Dev/BA | 60
14.3 |  | Partial Edit, Hindi UI, LGD code export | Dev/BA | 24
14.4 |  | UAT, regression, release | Dev/BA | 16
15 | CMMI L5 Documentation | ── Full Module Lifecycle ── | BA/QA | 500
15.1 |  | Cycle 3 documents preparation | BA/QA | 80
15.2 |  | UI-level CMMI docs (all modules) | BA/QA | 180
15.3 |  | CMMI presentation, MQAS review | BA/QA | 80
15.4 |  | Cycle 4 BRTM, US, SRS, RRD finalisation | BA/QA | 120
15.5 |  | Final audit submission and sign-off | BA/QA | 40
16 | Site Security & User Roles | ── Full Module Lifecycle ── | Dev/Admin | 48
16.1 |  | Security audit fixes (role-based access) | Dev/Admin | 32
16.2 |  | User role creation for new modules | Dev/Admin | 16
17 | Sopan Contractor | ── Full Module Lifecycle ── | Dev | 6
17.1 |  | OHT mapping issue; WTP scheme bug fix | Dev | 5
17.2 |  | IPS production issue resolution | Dev | 1
Legend:
| 1:Anusharavan | 2:Asset Mappin | 3:Bharosa Fact | 4:Cube Testing | 5:Daily Inspec | 6:Dashboard & | 7:Dhara Module | 8:FHTC / Parin | 9:Master Modul | 10:Material Tes | 11:Nirmal Modul | 12:O&M Billing | 13:Sahbhagita C