Work Breakdown Structure (WBS) – Jal Rekha Project

Cycle 4: January 2026 – June 2026  |  CMMI Level 5

| Document Title | Work Breakdown Structure – Cycle 4 |  |  | Project | Jal Rekha |  | Version | 1.0 |  | Period | Jan 2026 – Jun 2026 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Prepared By | Mr. Dheeraj Motiyani, Sr. BA |  |  | Reviewed By | Mr. Tapan Khandelwal, PM |  | Approved By | Dr. Rakesh Dubey |  | Date | 22-Jun-2026 |  |  |  |

Introduction

This Work Breakdown Structure (WBS) defines the complete scope of work for Jal Rekha Cycle 4 (January–June 2026), aligned with CMMI Level 5 standards. Cycle 4 encompasses new module development, change requests across all existing modules, CMMI documentation, and the first release of the O&M Billing multi-level workflow and SVS Water Supply Monitoring module.

Objective of WBS

To provide a structured hierarchical view of all Cycle 4 deliverables, enabling effective planning, resource allocation, chronological tracking, effort measurement, and quantitative process control in alignment with CMMI Level 5 process areas (PP, PMC, REQM, CM).

MODULE SUMMARY – CYCLE 4 (17 MODULES)

| # | Module | Timeline | Owner | Total Effort (Hrs) | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | Anusharavan | Wk1–Wk8 | BA / Dev Team | 84 | Done |
| 2 | Asset Mapping | Wk1–Wk3 | Dev Team | 42 | Done |
| 3 | Bharosa Factory Testing | Wk1–Wk8 | Dev / QA Team | 120 | Done |
| 4 | Cube Testing (New Module) | Wk5–Wk14 | Dev / QA Team | 344 | Done |
| 5 | Daily Inspection | Wk1–Wk2 | Dev Team | 12 | Done |
| 6 | Dashboard & Public Reports | Wk3–Wk8 | Dev / BA | 46 | Done |
| 7 | Dhara Module CR | Wk1–Wk18 | Dev / BA / QA | 340 | Done |
| 8 | FHTC / Parinaam | Wk5–Wk16 | Dev / AI Team | 256 | Done |
| 9 | Master Module CR | Wk4–Wk12 | Dev / BA | 198 | Done |
| 10 | Material Testing CR | Wk1–Wk8 | Dev / QA | 180 | Done |
| 11 | Nirmal Module CR | Wk1–Wk6 | Dev / QA | 108 | Done |
| 12 | O&M Billing (Aakalan) CR | Wk1–Wk22 | Dev / BA / QA | 593 | In Progress |
| 13 | Sahbhagita CR | Wk3–Wk14 | Dev / BA | 172 | In Progress |
| 14 | SVS – Water Supply Monitoring (New) | Wk16–Wk22 | Dev / BA | 140 | Done |
| 15 | CMMI L5 Documentation | Wk1–Wk26 | BA / QA | 500 | In Progress |
| 16 | Site Security Audit & User Role Management | Wk10–Wk14 | Dev / Admin | 48 | Done |
| 17 | Sopan Contractor | Wk3–Wk5 | Dev Team | 6 | Done |
|  | TOTAL | Jan – Jun 2026 |  | 3189 hrs |  |

DETAILED WBS – WORK PACKAGES & TASKS

| WBS ID | Module | Work Package / Task | Phase | Timeline | Owner | Effort (Hrs) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Anusharavan | Anusharavan – Full Lifecycle | Full Lifecycle | Wk1–Wk8 | BA / Dev Team | 84 |
| 1.1 | Anusharavan | CR – RFI New Stages & Stage Updation | Design/Dev | Wk1–Wk2 | BA / Dev Team | 28 |
| 1.2 | Anusharavan | UI Enhancement – Contractor & FE Login | Dev/Test | Wk3–Wk4 | BA / Dev Team | 20 |
| 1.3 | Anusharavan | View Details/Log View & Inspection Request Enhancement | Dev/Test | Wk5–Wk6 | BA / Dev Team | 20 |
| 1.4 | Anusharavan | Accuracy field changes; Daily Inspection search | Dev/Test | Wk7 | BA / Dev Team | 8 |
| 1.5 | Anusharavan | UAT, regression, Play Store release | UAT/Release | Wk8 | BA / Dev Team | 8 |
| 2 | Asset Mapping | Asset Mapping – Full Lifecycle | Full Lifecycle | Wk1–Wk3 | Dev Team | 42 |
| 2.1 | Asset Mapping | OHT village mapping production data fix | Dev/Fix | Wk1 | Dev Team | 10 |
| 2.2 | Asset Mapping | OHT search box on map (GET/SET API methods) | Dev/Test | Wk2 | Dev Team | 16 |
| 2.3 | Asset Mapping | Asset mapping page redesign (Jal Rekha & Amrut Rekha) | Dev | Wk3 | Dev Team | 16 |
| 3 | Bharosa Factory Testing | Bharosa Factory Testing – Full Lifecycle | Full Lifecycle | Wk1–Wk8 | Dev / QA Team | 120 |
| 3.1 | Bharosa Factory Testing | Web – Inner page redesign, multi-doc upload, 3rd Party QAP upload | Design/Dev | Wk1–Wk3 | Dev / QA Team | 44 |
| 3.2 | Bharosa Factory Testing | Mobile – QAP download, Contractor login, Play Store | Dev/Release | Wk4–Wk5 | Dev / QA Team | 36 |
| 3.3 | Bharosa Factory Testing | CR – Report View (GM/PIU), DB architecture/Master Check | Dev/Test | Wk6–Wk7 | Dev / QA Team | 24 |
| 3.4 | Bharosa Factory Testing | UAT, regression testing, final release | UAT/Release | Wk8 | Dev / QA Team | 16 |
| 4 | Cube Testing (New Module) | Cube Testing (New Module) – Full Lifecycle | Full Lifecycle | Wk5–Wk14 | Dev / QA Team | 344 |
| 4.1 | Cube Testing (New Module) | Requirement Analysis, DB schema, Master tables design | Analysis/Design | Wk5–Wk6 | Dev / QA Team | 60 |
| 4.2 | Cube Testing (New Module) | Contractor Login – UI, API, 7-day/28-day RFI logic | Dev | Wk7–Wk8 | Dev / QA Team | 80 |
| 4.3 | Cube Testing (New Module) | FE Login – wireframe, form, mobile API | Dev | Wk7–Wk9 | Dev / QA Team | 80 |
| 4.4 | Cube Testing (New Module) | GM / SQC / TPIA – RFI status update, read access | Dev | Wk9–Wk10 | Dev / QA Team | 60 |
| 4.5 | Cube Testing (New Module) | CR – Post-UAT changes (PDF upload, filter bed sub-component) | Dev/Fix | Wk11–Wk12 | Dev / QA Team | 40 |
| 4.6 | Cube Testing (New Module) | UAT, regression, Play Store deployment | UAT/Release | Wk13–Wk14 | Dev / QA Team | 24 |
| 5 | Daily Inspection | Daily Inspection – Full Lifecycle | Full Lifecycle | Wk1–Wk2 | Dev Team | 12 |
| 5.1 | Daily Inspection | Search by Survey ID – FE and Contractor login | Dev/Test | Wk1 | Dev Team | 4 |
| 5.2 | Daily Inspection | View Logs display bug fix (mobile app) | Dev/Fix | Wk2 | Dev Team | 8 |
| 6 | Dashboard & Public Reports | Dashboard & Public Reports – Full Lifecycle | Full Lifecycle | Wk3–Wk8 | Dev / BA | 46 |
| 6.1 | Dashboard & Public Reports | Jal Rekha brochure (4-page) wireframing | Design | Wk3 | Dev / BA | 6 |
| 6.2 | Dashboard & Public Reports | Public DWSR report exposed on dashboard | Dev/Test | Wk4–Wk5 | Dev / BA | 16 |
| 6.3 | Dashboard & Public Reports | Module sequence change and Left Menu colour coding | Dev/Test | Wk6–Wk8 | Dev / BA | 24 |
| 7 | Dhara Module CR | Dhara Module CR – Full Lifecycle | Full Lifecycle | Wk1–Wk18 | Dev / BA / QA | 340 |
| 7.1 | Dhara Module CR | Intake/WTP/OHT Meter Survey re-sequencing (GM Login) | Design/Dev | Wk1–Wk3 | Dev / BA / QA | 96 |
| 7.2 | Dhara Module CR | DWSR, MWSR, Bulk Consumer, UFW reports recreate & fetch | Dev | Wk4–Wk6 | Dev / BA / QA | 80 |
| 7.3 | Dhara Module CR | GM Approval / Contractor Dispute / Auto-approve 3-day logic | Dev/Test | Wk7–Wk9 | Dev / BA / QA | 60 |
| 7.4 | Dhara Module CR | DWSR hyperlinks, abstract of contract, restrict Nemawar/Rignod | Dev/Test | Wk10–Wk12 | Dev / BA / QA | 48 |
| 7.5 | Dhara Module CR | New Dhara Report rollout to all logins; Mohkhed tapping-point bug fix | Dev/Fix | Wk13–Wk15 | Dev / BA / QA | 32 |
| 7.6 | Dhara Module CR | Site Security Audit fixes; UFW report correction | Dev/Fix | Wk16–Wk18 | Dev / BA / QA | 24 |
| 8 | FHTC / Parinaam | FHTC / Parinaam – Full Lifecycle | Full Lifecycle | Wk5–Wk16 | Dev / AI Team | 256 |
| 8.1 | FHTC / Parinaam | Loop/Re-inspection form, History screen, Contractor login API | Dev | Wk5–Wk7 | Dev / AI Team | 84 |
| 8.2 | FHTC / Parinaam | Stage 1/2/3 (Connection/Work Done/Payment) sequential flow | Dev/Test | Wk8–Wk10 | Dev / AI Team | 60 |
| 8.3 | FHTC / Parinaam | Geo-fencing (30m Google AI), Accepted/Rejected with View Log | Dev/Test | Wk11–Wk12 | Dev / AI Team | 40 |
| 8.4 | FHTC / Parinaam | AI/ML – FHTC Tap Connection monitoring, buffer region | Dev/AI | Wk13–Wk14 | Dev / AI Team | 48 |
| 8.5 | FHTC / Parinaam | All public reports on Dashboard; UAT, release | UAT/Release | Wk15–Wk16 | Dev / AI Team | 24 |
| 9 | Master Module CR | Master Module CR – Full Lifecycle | Full Lifecycle | Wk4–Wk12 | Dev / BA | 198 |
| 9.1 | Master Module CR | Scheme Village & OHT Master – validations, Local Name column | Design/Dev | Wk4–Wk5 | Dev / BA | 66 |
| 9.2 | Master Module CR | Bulk Consumer Master – Add/Update/Delete, 2-screen split | Dev/Test | Wk6–Wk7 | Dev / BA | 48 |
| 9.3 | Master Module CR | WTP Meter Mapping – new columns (Meter Name, OHT count, type) | Dev | Wk8–Wk9 | Dev / BA | 36 |
| 9.4 | Master Module CR | Pipeline Master – details & report pages; Vistrit Summary Report | Dev/Test | Wk10–Wk12 | Dev / BA | 48 |
| 10 | Material Testing CR | Material Testing CR – Full Lifecycle | Full Lifecycle | Wk1–Wk8 | Dev / QA | 180 |
| 10.1 | Material Testing CR | GM/Contractor Login – SQC/TPIA login, customised reports | Dev/Test | Wk1–Wk3 | Dev / QA | 90 |
| 10.2 | Material Testing CR | FE Login – mobile API, OHT search, Save as Draft | Dev/Test | Wk3–Wk5 | Dev / QA | 60 |
| 10.3 | Material Testing CR | UAT/Prod testing, Promot update, Play Store merge | UAT/Release | Wk6–Wk8 | Dev / QA | 30 |
| 11 | Nirmal Module CR | Nirmal Module CR – Full Lifecycle | Full Lifecycle | Wk1–Wk6 | Dev / QA | 108 |
| 11.1 | Nirmal Module CR | FE Mobile – Beneficiary/OHT/WTP/Raw Water reports & FRC fix | Dev/Test | Wk1–Wk3 | Dev / QA | 58 |
| 11.2 | Nirmal Module CR | Water quality test – FRC value, Pending Samples, failed sample remark | Dev/Test | Wk4–Wk5 | Dev / QA | 36 |
| 11.3 | Nirmal Module CR | Contractor-only scheme display; UAT and production move | UAT/Release | Wk6 | Dev / QA | 14 |
| 12 | O&M Billing (Aakalan) CR | O&M Billing (Aakalan) CR – Full Lifecycle | Full Lifecycle | Wk1–Wk22 | Dev / BA / QA | 593 |
| 12.1 | O&M Billing (Aakalan) CR | GM – Power Consumption, Summary tab, Bulk User, RA Bill No. generation | Dev/Test | Wk1–Wk4 | Dev / BA / QA | 136 |
| 12.2 | O&M Billing (Aakalan) CR | Contractor CR – Excel export, Residual Pressure, Complaint Redressal, Net Payable | Dev/Test | Wk5–Wk8 | Dev / BA / QA | 117 |
| 12.3 | O&M Billing (Aakalan) CR | Dhara Report integration in O&M Billing; DWSR/MWSR/UFW merge | Dev/Test | Wk9–Wk11 | Dev / BA / QA | 80 |
| 12.4 | O&M Billing (Aakalan) CR | Bill generation for 64 schemes – end-to-end PIU runs | Dev/Test | Wk12–Wk14 | Dev / BA / QA | 60 |
| 12.5 | O&M Billing (Aakalan) CR | Remove redundant reports; Public DWSR clickable hyperlink | Dev/Test | Wk15–Wk16 | Dev / BA / QA | 32 |
| 12.6 | O&M Billing (Aakalan) CR | O&M Billing Workflow (multi-level: Firm→MD) – UI, User WF, GM(PIU) lock | Design/Dev | Wk17–Wk20 | Dev / BA / QA | 120 |
| 12.7 | O&M Billing (Aakalan) CR | Power Consumption bill (Contractor+GM), Pump Transformer 10% deduction | Dev/Test | Wk21–Wk22 | Dev / BA / QA | 48 |
| 13 | Sahbhagita CR | Sahbhagita CR – Full Lifecycle | Full Lifecycle | Wk3–Wk14 | Dev / BA | 172 |
| 13.1 | Sahbhagita CR | ISA payment tracking; CR Manager Approve step | Dev/Test | Wk3–Wk5 | Dev / BA | 48 |
| 13.2 | Sahbhagita CR | RA Bill on CP Manager; Save as Draft (video/images/docs) | Dev/Test | Wk6–Wk8 | Dev / BA | 36 |
| 13.3 | Sahbhagita CR | Village-wise activity & Combined activity billing | Dev/Test | Wk9–Wk11 | Dev / BA | 48 |
| 13.4 | Sahbhagita CR | Generate Abstract – Select RA Bill; multi-select dropdown | Dev/Test | Wk12–Wk14 | Dev / BA | 40 |
| 14 | SVS – Water Supply Monitoring (New) | SVS – Water Supply Monitoring (New) – Full Lifecycle | Full Lifecycle | Wk16–Wk22 | Dev / BA | 140 |
| 14.1 | SVS – Water Supply Monitoring (New) | DB schema, Master tables, GP/PHE form design | Analysis/Design | Wk16–Wk17 | Dev / BA | 40 |
| 14.2 | SVS – Water Supply Monitoring (New) | Web & Mobile – form (Yes/No/Partial, Date picker, Reason dropdown) | Dev | Wk18–Wk20 | Dev / BA | 60 |
| 14.3 | SVS – Water Supply Monitoring (New) | Partial Edit (DD), MP Shashan Hindi UI, LGD code export | Dev/Test | Wk21 | Dev / BA | 24 |
| 14.4 | SVS – Water Supply Monitoring (New) | UAT, regression, release | UAT/Release | Wk22 | Dev / BA | 16 |
| 15 | CMMI L5 Documentation | CMMI L5 Documentation – Full Lifecycle | Full Lifecycle | Wk1–Wk26 | BA / QA | 500 |
| 15.1 | CMMI L5 Documentation | Cycle 3 document preparation and review | Documentation | Wk1–Wk4 | BA / QA | 80 |
| 15.2 | CMMI L5 Documentation | UI-level CMMI docs (Dhara, Nirmal, Bharosa, Material, O&M) | Documentation | Wk5–Wk12 | BA / QA | 180 |
| 15.3 | CMMI L5 Documentation | CMMI presentation, MQAS review meeting, findings closure | Review | Wk13–Wk18 | BA / QA | 80 |
| 15.4 | CMMI L5 Documentation | Cycle 4 BRTM, User Stories, SRS, RRD finalisation | Documentation | Wk19–Wk24 | BA / QA | 120 |
| 15.5 | CMMI L5 Documentation | Final audit submission and sign-off | Closure | Wk25–Wk26 | BA / QA | 40 |
| 16 | Site Security Audit & User Role Management | Site Security Audit & User Role Management – Full Lifecycle | Full Lifecycle | Wk10–Wk14 | Dev / Admin | 48 |
| 16.1 | Site Security Audit & User Role Management | Security audit fixes (role-based access, Dhara/O&M) | Dev/Fix | Wk10–Wk12 | Dev / Admin | 32 |
| 16.2 | Site Security Audit & User Role Management | User role creation and management for new modules | Dev/Test | Wk13–Wk14 | Dev / Admin | 16 |
| 17 | Sopan Contractor | Sopan Contractor – Full Lifecycle | Full Lifecycle | Wk3–Wk5 | Dev Team | 6 |
| 17.1 | Sopan Contractor | OHT mapping issue, WTP scheme bug fix (Rewa Bansagar) | Dev/Fix | Wk3–Wk4 | Dev Team | 5 |
| 17.2 | Sopan Contractor | IPS production issue resolution | Dev/Fix | Wk5 | Dev Team | 1 |

Page 1 of 1  |  Jal Rekha – WBS Cycle 4  |  January 2026 – June 2026