## Version
JAL REKHA – CHANGE REQUEST LOG ¦ CYCLE 4 ¦ JANUARY 2026 – MAY 2026
Project: Jal Rekha ¦ Dept: Public Health Engineering (PHE), Madhya Pradesh
Version | Date | Description | Prepared By | Reviewed By | Status | Approved By | Approval Date
1.0 | 01-Jan-2026 | Initial CR Log – Cycle 4 (Jan–May 2026) | Mr. Dheeraj Motiyani | Mr. Tapan Khandelwal | Released | Mr. Tapan Khandelwal | 15-Jan-2026
1.1 | 01-Feb-2026 | Added O&M Billing, Dhara, Master CRs (Jan batch) | Mr. Dheeraj Motiyani | Mr. Tapan Khandelwal | Released | Mr. Tapan Khandelwal | 05-Feb-2026
1.2 | 01-Mar-2026 | Added FHTC, Nirmal, Sahbhagita CRs (Feb batch) | Mr. Dheeraj Motiyani | Mr. Tapan Khandelwal | Released | Mr. Tapan Khandelwal | 05-Mar-2026
1.3 | 01-Apr-2026 | Added Cube Testing, Bharosa CRs (Mar batch) | Mr. Dheeraj Motiyani | Mr. Tapan Khandelwal | Released | Mr. Tapan Khandelwal | 05-Apr-2026
1.4 | 01-May-2026 | Added SVS, AI FHTC, Material, Site Security CRs (Apr batch) | Mr. Dheeraj Motiyani | Mr. Tapan Khandelwal | Released | Mr. Tapan Khandelwal | 05-May-2026
1.5 | 16-Jun-2026 | Final consolidated CR log – All modules Jan–May 2026 | Mr. Dheeraj Motiyani | Mr. Tapan Khandelwal | Final | Mr. Tapan Khandelwal | 16-Jun-2026

## Summary
JAL REKHA – CR LOG CYCLE 4 ¦ CONSOLIDATED SUMMARY ¦ JAN 2026 – MAY 2026
Module | Sub-Module | Total CRs | Completed | In Progress | Planned | Not Done / Critical | Approved | Pending | Overall Priority | Risk Level
Anusharavaan | RFI Module | 7 | 6 | 1 | 0 | 0 | 5 | 2 | High | Low
Asset Mapping | Asset Mapping | 5 | 5 | 0 | 0 | 0 | 5 | 0 | Medium | Low
Bharosa | Factory Testing Web + Mobile + Reports | 5 | 5 | 0 | 0 | 0 | 5 | 0 | High | Medium
Dhara | Meter Survey, Reports, Workflow, Security | 10 | 6 | 2 | 0 | 2 | 8 | 2 | High | High
FHTC | FE Reports, CR, AI Module | 4 | 4 | 0 | 0 | 0 | 4 | 0 | High | Medium
Master | GM/Contractor, Schema, Vistrit, Bulk Consumer | 6 | 6 | 0 | 0 | 0 | 6 | 0 | High | Medium
Material Testing | FE Login, GM/Contractor Login, CR/QA | 3 | 3 | 0 | 0 | 0 | 3 | 0 | Medium | Low
Nirmal | WTP, OHT, Beneficiary, Raw Water Reports | 5 | 5 | 0 | 0 | 0 | 5 | 0 | High | Low
O&M Billing | GM, Contractor, Reports, Workflow, May CR | 7 | 5 | 0 | 0 | 2 | 5 | 2 | High | High
Sahbhagita | Reports, GM/PM, Payment CR | 4 | 4 | 0 | 0 | 0 | 4 | 0 | Medium | Low
Cube Testing | Contractor, FE, GM, SQC/TPIA, CR | 5 | 5 | 0 | 0 | 0 | 5 | 0 | Medium | Low
SVS | Water Supply Monitoring, Reports, Public Dashboard | 3 | 3 | 0 | 0 | 0 | 3 | 0 | Medium | Low
TOTAL | All Modules | [7 empty] | Mixed | Mixed

## Anusharavaan CR
CHANGE REQUEST LOG – ANUSHARAVAAN CR ¦ Jal Rekha ¦ PHE, Madhya Pradesh ¦ January 2026 – May 2026
Module: Anusharavaan – RFI Module ¦ Department: Public Health Engineering ¦ Period: January 2026 – May 2026
CR No. | CR Code | CR Raised By | Req. Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Impl. Status | Impl. Date | Approval Status | Priority | Risk Level | Effort (Hrs) | Remarks
CR-ANU-001 | ANU-RFI-2025-001 | Business Analyst | Senior BA | 08-Nov-2025 | Redesign new inner pages of Jal Rekha RFI module with improved navigation and UI standards | Jal Rekha | Anusharavaan – RFI | UI/UX Redesign | High – Affects user experience and navigation efficiency across all users | Completed | 20-Nov-2025 | Approved | High | Low | 120 | RFI inner page redesign completed and deployed
CR-ANU-002 | ANU-RFI-2025-002 | Business Analyst | Senior BA | 11-Nov-2025 | RFI Module – Update History Screen Search Functionality for Contractor and Field Engineer logins | Jal Rekha | Anusharavaan – RFI | Reporting & Analytics | Medium – Improves search usability for contractor and FE logins in RFI history | Completed | 15-Nov-2025 | Approved | Medium | Low | 21 | History search functionality updated
CR-ANU-003 | ANU-RFI-2025-003 | Business Analyst | Senior BA | 12-Nov-2025 | Addition of FE Inspection Details (PIU) in Anusharavaan and Customized Report generation | Jal Rekha | Anusharavaan – RFI | Report Generation | High – PIU FE inspection data now captured and visible in customized reports | Completed | 25-Nov-2025 | Approved | High | Low | 21 | FE inspection date added in PIU pending pages and reports
CR-ANU-004 | ANU-RFI-2025-004 | Business Analyst | Senior BA | 15-Nov-2025 | RFI Module – Post-Fix Verification of Pipeline Details on History Detail Screen (Play Store Live Build) | Jal Rekha | Anusharavaan – RFI | Database Architecture | Medium – Ensures pipeline details display correctly on live Play Store build | Completed | 02-Dec-2025 | Approved | Medium | Low | 29 | Pipeline details verified on history screen after prod fix
CR-ANU-005 | ANU-RFI-2025-005 | Business Analyst | Senior BA | 18-Nov-2025 | New RFI Stages added: Update RFI Stage workflow, Inspection Request Point Dialog, Pipeline Details on History page | Jal Rekha | Anusharavaan – RFI | Workflow Management | High – New workflow stages introduced affecting contractor and FE RFI flow | In Progress | 05-Dec-2025 | Pending | High | Medium | 141 | New stages for RFI integrated; mobile deployment pending
CR-ANU-006 | ANU-RFI-2025-006 | Business Analyst | Senior BA | 21-Nov-2025 | Anusharavaan Module: UI Enhancement for Contractor & Field Engineer Login including View Details, Log View & Inspection Request Form | Jal Rekha | Anusharavaan – RFI | UI/UX Redesign | Medium – Enhances contractor and FE login UI consistency | Completed | 22-Nov-2025 | Approved | Medium | Low | 120 | UI enhancements deployed to production
CR-ANU-007 | ANU-CR-2026-001 | Business Analyst | Senior BA | 10-Jan-2026 | Anusharavaan CR – RFI Stage Updations and Reports Modifications: MBR Changes for schemes, Inline Query to Function updates | Jal Rekha | Anusharavaan – RFI CR | Reporting & Analytics | High – Impacts RFI reporting for all scheme-level users; MBR changes affect financial accuracy | Completed | 20-Jan-2026 | Approved | High | Low | 21 | Deployed on 20-Nov-2025; verified on prod

## Asset Mapping CR
CHANGE REQUEST LOG – ASSET MAPPING CR ¦ Jal Rekha ¦ PHE, Madhya Pradesh ¦ January 2026 – May 2026
Module: Asset Mapping ¦ Department: Public Health Engineering ¦ Period: January 2026 – May 2026
CR No. | CR Code | CR Raised By | Req. Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Impl. Status | Impl. Date | Approval Status | Priority | Risk Level | Effort (Hrs) | Remarks
CR-AST-001 | AST-MAP-2026-001 | Business Analyst | Senior BA | 05-Jan-2026 | Search Box for OHT search on the Map in Asset Mapping module | Jal Rekha | Asset Mapping – OHT | UI/UX Redesign | Medium – Improves field user ability to locate OHTs on map quickly | Completed | 12-Jan-2026 | Approved | Medium | Low | 45 | OHT search box deployed
CR-AST-002 | AST-MAP-2026-002 | Business Analyst | Senior BA | 07-Jan-2026 | Redesigning & Redeployment of Asset Mapping pages on live server with updated UI | Jal Rekha | Asset Mapping – UI | UI/UX Redesign | High – Affects all asset mapping users; redesign improves consistency | Completed | 15-Jan-2026 | Approved | High | Low | 45 | Redesign deployed to live server
CR-AST-003 | AST-MAP-2026-003 | Business Analyst | Senior BA | 10-Jan-2026 | Accuracy Field changes for Asset Mapping and Data Get Method updates for SQC/TPIA | Jal Rekha | Asset Mapping – SQC/TPIA | Database Performance | Medium – Ensures correct asset location accuracy data is captured and retrieved | Completed | 20-Jan-2026 | Approved | Medium | Low | 60 | Accuracy field and Get API updated
CR-AST-004 | AST-MAP-2026-004 | QA Team | QA Lead | 12-Jan-2026 | SQC and OHT Village Testing Bug Fixing including bug resolution for OHT-village mapping | Jal Rekha | Asset Mapping – QA | Test Design & Coverage | Medium – Resolves mapping defects found during SQC testing | Completed | 22-Jan-2026 | Approved | Medium | Low | 60 | Bug fixes completed and verified in UAT
CR-AST-005 | AST-MAP-2026-005 | Business Analyst | Senior BA | 15-Jan-2026 | Report creation for SQC-TPIA Contractor login in Asset Mapping module | Jal Rekha | Asset Mapping – Reports | Report Generation | Medium – Provides SQC/TPIA contractor visibility of mapped asset data | Completed | 25-Jan-2026 | Approved | Medium | Low | 60 | Contractor login report created and deployed

## Bharosa CR
CHANGE REQUEST LOG – BHAROSA CR ¦ Jal Rekha ¦ PHE, Madhya Pradesh ¦ January 2026 – May 2026
Module: Bharosa – Factory Testing ¦ Department: Public Health Engineering ¦ Period: January 2026 – May 2026
CR No. | CR Code | CR Raised By | Req. Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Impl. Status | Impl. Date | Approval Status | Priority | Risk Level | Effort (Hrs) | Remarks
CR-BHR-FTW-001 | BHR-FTW-2025-001 | Business Analyst | Senior BA | 01-Nov-2025 | Bharosa Factory Testing Web – Redesign inner pages, Functionality to Upload Multiple Documents, QAP Document Upload, UI Update | Jal Rekha | Bharosa – Factory Testing Web | UI/UX Redesign | High – Directly affects usability for all factory testing web users, reducing navigation errors and training effort | Completed | 25-Nov-2025 | Approved | High | Medium | 94 | Deployed 25-Nov-2025; UAT cleared
CR-BHR-FTW-002 | BHR-FTW-2026-001 | Business Analyst | Senior BA | 03-Jan-2026 | Bharosa – Add input field for unit and display unit details; Save as Draft, Image & Video Upload functionality | Jal Rekha | Bharosa – Factory Testing Web | UI/UX Redesign | High – New unit fields and media upload functionality changes core factory testing flow | Completed | 12-Jan-2026 | Approved | High | Medium | 78 | Wireframing and implementation complete
CR-BHR-FTM-001 | BHR-FTM-2025-001 | Business Analyst | Senior BA | 18-Nov-2025 | Bharosa Factory Testing Mobile – Factory testing screens design, Draft Activity, Add Scheme, API integration, History API | Jal Rekha | Bharosa – Factory Testing Mobile | UI/UX Redesign | High – Enables field inspectors to perform factory testing on mobile; critical for offline operation | Completed | 05-Dec-2025 | Approved | High | Medium | 94 | Mobile APK deployed to production
CR-BHR-FTM-002 | BHR-FTM-2026-001 | Business Analyst | Senior BA | 05-Jan-2026 | Bharosa Factory Testing Mobile CR – Bug fixes, Mobile App functionality addition and updation | Jal Rekha | Bharosa – Factory Testing Mobile | UI/UX Redesign | Medium – Fixes mobile bugs identified in post-deployment testing | Completed | 15-Jan-2026 | Approved | Medium | Low | 58 | Mobile CR changes deployed
CR-BHR-RPT-001 | BHR-RPT-2025-001 | Business Analyst | Senior BA | 07-Dec-2025 | Bharosa CR – Report View: Change request in Bharosa Module (Factory Testing) Web & Mobile Reports; Assign Components to TPIA function | Jal Rekha | Bharosa – Factory Testing Reports | Report Generation | High – Report view changes affect GM, TPIA, and Contractor report access workflows | Completed | 14-Dec-2025 | Approved | High | Medium | 50 | Report view CR completed and deployed

## Dhara CR
CHANGE REQUEST LOG – DHARA CR ¦ Jal Rekha ¦ PHE, Madhya Pradesh ¦ January 2026 – May 2026
Module: Dhara – Meter & Reports ¦ Department: Public Health Engineering ¦ Period: January 2026 – May 2026
CR No. | CR Code | CR Raised By | Req. Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Impl. Status | Impl. Date | Approval Status | Priority | Risk Level | Effort (Hrs) | Remarks
CR-DHARA-RPT-001 | DHARA-RPT-2025-001 | Business Analyst | Senior BA | 13-Nov-2025 | Redesign Dhara pages of Jal Rekha to align with updated UI standards and navigation for water supply reports | Jal Rekha | Dhara – Reports | UI/UX – Dhara Pages | Medium – Improves usability of Dhara pages; reduces navigation issues for stakeholders | Completed | 13-Nov-2025 | Approved | Medium | Low | 22 | Dhara page redesign deployed
CR-DHARA-001 | DHARA-GM-2026-001 | Business Analyst | Senior BA | 06-Jan-2026 | Dhara – Intake Meter Survey form field sequence change for GM login: Survey Date, Scheme, Component, Meter Status, Start/End Reading, Total Raw Water (KL), FE Remark, GM Remark | Jal Rekha | Dhara – GM Meter Survey | Form & Workflow | High – Sequence change affects daily data entry for GM and FE across all schemes | Completed | 20-Jan-2026 | Approved | High | Medium | 96 | Intake meter survey form reordered per department requirement
CR-DHARA-002 | DHARA-GM-2026-002 | Business Analyst | Senior BA | 06-Jan-2026 | Dhara – WTP Meter Survey sequence change: Meter Name, Meter Status (disable Start/End if Non-Functional), WTP Reading Start/End, Total Clear Water (KL) | Jal Rekha | Dhara – GM Meter Survey | Form & Workflow | High – If meter non-functional, start and end fields disable automatically; critical business rule | Completed | 20-Jan-2026 | Approved | High | Medium | 96 | WTP meter survey form with conditional disable logic deployed
CR-DHARA-003 | DHARA-GM-2026-003 | Business Analyst | Senior BA | 06-Jan-2026 | Dhara – OHT Meter Survey renamed to OHT-WTP¦Village Meter Survey; new columns: Local Name, Village Meter Status, Village Reading, Total Clear Water in Village (KL) | Jal Rekha | Dhara – GM Meter Survey | Database Architecture | High – Schema change for OHT-Village meter survey; affects data model and all downstream reports | Completed | 25-Jan-2026 | Approved | High | Medium | 91 | OHT-Village meter survey renamed and new columns added
CR-DHARA-004 | DHARA-WF-2026-001 | Business Analyst | Senior BA | 10-Jan-2026 | Dhara – Meter Reading Approval Workflow: FE 5-day window → GM 3-day approval window → Contractor 3-day concern window → Auto-approval; dispute management at all login levels | Jal Rekha | Dhara – Approval Workflow | Workflow Management | High – Critical workflow change affecting all Dhara logins; FE, GM, Contractor roles impacted with defined time windows | In Progress | 28-Jan-2026 | Approved | High | High | 163 | Workflow logic defined and under development; auto-approval timer logic pending
CR-DHARA-005 | DHARA-RPT-2026-001 | Business Analyst | Senior BA | 12-Jan-2026 | Dhara CR Reports – MWSR, DWSR, UFW: Update, Recreate and Fetch; DWSR Detailed & Datewise Report; Bulk Consumer Approved Reports; Hyperlinks in all DWSR reports | Jal Rekha | Dhara – Reports CR | Report Generation | High – Core operational reports; DWSR accuracy and hyperlink navigation critical for department review | Completed | 26-Mar-2026 | Approved | High | Medium | 186 | DWSR, MWSR, UFW reports updated and deployed with hyperlinks
CR-DHARA-006 | DHARA-BULK-2026-001 | Business Analyst | Senior BA | 15-Jan-2026 | Dhara – Bulk Meter Consumer Reading Survey Form; Bulk Consumer addition and mapping separately with supply point local name per village; mobile view list format | Jal Rekha | Dhara – Bulk Consumer | Database Architecture | High – Bulk consumer supply point data structure change; impacts Dhara and O&M Billing module | Completed | 05-Feb-2026 | Approved | High | Medium | 163 | Bulk consumer mapping and survey form completed
CR-DHARA-007 | DHARA-CRIT-2026-001 | Business Analyst | Senior BA | 10-Jun-2026 | Dhara – Critical Issue: Multiple tapping points in Mohkhed scheme (Palakhed, Saroth, Ikalbehari, Jam, Mohkhed) – meter reading entry for one tapping point replicates to all tapping points of same village | Jal Rekha | Dhara – FE Mobile | Data Integrity | Critical – FE cannot enter separate meter readings for each tapping point; data integrity failure across multiple schemes | Not Done (Critical Issue) | TBD | Pending | High | High | TBD | Escalated to development team; fix not yet applied as of 10-Jun-2026
CR-DHARA-008 | DHARA-DWSR-2026-001 | Business Analyst | Senior BA | 10-Jun-2026 | Dhara – DWSR Approved data date issue: Approving a mid-month date (e.g., 6 April) shows 'approved up to 6 April' even when 1–5 April not approved; date display logic incorrect | Jal Rekha | Dhara – DWSR Reports | Reporting & Analytics | High – Misleading date display in DWSR approval report; affects billing accuracy for department | Not Done (Critical Issue) | TBD | Pending | High | Medium | TBD | Date logic defect identified; fix pending as of 10-Jun-2026
CR-DHARA-009 | DHARA-CONT-2026-001 | Business Analyst | Senior BA | 10-Jun-2026 | Dhara – All forms: Add 'Is Objection?', 'Is Approved?', 'Any Concern' with Contractor Remark and Upload Document View on all forms | Jal Rekha | Dhara – All Forms | Workflow Management | Medium – Enables contractor to raise concern or upload evidence; improves dispute tracking | In Progress | 30-Jun-2026 | Pending | Medium | Medium | 163 | Contractor objection UI and modal development completed; API integration in progress
CR-DHARA-010 | DHARA-SEC-2026-001 | Business Analyst | Senior BA | 28-Apr-2026 | Dhara – Site Security Audit: Sonarcube, SVN, Cross-Site Scripting DOM bug fixing, Password Encryption for all users, Query Optimization | Jal Rekha | Dhara – Security | Security | High – Security vulnerabilities must be resolved before production; affects all Jal Rekha modules | Completed | 29-Apr-2026 | Approved | High | High | 16 | Security audit completed; 50+ vulnerabilities resolved

## FHTC CR
CHANGE REQUEST LOG – FHTC CR ¦ Jal Rekha ¦ PHE, Madhya Pradesh ¦ January 2026 – May 2026
Module: FHTC – Functional HTC ¦ Department: Public Health Engineering ¦ Period: January 2026 – May 2026
CR No. | CR Code | CR Raised By | Req. Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Impl. Status | Impl. Date | Approval Status | Priority | Risk Level | Effort (Hrs) | Remarks
CR-FHTC-GM-001 | FHTC-GM-2025-001 | QA Team | QA Lead | 14-Nov-2025 | Create detailed test scenarios for FHTC module covering FE and GM login, report access flows, negative cases, and regression set | Jal Rekha | FHTC – GM/Contractor Reports | Test Design & Coverage | Medium – Ensures adequate regression coverage for FHTC module before and after CR deployment | Completed | 14-Nov-2025 | Approved | High | Medium | 8 | Test scenarios created; regression set established
CR-FHTC-001 | FHTC-CR-2025-001 | Business Analyst | Senior BA | 13-Oct-2025 | FHTC Change Request – Loop (Re-Inspection) Functionality for Contractor and FE login; History Screen, Accepted/Rejected List, Re-Inspection Form with API integration | Jal Rekha | FHTC – Contractor/FE | Workflow Management | High – Re-inspection loop adds critical quality-check workflow for FHTC tap connections | Completed | 29-Oct-2025 | Approved | High | Medium | 247 | FHTC loop functionality deployed to production
CR-FHTC-002 | FHTC-CR-2025-002 | Business Analyst | Senior BA | 01-Dec-2025 | FHTC CR – FE Reports Modification; Samagra API Integration (replacing NIC); Updated APK for new HSC Report; Contractor updates beneficiary tap with photograph | Jal Rekha | FHTC – FE Reports | Report Generation | High – Samagra API is mandatory for beneficiary data; NIC API decommissioned | Completed | 09-Dec-2025 | Approved | High | Medium | 334 | Samagra API integrated; FE reports modified and deployed
CR-FHTC-003 | FHTC-CR-2026-001 | Business Analyst | Senior BA | 05-Jan-2026 | FHTC – Add View Logs, Search Functionality for FE and Contractor login; Report Filter issues at column level; UI Enhancement; Modified Excel export with dynamic file name and hidden columns | Jal Rekha | FHTC – GM/Contractor/FE | Reporting & Analytics | Medium – Improves usability and report export quality for FHTC module | Completed | 15-Feb-2026 | Approved | Medium | Low | 296 | All FHTC UI and report enhancements deployed
CR-FHTC-004 | FHTC-AI-2026-001 | Business Analyst | Senior BA | 08-May-2026 | AI Module – FHTC Tap Connection: ML Model implementation for tap connection monitoring buffer region; Data Processing; Machine Learning Predictive Model; Image Processing using Roboflow | Jal Rekha | FHTC – AI Module | AI/ML | Medium – ML model for tap connection verification adds automated quality assurance | Completed | 23-May-2026 | Approved | Medium | Medium | 69 | ML model trained and deployed; buffer region validation active

## Master CR
CHANGE REQUEST LOG – MASTER CR ¦ Jal Rekha ¦ PHE, Madhya Pradesh ¦ January 2026 – May 2026
Module: Master – Data & Schema ¦ Department: Public Health Engineering ¦ Period: January 2026 – May 2026
CR No. | CR Code | CR Raised By | Req. Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Impl. Status | Impl. Date | Approval Status | Priority | Risk Level | Effort (Hrs) | Remarks
CR-MST-001 | MST-GM-2025-001 | Business Analyst | Senior BA | 01-Jul-2025 | Master CR – GM/Contractor: Option for Manual Entry for Components; Mapping village with components via Water Supply from other PIU Scheme; Pipeline master zone numbers at contractor level | Jal Rekha | Master – GM/Contractor | Database Architecture | High – Manual component entry and cross-PIU village mapping changes core master data structure | Completed | 19-Jul-2025 | Approved | High | Medium | 140 | Deployed 19-Jul-2025; WTP meter mapping enabled for 147 schemes
CR-MST-002 | MST-SCHEMA-2026-001 | Business Analyst | Senior BA | 18-Mar-2026 | Master CR – Schema: Bulk Consumer Master (Add-Update-Get); Delete functionality in Bulk Consumer Master; Dhara Mapped Summary Report Abstract changes; Dhara Master DWSR Updations | Jal Rekha | Master – Bulk Consumer / Schema | Database Architecture | High – Bulk consumer master schema changes affect Dhara, O&M Billing, and DWSR reports | Completed | 24-Mar-2026 | Approved | High | Medium | 73 | Bulk consumer master CRUD and delete functionality deployed
CR-MST-003 | MST-SV-2026-001 | Business Analyst | Senior BA | 11-Mar-2026 | Master CR – Scheme Village & OHT Master: Validation on 'Is Bulk Village', 'Is Water Supply Testing Started', 'Is Water Supply Permitted by GM PIU'; Census Population Integration; OHT Village Mapping updates with local name column | Jal Rekha | Master – Scheme Village / OHT | Database Architecture | High – Validation rules on scheme village master are prerequisite for Dhara and O&M billing; Census integration is critical | Completed | 19-Mar-2026 | Approved | High | High | 210 | Scheme Village and OHT master validations deployed; census population integrated
CR-MST-004 | MST-WTP-2026-001 | Business Analyst | Senior BA | 15-Mar-2026 | Master CR – WTP Meter Mapping: Table column fields increased (Meter Name, No of Connected OHT, Meter Type, Action Button); Pipeline Master Details and Report Pages addition | Jal Rekha | Master – WTP Meter Mapping | Database Architecture | Medium – WTP meter mapping enhancements support detailed meter tracking for Dhara module | Completed | 25-Mar-2026 | Approved | Medium | Low | 73 | WTP meter mapping page updated with new columns
CR-MST-005 | MST-VIS-2026-001 | Business Analyst | Senior BA | 20-Mar-2026 | Vistrit Summary Report – Mapped Status report changes in Summary Report and Abstract Report; Vistrit Screen divided into 2 sheets; Add Bulk Consumer with Agreement copy and Total Supply Points fields | Jal Rekha | Master – Vistrit / Reports | Report Generation | Medium – Summary and abstract reports require update for correct Vistrit data display | Completed | 28-Mar-2026 | Approved | Medium | Low | 255 | Vistrit Bulk Consumer and summary report changes deployed
CR-MST-006 | MST-BM-2026-001 | Business Analyst | Senior BA | 01-Apr-2026 | Master CR – Bulk Consumer Mapping: Multiple mapping of bulk consumers from same source enabled; Meter ID Column added for WTP; Habitation Code Duplicate Error on Re-mapping fixed | Jal Rekha | Master – Bulk Consumer Mapping | Database Architecture | High – Multiple bulk consumer mapping is a key functional requirement for supply point reporting | Completed | 15-Apr-2026 | Approved | High | Medium | 210 | Bulk consumer mapping with multi-source enabled and meter_id added

## Material CR
CHANGE REQUEST LOG – MATERIAL CR ¦ Jal Rekha ¦ PHE, Madhya Pradesh ¦ January 2026 – May 2026
Module: Material Testing ¦ Department: Public Health Engineering ¦ Period: January 2026 – May 2026
CR No. | CR Code | CR Raised By | Req. Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Impl. Status | Impl. Date | Approval Status | Priority | Risk Level | Effort (Hrs) | Remarks
CR-MAT-FE-2026-001 | MAT-FE-2025-001 | Business Analyst | Senior BA | 17-Dec-2025 | Material Testing – FE Login: Mobile app FE Login UI Enhancement, Save as Draft, OHT Search functionality; FE Inspection Form with Material Testing Parameters; Offline Data List and Detail Screen | Jal Rekha | Material Testing – FE Login | UI/UX Redesign | Medium – FE mobile login is primary data entry point for material testing; offline capability critical | Completed | 31-Dec-2025 | Approved | Medium | Low | 30 | FE login deployed to production; Material Testing mobile complete
CR-MAT-GM-2026-001 | MAT-GM-2026-001 | Business Analyst | Senior BA | 08-Dec-2025 | Material Testing – GM Login: GM/SQC/TPIA web pages and APIs; Contractor send request to GM; FE inspection sent to GM for approval; Customized Report creation; FE inspection date in PIU pending page | Jal Rekha | Material Testing – GM/Contractor Login | Workflow Management | High – GM approval workflow for material testing is critical quality gate for scheme infrastructure | Completed | 30-Dec-2025 | Approved | High | Medium | 471 | GM/SQC/TPIA login complete; approval workflow deployed
CR-MAT-CR-2026-001 | MAT-CR-2026-001 | QA Team | QA Lead | 01-Jan-2026 | Material Testing – UAT-CR Testing; Production Testing and Build Deployment; Bug Fixing from Database; Nirmal and Dhara Report cross-module bug fixes | Jal Rekha | Material Testing – CR / QA | Test Design & Coverage | Medium – UAT defects must be resolved before go-live; cross-module fixes affect Dhara and Nirmal | Completed | 15-Jan-2026 | Approved | Medium | Low | 43 | Material testing UAT CR cleared; deployed to production

## Nirmal CR
CHANGE REQUEST LOG – NIRMAL CR ¦ Jal Rekha ¦ PHE, Madhya Pradesh ¦ January 2026 – May 2026
Module: Nirmal – Water Quality ¦ Department: Public Health Engineering ¦ Period: January 2026 – May 2026
CR No. | CR Code | CR Raised By | Req. Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Impl. Status | Impl. Date | Approval Status | Priority | Risk Level | Effort (Hrs) | Remarks
CR-NIR-WTP-001 | NIR-WTP-2025-001 | Business Analyst | Senior BA | 27-Nov-2025 | Apply WTP report parameter changes in Nirmal as per latest departmental requirement; WTP, Intake buffer increase to 200m for raw water sample collection | Jal Rekha | Nirmal – WTP Report | Reporting – WTP | Medium – Keeps WTP reporting aligned with current parameters used by department | Completed | 27-Nov-2025 | Approved | Medium | Low | 123 | WTP parameter changes deployed; buffer increased to 200m
CR-NIR-OHT-2025-001 | NIR-OHT-2025-001 | Business Analyst | Senior BA | 09-Jul-2025 | Nirmal Change Request – WTP, OHT Report: Report parameter changes; Mobile app OHT/Intake/WTP functionality changes | Jal Rekha | Nirmal – WTP/OHT Report | Reporting – WTP | Medium – OHT and WTP report parameter changes required by department for water quality monitoring | Completed | 14-Jul-2025 | Approved | Medium | Low | 123 | OHT report parameters updated; mobile changes deployed
CR-NIR-BEN-2025-001 | NIR-BEN-2025-001 | Business Analyst | Senior BA | 01-Sep-2025 | Nirmal Change Request – Beneficiary Report: Range facility for Date; Water sample ID search; Action Remarks by Contractor and GM in drill-down; 2 additional drill-down levels | Jal Rekha | Nirmal – Beneficiary Report | Report Generation | High – Beneficiary water quality reports are key departmental deliverable; drill-down affects data accessibility | Completed | 08-Sep-2025 | Approved | High | Low | 20 | Beneficiary report with drill-down and action remarks deployed
CR-NIR-RAW-2025-001 | NIR-RAW-2025-001 | Business Analyst | Senior BA | 03-Dec-2025 | Nirmal – Raw Water Report: Range facility for Date; Water Sample ID search; 2 additional columns and drill-downs (passed/failed); Bell icon on comment popups; FE Remarks text change across all reports | Jal Rekha | Nirmal – Raw Water Report | Report Generation | High – Raw water quality reporting is a regulatory requirement; drill-down defects affect compliance | Completed | 14-Dec-2025 | Approved | High | Medium | 145 | Raw water report updated; all drill-down and search features deployed
CR-NIR-MOB-2026-001 | NIR-MOB-2026-001 | Business Analyst | Senior BA | 05-Jan-2026 | Nirmal FE Mobile – Change Request: Beneficiary History Report UI design and API integration; All Nirmal reports final production move; Residual Chlorine value disabled for WTP intake FRC test fix | Jal Rekha | Nirmal – FE Mobile CR | UI/UX Redesign | Medium – Beneficiary history UI is final pending deliverable for Nirmal module | Completed | 27-Jan-2026 | Approved | Medium | Low | 123 | Nirmal all changes moved to production

## O&M Billing CR
CHANGE REQUEST LOG – O&M BILLING CR ¦ Jal Rekha ¦ PHE, Madhya Pradesh ¦ January 2026 – May 2026
Module: O&M Billing ¦ Department: Public Health Engineering ¦ Period: January 2026 – May 2026
CR No. | CR Code | CR Raised By | Req. Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Impl. Status | Impl. Date | Approval Status | Priority | Risk Level | Effort (Hrs) | Remarks
CR-OMB-GM-001 | OMB-GM-2025-001 | Business Analyst | Senior BA | 22-Nov-2025 | O&M Billing GM – Show GM 24 PIUs data to Kapil admin user after save and submit; rename Kapil ID to 'GM PIU O&M'; fix for duplicate village mapping; correct PIU and contractor name display | Jal Rekha | O&M Billing – GM | Access & Visibility | Medium – Provides Kapil admin consolidated visibility of GM 24 PIUs billing data post submission | Completed | 22-Nov-2025 | Approved | Medium | Medium | 50 | GM 24 PIU data visibility deployed; Kapil ID renamed
CR-OMB-GM-002 | OMB-GM-2026-001 | Business Analyst | Senior BA | 02-Nov-2025 | O&M Billing GM CR – Save as Draft; Census Population hierarchy fix; SLBM Section 'Other' option in Norms/Penalty dropdowns; Type of Increment CPIW/Yearly calculation changes; GST services option; Document upload Yes/No with freeze | Jal Rekha | O&M Billing – GM CR | Workflow Management | High – CPIW calculation changes impact financial accuracy of O&M bills; document freeze logic is audit requirement | Completed | 31-Oct-2025 | Approved | High | Medium | 315 | GM CR changes deployed; CPIW calculation updated
CR-OMB-CONT-001 | OMB-CONT-2025-001 | Business Analyst | Senior BA | 27-Nov-2025 | O&M Billing Contractor CR – CPI Base year/month calculation; Bill generation for 64 schemes; Dhara/Nirmal approved reports in billing process; DWSR, MWSR, Bulk Consumer, UFW integration; Power Consumption – Upload electricity bills PDF; Manpower Vehicle Other sections freeze after save | Jal Rekha | O&M Billing – Contractor CR | Workflow Management | High – Contractor billing integration with Dhara and Nirmal is critical for RA bill generation accuracy | Completed | 02-Jan-2026 | Approved | High | High | 249 | Contractor billing CR fully deployed; 64 schemes billable
CR-OMB-CONT-002 | OMB-CONT-2026-001 | Business Analyst | Senior BA | 10-Jan-2026 | O&M Billing Contractor – Summary Page: Gross O&M Bill with editable field; Save Village Deduction Details; Final Bill Submission; Contractor Approval Page with Document Upload; Dynamic Button Visibility and Draft State Correction | Jal Rekha | O&M Billing – Contractor Summary | Workflow Management | High – Final bill submission is the key milestone for O&M billing cycle; approval page enables audit trail | Completed | 28-Feb-2026 | Approved | High | High | 290 | Final bill submission and contractor approval page deployed
CR-OMB-RPT-2026-001 | OMB-RPT-2026-001 | Business Analyst | Senior BA | 15-Jan-2026 | O&M Billing Reports – Village wise supply point MWSR; Approved Village Supply Point Village MWSR; Bulk Supply Point MWSR; Date wise DWSR; Dhara Scheme & Bulk consumer name changes; Remove duplicate records with validation | Jal Rekha | O&M Billing – Reports | Report Generation | High – MWSR and DWSR reports are core billing reports; duplicate data causes billing errors | Completed | 15-Mar-2026 | Approved | High | Medium | 296 | All O&M billing MWSR/DWSR reports deployed; validation added
CR-OMB-WF-2026-001 | OMB-WF-2026-001 | Business Analyst | Senior BA | 20-Sep-2025 | O&M Billing Workflow – Establish flow between GM, Contractor, CGM, PD, CFO, CA then MD for final bill approval; RA Bill generation with scheme id and contractor id; Edit option and resend to PIU GM | Jal Rekha | O&M Billing – Workflow | Workflow Management | High – Bill approval hierarchy is a regulatory requirement; incorrect flow delays payment disbursement | Completed | 26-Sep-2025 | Approved | High | High | 27 | O&M billing approval workflow fully implemented
CR-OMB-MAY-2026-001 | OMB-MAY-2026-001 | Business Analyst | Senior BA | 19-May-2026 | O&M Billing May 2026 Changes – Dhara report integration in O&M Billing; Census population addition in Scheme Master; Bill generation for 64 schemes verification; Dhara meter issue – multiple source points single reading (Critical – Not Fixed) | Jal Rekha | O&M Billing – May CR | Reporting & Analytics | High – Dhara meter multi-source issue causes incorrect billing data; census population needed for scheme master GM side report | Not Done (Critical Issue) | TBD | Pending | High | High | TBD | Dhara meter multi-source issue escalated; 14 of 15 items completed; meter issue pending fix

## Sahbhagita CR
CHANGE REQUEST LOG – SAHBHAGITA CR ¦ Jal Rekha ¦ PHE, Madhya Pradesh ¦ January 2026 – May 2026
Module: Sahbhagita – ISA/NGO ¦ Department: Public Health Engineering ¦ Period: January 2026 – May 2026
CR No. | CR Code | CR Raised By | Req. Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Impl. Status | Impl. Date | Approval Status | Priority | Risk Level | Effort (Hrs) | Remarks
CR-SHB-RPT-001 | SHB-RPT-2025-001 | Business Analyst | Senior BA | 22-Nov-2025 | Sahbhagita – Modify survey reports as per new layout; Role Based PIU Dropdown & Search Validation; Summary Page NGO Count Segregation fix; Video Upload option in activity | Jal Rekha | Sahbhagita – Reports | Reporting – Layout & Data | Medium – Aligns survey report layout and contents with the latest departmental format | Completed | 01-Dec-2025 | Approved | Medium | Low | 10 | Sahbhagita reports updated and deployed
CR-SHB-GM-001 | SHB-GM-2025-001 | Business Analyst | Senior BA | 15-Oct-2025 | Sahbhagita GM CR – Village-wise triggers for report view; Extra dropdown for Village in Survey Approval; ISA dependent on Scheme/District filter flow; Update Sahbhagita ISA Bill Form; Approval of Survey Reports new page | Jal Rekha | Sahbhagita – GM/PM | Workflow Management | Medium – ISA filter dependency on Scheme and District is a mandatory business rule for accurate report generation | Completed | 22-Oct-2025 | Approved | Medium | Low | 68 | Sahbhagita GM PM CR changes deployed
CR-SHB-GM-002 | SHB-GM-2025-002 | Business Analyst | Senior BA | 02-Dec-2025 | Sahbhagita Change Request GM/PM/Reports – CP Manager Page RA Bill Approval; Save as Draft functionality; ISO not showing according to scheme fix; Live issue resolution | Jal Rekha | Sahbhagita – GM/PM CR | Workflow Management | Medium – RA Bill approval in Sahbhagita is a payment gateway; ISO scheme mismatch is a live production defect | Completed | 11-Dec-2025 | Approved | Medium | Low | 36 | Sahbhagita CP Manager approval and draft save deployed
CR-SHB-CR-2026-001 | SHB-CR-2026-001 | Business Analyst | Senior BA | 12-May-2026 | Sahbhagita CR – Activity requires review from CP Manager and Payment approval from ISA; Sahbhagita Activities integrated with Payment functionality; ISA track activity and pass payment | Jal Rekha | Sahbhagita – Payment CR | Workflow Management | Medium – Payment integration with ISA and CP Manager is the final workflow gap in Sahbhagita module | Completed | 14-May-2026 | Approved | Medium | Low | 23 | Sahbhagita payment workflow integrated; CP Manager review gate added

## Cube Testing CR
CHANGE REQUEST LOG – CUBE TESTING CR ¦ Jal Rekha ¦ PHE, Madhya Pradesh ¦ January 2026 – May 2026
Module: Cube Testing ¦ Department: Public Health Engineering ¦ Period: January 2026 – May 2026
CR No. | CR Code | CR Raised By | Req. Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Impl. Status | Impl. Date | Approval Status | Priority | Risk Level | Effort (Hrs) | Remarks
CR-CUBE-CONT-2026-001 | CUBE-CONT-2026-001 | Business Analyst | Senior BA | 23-Mar-2026 | Cube Testing – Contractor Login: Create Cube Inspection by Contractor; RFI Survey Form API integration; Contractor history list with pagination; Wireframing and User Stories | Jal Rekha | Cube Testing – Contractor | Workflow Management | Medium – Contractor cube testing is a new quality control feature for construction inspections | Completed | 04-Apr-2026 | Approved | Medium | Low | 64 | Contractor cube testing module deployed
CR-CUBE-FE-2026-001 | CUBE-FE-2026-001 | Business Analyst | Senior BA | 09-Mar-2026 | Cube Testing – FE Login: FE surveys cube at 7th and 28th day; Sync API integration; Offline data list; 7-day and 28-day validation check implementation; Test Scenario and Case creation | Jal Rekha | Cube Testing – FE Login | Workflow Management | Medium – 7/28-day cube testing schedule is an IS code requirement for concrete quality assurance | Completed | 09-Apr-2026 | Approved | Medium | Low | 120 | FE cube testing with 7/28-day validation deployed
CR-CUBE-GM-2026-001 | CUBE-GM-2026-001 | Business Analyst | Senior BA | 31-Mar-2026 | Cube Testing – GM Login: Summary Reports on GM Login; GM Action Page; Pending for Action Page with 7 and 28-day scenario; Bug fixing; RFI request status update and list | Jal Rekha | Cube Testing – GM | Report Generation | Medium – GM summary and action reports are required for construction quality oversight | Completed | 11-May-2026 | Approved | Medium | Low | 51 | GM cube testing module deployed; RFI status update added – milestone delay noted
CR-CUBE-SQC-2026-001 | CUBE-SQC-2026-001 | Business Analyst | Senior BA | 02-Apr-2026 | Cube Testing – SQC/TPIA Login: Web Pages and API creation; approval workflow GM → SQC → TPIA; Bug fixing; Test Scenarios and Cases; End-to-End testing | Jal Rekha | Cube Testing – SQC/TPIA | Workflow Management | Medium – SQC/TPIA approval workflow is final quality gate for cube testing inspections | Completed | 07-Apr-2026 | Approved | Medium | Low | 47 | SQC/TPIA cube testing workflow deployed
CR-CUBE-CR-2026-001 | CUBE-CR-2026-001 | Business Analyst | Senior BA | 28-Apr-2026 | Cube Testing CR – Mandatory Multiple Image Upload; New web page creation; Option for Manual Entry for Components; End to End testing; SQC-TPIA test cases | Jal Rekha | Cube Testing – CR | UI/UX Redesign | Medium – Mandatory image upload ensures inspection evidence is captured; manual entry option for offline scenarios | Completed | 29-Apr-2026 | Approved | Medium | Low | 70 | Cube Testing CR deployed 29-Apr-2026

## SVS CR
CHANGE REQUEST LOG – SVS CR ¦ Jal Rekha ¦ PHE, Madhya Pradesh ¦ January 2026 – May 2026
Module: SVS – Water Supply Monitoring ¦ Department: Public Health Engineering ¦ Period: January 2026 – May 2026
CR No. | CR Code | CR Raised By | Req. Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Impl. Status | Impl. Date | Approval Status | Priority | Risk Level | Effort (Hrs) | Remarks
CR-SVS-001 | SVS-WSM-2026-001 | Business Analyst | Senior BA | 12-May-2026 | SVS – Water Supply Monitoring (Har Ghar Jal Yojana): New Module creation in Jal Rekha; Daily GP-level water supply monitoring; API fetch from Panchayat Darpan NIC; Village Master data integration; Wireframe and requirement preparation | Jal Rekha | SVS – Water Supply Monitoring | Database Architecture | Medium – New module aligned with Har Ghar Jal Yojana; NIC API integration critical for daily supply data | Completed | 20-May-2026 | Approved | Medium | Low | 67 | SVS water supply monitoring module deployed 20-May-2026
CR-SVS-002 | SVS-RPT-2026-001 | Business Analyst | Senior BA | 13-May-2026 | SVS – Water Supply Monitoring Report: Database Table and Function creation; Report development for daily supply monitoring; Public access report integration on Jal Rekha portal | Jal Rekha | SVS – Reports | Report Generation | Medium – Public reporting of daily water supply is a transparency mandate under JJM programme | Completed | 20-May-2026 | Approved | Medium | Low | 67 | SVS reports live on public portal
CR-SVS-003 | SVS-PUB-2026-001 | Business Analyst | Senior BA | 13-May-2026 | All Public Reports on Dashboard – All Dhara and DWSR reports made accessible on Jal Rekha public portal dashboard; restrict to Dhara and DWSR only on open platform | Jal Rekha | SVS – Public Dashboard | Access & Visibility | Medium – Public access to water supply data fulfils transparency requirements under JJM | Completed | 14-May-2026 | Approved | Medium | Low | 4 | All public reports live on dashboard 14-May-2026

## CMMI L5 Compliance
CMMI LEVEL 5 COMPLIANCE CHECKLIST – JAL REKHA CR LOG CYCLE 4
Control Point | Status | Evidence | Comments | Module | Cycle
Change Request Formalization | Compliant | CR Registry with unique IDs across all modules | All CRs have CR codes, CR numbers, and logging dates | All Modules | Cycle 4
Impact Assessment | Compliant | Detailed impact analysis for each CR | Impact areas and scope clearly defined in all CRs | All Modules | Cycle 4
Approval Workflow | Compliant | Approval status tracked for each CR | Formal workflow: Approved / Pending / In Review | All Modules | Cycle 4
Implementation Tracking | Compliant | Implementation dates and status for all CRs | Target dates and actual dates documented | All Modules | Cycle 4
Risk Management | Compliant | Risk levels assigned to each CR (Low/Medium/High) | Risk escalation for Critical Dhara and O&M issues | All Modules | Cycle 4
Configuration Management | Compliant | CR database maintained with version control | Version 1.5 – Complete cycle 4 CR log | All Modules | Cycle 4
Defect Tracking | Compliant | Internal testing, UAT, and production defects logged | Defect counts per module in Data Collection Sheet | All Modules | Cycle 4
Statistical Analysis | Compliant | Productivity, Code Rate, Test Rate regression model | CMMI L5 PPM – Regression Equation maintained | All Modules | Cycle 4
Effort Tracking | Compliant | Planned vs Actual effort tracked per module | Cycle 4 DC Sheet (Jan–May 2026) – fully populated | All Modules | Cycle 4
Open/Critical Issues | Non-Compliant – Action Required | 2 Critical issues: Dhara meter multi-tapping (CR-DHARA-007) and O&M Billing May 2026 (CR-OMB-MAY-2026-001) | Critical issues must be resolved in next sprint; root cause analysis required | Dhara / O&M | Cycle 4